## README
item | details
Dataset purpose | Synthetic training/evaluation corpus for SIH26122 Planning-to-Execution Bridge.
Important | This dataset is synthetic. It should be used to build the prototype, test extraction/matching, and optionally fine-tune a small model—not as evidence of real OIL project performance.
Primary task | Extract activity/event/status from messy site updates and link them to a canonical L5/L6 schedule activity.
Recommended training strategy | Do not train an LLM from scratch. Use an existing LLM for structured extraction and train/evaluate the matching layer using this labeled corpus.
Modalities | plain_text, whatsapp, email, voice_transcript, site_diary, word_document, pdf_text, excel_note, ms_project_update
Core labels | activity_code, event_type, status, progress_percent, actual_start, actual_finish, delay_reason, location, discipline
Decision labels | AUTO_ACCEPT, HUMAN_REVIEW, UNMATCHED_NEW_ACTIVITY
Suggested split | 70% train / 15% validation / 15% test, with ambiguous and unmatched examples kept as separate evaluation sets.
Matching recommendation | Embedding similarity + fuzzy token similarity + discipline/location/WBS constraints + confidence threshold.
Voice handling | Voice should first be converted to transcript; the same extraction pipeline then processes the transcript.
Word/PDF/email/WhatsApp handling | Treat the container as a source modality and normalize its text before extraction.
MS Project handling | Use structured fields when available, but also process free-text update notes because planners may enter comments rather than clean status fields.

## Schedule_Activities
activity_id | activity_code | activity_name | description | discipline | wbs_level | location | planned_start | planned_finish | planned_duration_days | unit
1 | CIV-F15-001 | Foundation F15 excavation | Foundation F15 excavation at Unit 2 | Civil | L6 | Unit 2 | 2026-09-07 | 2026-09-12 | 6 | m
2 | CIV-F15-002 | Foundation F15 reinforcement | Foundation F15 reinforcement at Unit 2 | Civil | L5 | Unit 2 | 2026-10-01 | 2026-10-03 | 3 | MT
3 | CIV-F15-003 | Foundation F15 concreting | Foundation F15 concreting at Unit 2 | Civil | L6 | Unit 2 | 2026-09-13 | 2026-09-16 | 4 | m
4 | CIV-R02-001 | Road R02 subgrade preparation | Road R02 subgrade preparation at Plant Area | Civil | L5 | Plant Area | 2026-09-15 | 2026-09-19 | 5 | nos
5 | CIV-R02-002 | Road R02 PCC laying | Road R02 PCC laying at Plant Area | Civil | L6 | Plant Area | 2026-09-04 | 2026-09-08 | 5 | m
6 | CIV-TK01-001 | Tank T01 foundation completion | Tank T01 foundation completion at Tank Farm | Civil | L5 | Tank Farm | 2026-09-20 | 2026-09-23 | 4 | m
7 | PIP-L23-001 | Erect Line 23 | Erect Line 23 at Unit 2 | Piping | L5 | Unit 2 | 2026-09-11 | 2026-09-15 | 5 | inch-dia
8 | PIP-L23-002 | Weld Line 23 | Weld Line 23 at Unit 2 | Piping | L5 | Unit 2 | 2026-09-16 | 2026-09-18 | 3 | %
9 | PIP-L23-003 | Hydrotest Line 23 | Hydrotest Line 23 at Unit 2 | Piping | L5 | Unit 2 | 2026-09-19 | 2026-09-22 | 4 | %
10 | PIP-L24-001 | Erect Line 24 | Erect Line 24 at Unit 2 | Piping | L6 | Unit 2 | 2026-10-04 | 2026-10-05 | 2 | nos
11 | PIP-L24-002 | Weld Line 24 | Weld Line 24 at Unit 2 | Piping | L6 | Unit 2 | 2026-09-19 | 2026-09-21 | 3 | m
12 | PIP-L24-003 | Hydrotest Line 24 | Hydrotest Line 24 at Unit 2 | Piping | L6 | Unit 2 | 2026-09-07 | 2026-09-10 | 4 | job
13 | PIP-L30-001 | Install 30-inch header | Install 30-inch header at Unit 1 | Piping | L6 | Unit 1 | 2026-09-16 | 2026-09-20 | 5 | %
14 | PIP-V12-001 | Install Valve V12 | Install Valve V12 at Unit 2 | Piping | L6 | Unit 2 | 2026-09-17 | 2026-09-22 | 6 | %
15 | MEC-P03-001 | Install Pump P03 | Install Pump P03 at Pump House | Mechanical | L6 | Pump House | 2026-09-24 | 2026-09-26 | 3 | inch-dia
16 | MEC-P04-001 | Align Pump P04 | Align Pump P04 at Pump House | Mechanical | L5 | Pump House | 2026-10-06 | 2026-10-10 | 5 | nos
17 | MEC-C01-001 | Install Compressor C01 | Install Compressor C01 at Compressor Area | Mechanical | L6 | Compressor Area | 2026-10-06 | 2026-10-07 | 2 | MT
18 | MEC-T02-001 | Install Tank T02 internals | Install Tank T02 internals at Tank Farm | Mechanical | L6 | Tank Farm | 2026-09-25 | 2026-09-26 | 2 | job
19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Install Heat Exchanger HX01 at Unit 1 | Mechanical | L6 | Unit 1 | 2026-09-03 | 2026-09-07 | 5 | nos
20 | ELE-MCC03-001 | Install MCC Panel 3 | Install MCC Panel 3 at Electrical Room | Electrical | L5 | Electrical Room | 2026-09-17 | 2026-09-21 | 5 | MT
21 | ELE-CBL07-001 | Lay Cable Route 7 | Lay Cable Route 7 at Unit 2 | Electrical | L6 | Unit 2 | 2026-09-17 | 2026-09-19 | 3 | inch-dia
22 | ELE-TR02-001 | Install Transformer TR02 | Install Transformer TR02 at Substation | Electrical | L6 | Substation | 2026-09-28 | 2026-10-01 | 4 | inch-dia
23 | ELE-LTG02-001 | Install Unit 2 lighting | Install Unit 2 lighting at Unit 2 | Electrical | L5 | Unit 2 | 2026-09-27 | 2026-10-01 | 5 | job
24 | INS-T04-001 | Install Temperature Transmitter T04 | Install Temperature Transmitter T04 at Unit 2 | Instrumentation | L5 | Unit 2 | 2026-09-12 | 2026-09-13 | 2 | %
25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Install Pressure Transmitter PT08 at Unit 1 | Instrumentation | L6 | Unit 1 | 2026-10-06 | 2026-10-10 | 5 | %
26 | INS-CV11-001 | Install Control Valve CV11 | Install Control Valve CV11 at Unit 2 | Instrumentation | L6 | Unit 2 | 2026-10-01 | 2026-10-05 | 5 | MT
27 | INS-JB05-001 | Terminate Junction Box JB05 | Terminate Junction Box JB05 at Unit 2 | Instrumentation | L6 | Unit 2 | 2026-09-18 | 2026-09-22 | 5 | job
28 | HSE-001-001 | Complete work-at-height inspection | Complete work-at-height inspection at Unit 2 | HSE | L6 | Unit 2 | 2026-09-15 | 2026-09-18 | 4 | job
29 | HSE-002-001 | Close scaffold inspection actions | Close scaffold inspection actions at Unit 1 | HSE | L6 | Unit 1 | 2026-09-11 | 2026-09-12 | 2 | nos

## Train_Updates
record_id | source_modality | source_container | event_date | project_code | raw_input | activity_id | activity_code | canonical_activity | discipline | location | event_type | status | progress_percent | actual_start | actual_finish | delay_reason | expected_next_action | requires_human_review | gold_match_confidence | source_language | dataset_split
UPD-00075 | ms_project_update | document | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: MS Project note: MEC-HX01-001 progress affected by QA/QC hold point not cleared; expected finish to move. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | planner review | FALSE | 0.961 | English | train
UPD-00474 | email | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-L24-001 Dear Team, Work is continuing on Erect Line 24. Regards, Site Supervisor FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-16 |  |  | mobilise crew | FALSE | 0.984 | English | train
UPD-01127 | voice_transcript | email | 2026-09-05 | OIL-UNIT2-DEMO | Uh, install transformer tr02 kicked off today. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 10 | 2026-09-05 |  |  | receive material | FALSE | 0.986 | English | train
UPD-01192 | excel_note | email | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: MEC-P04-001 ¦ Align Pump P04 ¦ BLOCKED ¦ insufficient manpower Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | insufficient manpower | update schedule | FALSE | 0.978 | English | train
UPD-01712 | excel_note | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: ELE-TR02-001 ¦ Install Transformer TR02 ¦ STARTED ¦ NA For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 10 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.933 | English | train
UPD-01675 | voice_transcript | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Today: Just to update you, erect line 23 is about 90% complete. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-12 |  |  | mobilise crew | FALSE | 0.976 | English | train
UPD-00548 | plain_text | document | 2026-09-10 | OIL-UNIT2-DEMO | DPR Update: Partial progress achieved on Erect Line 24. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-10 |  |  | resume after clearance | FALSE | 0.978 | English | train
UPD-01513 | plain_text | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Foundation F15 excavation remains not started. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.909 | English | train
UPD-01406 | whatsapp | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: Hydrotest Line 23 remains not started. 👍 For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.93 | English | train
UPD-00104 | word_document | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-17 Discipline: Electrical Observation: Lay Cable Route 7 is delayed because of valve not available at site. FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 40 |  |  | valve not available at site | resume after clearance | FALSE | 0.908 | English | train
UPD-00869 | pdf_text | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 partially completed today. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-19 |  |  | mobilise crew | FALSE | 0.924 | English | train
UPD-00082 | plain_text | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Planned work Terminate Junction Box JB05 did not commence. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.989 | English | train
UPD-00626 | pdf_text | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ MEC-P03-001 ¦ No start for Install Pump P03 today. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.922 | English | train
UPD-01038 | ms_project_update | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - MS Project update: MEC-T02-001 Actual % Complete = 40% as of 2026-09-16. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 40 | 2026-09-16 |  |  | mobilise crew | FALSE | 0.91 | English | train
UPD-01735 | email | email | 2026-09-17 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting completed today. Regards, Site Supervisor Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | continue work | FALSE | 0.99 | English | train
UPD-00604 | ms_project_update | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: MS Project update: ELE-TR02-001 Actual % Complete = 80% as of 2026-09-17. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 80 | 2026-09-17 |  |  | mobilise crew | FALSE | 0.947 | English | train
UPD-01701 | word_document | mobile | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-03 Discipline: Piping Observation: Partial progress achieved on Weld Line 23. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.908 | English | train
UPD-01101 | whatsapp | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: Hi, tank t01 foundation completion remains on hold due to access road blocked. Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | access road blocked | obtain permit | FALSE | 0.933 | English | train
UPD-00884 | site_diary | document | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-22 ¦ Unit 1 ¦ Install 30-inch header is in progress. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 50 | 2026-09-22 |  |  | continue work | FALSE | 0.979 | English | train
UPD-00904 | word_document | document | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-03 Discipline: Civil Observation: Foundation F15 excavation has resumed following resolution of the earlier issue. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 60 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.924 | English | train
UPD-00629 | whatsapp | document | 2026-09-30 | OIL-UNIT2-DEMO | Today: Weld Line 24 is behind plan owing to scaffold not ready. 👍 | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | scaffold not ready | mobilise crew | FALSE | 0.989 | English | train
UPD-01181 | site_diary | mobile | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-12 ¦ Unit 2 ¦ Install Control Valve CV11 will not be executed today. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.935 | English | train
UPD-00199 | email | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - ELE-CBL07-001 Dear Team, Lay Cable Route 7 could not proceed today due to material not received. Regards, Site Supervisor FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 30 |  |  | material not received | continue work | FALSE | 0.954 | English | train
UPD-00394 | email | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Work on Align Pump P04 was stopped because vendor technician not available. Regards, Site Supervisor Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 80 |  |  | vendor technician not available | resume after clearance | FALSE | 0.969 | English | train
UPD-00299 | ms_project_update | DPR | 2026-09-26 | OIL-UNIT2-DEMO | MS Project note: CIV-F15-001 status = CANCELLED. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.95 | English | train
UPD-01126 | plain_text | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Planned work Install Valve V12 did not commence. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.922 | English | train
UPD-01780 | excel_note | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | ELE-CBL07-001 ¦ Lay Cable Route 7 ¦ COMPLETED ¦ NA FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | receive material | FALSE | 0.918 | English | train
UPD-01509 | voice_transcript | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, work for lay cable route 7 is finished. Planner action required. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | complete inspection | FALSE | 0.941 | English | train
UPD-00482 | word_document | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-18 Discipline: Civil Observation: Road R02 subgrade preparation remains on hold due to insufficient manpower. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | insufficient manpower | obtain permit | FALSE | 0.922 | English | train
UPD-00192 | word_document | document | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-17 Discipline: Piping Observation: Install 30-inch header partially completed today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 50 | 2026-09-17 |  |  | receive material | FALSE | 0.918 | English | train
UPD-01317 | ms_project_update | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Today: MS Project note: PIP-L24-003 status = CANCELLED. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.978 | English | train
UPD-00283 | whatsapp | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: Work on Install Transformer TR02 was stopped because material not received. 👍 Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | delay | DELAYED | 30 |  |  | material not received | continue work | FALSE | 0.909 | English | train
UPD-01649 | whatsapp | document | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Line/area update: close scaffold insp. actions held up by access road blocked. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 60 |  |  | access road blocked | planner review | FALSE | 0.929 | English | train
UPD-01073 | voice_transcript | mobile | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that today's install control valve cv11 activity has been cancelled. Material expected tomorrow. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.982 | English | train
UPD-00820 | ms_project_update | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: MEC-HX01-001 status = NOT STARTED. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.979 | English | train
UPD-00920 | word_document | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-28 Discipline: Piping Observation: Execution of Erect Line 23 is blocked by late material inspection. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | continue work | FALSE | 0.919 | English | train
UPD-00071 | pdf_text | mobile | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ MEC-HX01-001 ¦ Execution of Install Heat Exchanger HX01 is blocked by inspection clearance pending. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | complete inspection | FALSE | 0.946 | English | train
UPD-00053 | email | mobile | 2026-09-21 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-P03-001 Dear Team, Crew resumed Install Pump P03 after clearance. Regards, Site Supervisor Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 10 | 2026-09-21 |  |  | planner review | FALSE | 0.984 | English | train
UPD-00732 | voice_transcript | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, no start for weld line 24 today. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.904 | English | train
UPD-00524 | site_diary | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-15 ¦ Substation ¦ Install Transformer TR02 done at site. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | obtain permit | FALSE | 0.931 | English | train
UPD-00862 | whatsapp | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Today: Sir, install 30-inch header resumed today after late material inspection was cleared. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 40 | 2026-09-30 |  |  | continue work | FALSE | 0.986 | English | train
UPD-00310 | word_document | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-22 Discipline: Electrical Observation: Lay Cable Route 7 is in progress. FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-22 |  |  | continue work | FALSE | 0.985 | English | train
UPD-01381 | ms_project_update | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Today: MS Project update: PIP-L24-002 actual start = 2026-09-23; work commenced. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 60 | 2026-09-23 |  |  | obtain permit | FALSE | 0.958 | English | train
UPD-01517 | email | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - CIV-F15-001 Dear Team, Only part of Foundation F15 excavation could be comp. today. Regards, Site Supervisor For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-21 |  |  | update schedule | FALSE | 0.919 | English | train
UPD-01789 | excel_note | DPR | 2026-09-29 | OIL-UNIT2-DEMO | CIV-R02-002 ¦ Road R02 PCC laying ¦ NOT STARTED ¦ NA Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.947 | English | train
UPD-00504 | voice_transcript | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Uh, execution of weld line 24 is blocked by insufficient manpower. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | obtain permit | FALSE | 0.973 | English | train
UPD-01244 | ms_project_update | mobile | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: ELE-CBL07-001 status = RESUMED. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 50 | 2026-09-20 |  |  | continue work | FALSE | 0.911 | English | train
UPD-01365 | excel_note | document | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ RESUMED ¦ NA Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 30 | 2026-09-23 |  |  | complete inspection | FALSE | 0.909 | English | train
UPD-00320 | email | document | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 could not proceed today due to insufficient manpower. Regards, Site Supervisor Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 60 |  |  | insufficient manpower | continue work | FALSE | 0.952 | English | train
UPD-01578 | word_document | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-11 Discipline: Civil Observation: Road R02 subgrade preparation is blocked pending valve not available at site. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | valve not available at site | complete inspection | FALSE | 0.909 | English | train
UPD-00328 | word_document | document | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-27 Discipline: Civil Observation: Work is continuing on Road R02 PCC laying. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 30 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.926 | English | train
UPD-00311 | word_document | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-15 Discipline: Instrumentation Observation: Cannot continue Install Control Valve CV11 until valve not available at site is resolved. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | receive material | FALSE | 0.923 | English | train
UPD-00450 | pdf_text | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 30-09-2026 ¦ INS-CV11-001 ¦ Crew mobilised and started Install Control Valve CV11. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 30 | 2026-09-30 |  |  | continue work | FALSE | 0.945 | English | train
UPD-01006 | site_diary | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-10 ¦ Electrical Room ¦ Install MCC Panel 3 resumed today after equipment breakdown was cleared. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 10 | 2026-09-10 |  |  | complete inspection | FALSE | 0.935 | English | train
UPD-01552 | whatsapp | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: Hi, install control valve cv11 is in progress. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-21 |  |  | complete inspection | FALSE | 0.987 | English | train
UPD-00730 | email | email | 2026-09-21 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - MEC-C01-001 Dear Team, Crew resumed Install Compressor C01 after clearance. Regards, Site Supervisor | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 10 | 2026-09-21 |  |  | continue work | FALSE | 0.978 | English | train
UPD-00773 | word_document | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-12 Discipline: Civil Observation: Tank T01 foundation completion done at site. Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | mobilise crew | FALSE | 0.956 | English | train
UPD-00298 | whatsapp | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Site Update: Hi, started install unit 2 lighting this morning. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 30 | 2026-09-15 |  |  | continue work | FALSE | 0.964 | English | train
UPD-00756 | pdf_text | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ CIV-F15-002 ¦ Foundation F15 reinforcement kicked off today. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 80 | 2026-09-20 |  |  | complete inspection | FALSE | 0.943 | English | train
UPD-00454 | word_document | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-04 Discipline: Piping Observation: Erect Line 24 has not started yet. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.949 | English | train
UPD-00096 | email | DPR | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Crew resumed Hydrotest Line 24 after clearance. Regards, Site Supervisor FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 10 | 2026-09-22 |  |  | obtain permit | FALSE | 0.985 | English | train
UPD-00781 | word_document | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-10 Discipline: HSE Observation: Close scaffold inspection actions has not started yet. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.946 | English | train
UPD-00729 | site_diary | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-01 ¦ Unit 2 ¦ Install Valve V12 will not be executed today. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.987 | English | train
UPD-00008 | voice_transcript | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Okay, today's update is that tank t01 foundation completion remains on hold due to shortage of 24-inch pipes. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | continue work | FALSE | 0.967 | English | train
UPD-01615 | ms_project_update | email | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: PIP-L24-001 status = IN PROGRESS. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-09 |  |  | planner review | FALSE | 0.975 | English | train
UPD-00453 | word_document | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-14 Discipline: Electrical Observation: No start for Lay Cable Route 7 today. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.923 | English | train
UPD-01495 | whatsapp | document | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: Sir, partial progress achieved on install valve v12. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-18 |  |  | update schedule | FALSE | 0.918 | English | train
UPD-00481 | pdf_text | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ INS-JB05-001 ¦ No progress on Terminate Junction Box JB05 today due to scaffold not ready. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 60 |  |  | scaffold not ready | planner review | FALSE | 0.978 | English | train
UPD-00174 | plain_text | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - Install Heat Exchanger HX01 has resumed following resolution of the earlier issue. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 80 | 2026-09-04 |  |  | obtain permit | FALSE | 0.901 | English | train
UPD-00422 | pdf_text | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 is behind plan owing to QA/QC hold point not cleared. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | QA/QC hold point not cleared | update schedule | FALSE | 0.984 | English | train
UPD-00782 | ms_project_update | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: MS Project update: MEC-HX01-001 marked 100% complete. Actual Finish: 2026-09-28. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | planner review | FALSE | 0.985 | English | train
UPD-01074 | plain_text | email | 2026-09-26 | OIL-UNIT2-DEMO | Today: Execution of Hydrotest Line 23 is blocked by inspection clearance pending. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | mobilise crew | FALSE | 0.978 | English | train
UPD-01586 | plain_text | email | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Install Pressure Transmitter PT08 has been completed at Unit 1. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | complete inspection | FALSE | 0.904 | English | train
UPD-00434 | email | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-L24-001 Dear Team, Erect Line 24 commenced at Unit 2. Regards, Site Supervisor FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-28 |  |  | continue work | FALSE | 0.982 | English | train
UPD-01184 | pdf_text | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ MEC-P03-001 ¦ Work for Install Pump P03 is finished. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | update schedule | FALSE | 0.906 | English | train
UPD-00202 | email | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - INS-CV11-001 Dear Team, Install Control Valve CV11 completed today. Regards, Site Supervisor Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | resume after clearance | FALSE | 0.963 | English | train
UPD-00578 | site_diary | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-07 ¦ Unit 2 ¦ Terminate Junction Box JB05 is blocked pending crane unavailable. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | crane unavailable | update schedule | FALSE | 0.901 | English | train
UPD-01612 | voice_transcript | document | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: So, basically, crew is currently working on erect line 23. Kindly update the plan. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-22 |  |  | mobilise crew | FALSE | 0.96 | English | train
UPD-00804 | excel_note | email | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-001 ¦ Foundation F15 excavation ¦ PARTIAL ¦ NA | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-29 |  |  | mobilise crew | FALSE | 0.954 | English | train
UPD-00713 | email | DPR | 2026-09-06 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - INS-CV11-001 Dear Team, Install Control Valve CV11 cancelled for today. Regards, Site Supervisor FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.901 | English | train
UPD-00686 | voice_transcript | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Supervisor update - So, basically, no start for close scaffold inspection actions today. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.975 | English | train
UPD-00513 | voice_transcript | mobile | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, today's install heat exchanger hx01 activity has been cancelled. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.928 | English | train
UPD-00957 | word_document | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-15 Discipline: Electrical Observation: Cannot continue Install Unit 2 lighting until rainfall at site is resolved. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | obtain permit | FALSE | 0.941 | English | train
UPD-01657 | whatsapp | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | Hi, crew is currently working on hydrotest line 24. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-06 |  |  | receive material | FALSE | 0.921 | English | train
UPD-00508 | word_document | document | 2026-09-08 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-08 Discipline: Civil Observation: Road R02 PCC laying completed today. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | update schedule | FALSE | 0.941 | English | train
UPD-01077 | pdf_text | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ ELE-LTG02-001 ¦ Work on Install Unit 2 lighting was stopped because drawing approval pending. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 70 |  |  | drawing approval pending | receive material | FALSE | 0.986 | English | train
UPD-01422 | word_document | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-08 Discipline: Piping Observation: Around 50% work completed on Hydrotest Line 24; balance is ongoing. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-08 |  |  | mobilise crew | FALSE | 0.929 | English | train
UPD-00913 | word_document | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-09 Discipline: Piping Observation: Weld Line 23 will not be executed today. Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.98 | English | train
UPD-01759 | plain_text | email | 2026-09-30 | OIL-UNIT2-DEMO | Progress note: Install Compressor C01 is delayed bcoz of scaffold not ready. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 10 |  |  | scaffold not ready | receive material | FALSE | 0.967 | English | train
UPD-00663 | plain_text | email | 2026-09-10 | OIL-UNIT2-DEMO | Supervisor update - Install Compressor C01 is blocked pending material not received. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | material not received | update schedule | FALSE | 0.965 | English | train
UPD-01584 | whatsapp | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Supervisor update - Line/area update: road r02 subgrade preparation is in progress. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 20 | 2026-09-11 |  |  | planner review | FALSE | 0.935 | English | train
UPD-00112 | excel_note | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ COMPLETED ¦ NA Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | receive material | FALSE | 0.983 | English | train
UPD-01659 | ms_project_update | email | 2026-09-09 | OIL-UNIT2-DEMO | Unit update: MS Project note: INS-PT08-001 status = CANCELLED. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.907 | English | train
UPD-00934 | pdf_text | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 resumed today after access road blocked was cleared. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 80 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.903 | English | train
UPD-01786 | ms_project_update | email | 2026-09-12 | OIL-UNIT2-DEMO | Today: MS Project update: CIV-F15-001 Actual % Complete = 30% as of 2026-09-12. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-12 |  |  | resume after clearance | FALSE | 0.917 | English | train
UPD-01778 | plain_text | email | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: Install Control Valve CV11 has not started yet. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.907 | English | train
UPD-00469 | ms_project_update | mobile | 2026-09-11 | OIL-UNIT2-DEMO | DPR Update: MS Project update: ELE-TR02-001 marked 100% complete. Actual Finish: 2026-09-11. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | planner review | FALSE | 0.976 | English | train
UPD-01455 | ms_project_update | DPR | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L23-001 status = NOT STARTED. Kindly update the plan. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.968 | English | train
UPD-00791 | pdf_text | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ PIP-L24-002 ¦ Started Weld Line 24 this morning. FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-11 |  |  | complete inspection | FALSE | 0.945 | English | train
UPD-00854 | whatsapp | document | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - Hi, work for install pressure transmitter pt08 is finished. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | complete inspection | FALSE | 0.962 | English | train
UPD-01515 | email | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - PIP-L23-003 Dear Team, Hydrotest Line 23 will not be executed today. Regards, Site Supervisor Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.941 | English | train
UPD-01076 | ms_project_update | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Site Update: MS Project note: PIP-L24-003 progress affected by rainfall at site; expected finish to move. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | complete inspection | FALSE | 0.918 | English | train
UPD-00500 | whatsapp | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Sir, lay cable route 7 cancelled for today. Planner action required. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.932 | English | train
UPD-00264 | word_document | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-22 Discipline: Electrical Observation: Lay Cable Route 7 is blocked pending rainfall at site. For information. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | complete inspection | FALSE | 0.923 | English | train
UPD-01228 | word_document | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-03 Discipline: Electrical Observation: Today's Install MCC Panel 3 activity has been cancelled. Material expected tomorrow. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.911 | English | train
UPD-01364 | excel_note | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - PIP-L24-003 ¦ Hydrotest Line 24 ¦ IN PROGRESS ¦ NA | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-08 |  |  | continue work | FALSE | 0.906 | English | train
UPD-01715 | excel_note | document | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ PARTIAL ¦ NA Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-12 |  |  | complete inspection | FALSE | 0.972 | English | train
UPD-01519 | voice_transcript | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Site Update: Uh, cannot continue weld line 24 until design revision pending is resolved. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | continue work | FALSE | 0.917 | English | train
UPD-00864 | ms_project_update | document | 2026-09-29 | OIL-UNIT2-DEMO | MS Project note: CIV-R02-001 status = CANCELLED. Kindly update the plan. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.945 | English | train
UPD-00768 | word_document | document | 2026-09-08 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-08 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 ongoing at Unit 2. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-08 |  |  | complete inspection | FALSE | 0.913 | English | train
UPD-01670 | site_diary | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-22 ¦ Substation ¦ Supervisor confirms Install Transformer TR02 completed. Please note. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | complete inspection | FALSE | 0.966 | English | train
UPD-00025 | whatsapp | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - Work for Install Pressure Transmitter PT08 is finished. 👍 Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | planner review | FALSE | 0.942 | English | train
UPD-01145 | email | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-F15-003 Dear Team, Crew mobilised and started Foundation F15 concreting. Regards, Site Supervisor For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 10 | 2026-09-08 |  |  | mobilise crew | FALSE | 0.943 | English | train
UPD-01614 | email | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Crew resumed Road R02 PCC laying after clearance. Regards, Site Supervisor Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 60 | 2026-09-03 |  |  | update schedule | FALSE | 0.959 | English | train
UPD-01435 | site_diary | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-12 ¦ Unit 2 ¦ Supervisor confirms Complete work-at-height inspection completed. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | complete inspection | FALSE | 0.96 | English | train
UPD-01289 | plain_text | email | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: Install Pressure Transmitter PT08 is complete as of today. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-21 | 2026-09-21 |  | receive material | FALSE | 0.986 | English | train
UPD-00334 | voice_transcript | DPR | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, crew is currently working on install transformer tr02. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 80 | 2026-09-23 |  |  | obtain permit | FALSE | 0.907 | English | train
UPD-00985 | excel_note | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ NOT STARTED ¦ NA Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.947 | English | train
UPD-00661 | ms_project_update | email | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: MS Project note: CIV-R02-002 progress affected by vendor technician not available; expected finish to move. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | vendor technician not available | complete inspection | FALSE | 0.962 | English | train
UPD-00757 | whatsapp | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | DPR Update: Hi, only part of install control valve cv11 could be completed today. Material expected tomorrow. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-09 |  |  | planner review | FALSE | 0.983 | English | train
UPD-01528 | pdf_text | email | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ ELE-CBL07-001 ¦ Crew resumed Lay Cable Route 7 after clearance. Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 10 | 2026-09-24 |  |  | planner review | FALSE | 0.929 | English | train
UPD-00752 | whatsapp | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Site Update: Hi, supervisor confirms complete work-at-height inspection completed. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | resume after clearance | FALSE | 0.922 | English | train
UPD-00553 | whatsapp | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | Supervisor update - Line/area update: today's install valve v12 activity has been cancelled. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.967 | English | train
UPD-00136 | ms_project_update | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Site Update: MS Project note: MEC-P03-001 status = RESUMED. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 20 | 2026-09-24 |  |  | planner review | FALSE | 0.961 | English | train
UPD-00129 | email | spreadsheet | 2026-09-21 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L24-002 Dear Team, Work on Weld Line 24 restarted today. Regards, Site Supervisor Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 20 | 2026-09-21 |  |  | mobilise crew | FALSE | 0.952 | English | train
UPD-01629 | email | document | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - INS-CV11-001 Dear Team, Install Control Valve CV11 remains on hold due to material not received. Regards, Site Supervisor Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | update schedule | FALSE | 0.943 | English | train
UPD-00793 | word_document | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-12 Discipline: Mechanical Observation: Install Compressor C01 remains on hold due to client approval pending. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | client approval pending | planner review | FALSE | 0.919 | English | train
UPD-01650 | site_diary | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-17 ¦ Electrical Room ¦ Install MCC Panel 3 is behind plan owing to valve not available at site. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | delay | DELAYED | 80 |  |  | valve not available at site | receive material | FALSE | 0.977 | English | train
UPD-01155 | ms_project_update | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | MS Project note: PIP-V12-001 status = NOT STARTED. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.985 | English | train
UPD-00981 | plain_text | document | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Cannot continue Complete work-at-height inspection until late material inspection is resolved. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | obtain permit | FALSE | 0.948 | English | train
UPD-00708 | whatsapp | document | 2026-09-01 | OIL-UNIT2-DEMO | Line/area update: weld line 24 kicked off today. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-01 |  |  | continue work | FALSE | 0.937 | English | train
UPD-01428 | word_document | document | 2026-09-24 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-24 Discipline: Civil Observation: Planned work Road R02 subgrade preparation did not commence. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.977 | English | train
UPD-00163 | excel_note | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: INS-CV11-001 ¦ Install Control Valve CV11 ¦ COMPLETED ¦ NA | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | planner review | FALSE | 0.951 | English | train
UPD-00024 | email | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-F15-002 Dear Team, Foundation F15 reinforcement will not be executed today. Regards, Site Supervisor For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.911 | English | train
UPD-01448 | plain_text | document | 2026-09-10 | OIL-UNIT2-DEMO | Install Transformer TR02 started today. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 70 | 2026-09-10 |  |  | obtain permit | FALSE | 0.925 | English | train
UPD-01488 | excel_note | mobile | 2026-09-15 | OIL-UNIT2-DEMO | CIV-R02-001 ¦ Road R02 subgrade preparation ¦ STARTED ¦ NA For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 20 | 2026-09-15 |  |  | complete inspection | FALSE | 0.922 | English | train
UPD-01611 | pdf_text | email | 2026-09-20 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ HSE-001-001 ¦ Complete work-at-height inspection is about 50% complete. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-20 |  |  | complete inspection | FALSE | 0.918 | English | train
UPD-00448 | pdf_text | mobile | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 26-09-2026 ¦ CIV-F15-001 ¦ Team finished Foundation F15 excavation. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | obtain permit | FALSE | 0.927 | English | train
UPD-00669 | site_diary | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Today: Date 2026-09-11 ¦ Unit 2 ¦ Today's Complete work-at-height inspection activity has been cancelled. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.967 | English | train
UPD-00393 | plain_text | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Site Update: Install Valve V12 remains on hold due to insufficient manpower. Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | mobilise crew | FALSE | 0.952 | English | train
UPD-00569 | excel_note | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: MEC-T02-001 ¦ Install Tank T02 internals ¦ NOT STARTED ¦ NA Material expected tomorrow. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.979 | English | train
UPD-00052 | voice_transcript | DPR | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Just to update you, weld line 24 is about 80% complete. FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-18 |  |  | planner review | FALSE | 0.921 | English | train
UPD-00449 | voice_transcript | DPR | 2026-09-26 | OIL-UNIT2-DEMO | DPR Update: Just to update you, crew mobilised and started terminate junction box jb05. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-26 |  |  | obtain permit | FALSE | 0.915 | English | train
UPD-00531 | voice_transcript | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: So, basically, hydrotest line 23 is delayed because of equipment breakdown. Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | equipment breakdown | planner review | FALSE | 0.953 | English | train
UPD-00509 | email | mobile | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Work on Install Heat Exchanger HX01 has begun. Regards, Site Supervisor Kindly update the plan. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 30 | 2026-09-10 |  |  | continue work | FALSE | 0.91 | English | train
UPD-01225 | pdf_text | spreadsheet | 2026-09-17 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 17-09-2026 ¦ MEC-C01-001 ¦ Execution of Install Compressor C01 is blocked by scaffold not ready. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | scaffold not ready | receive material | FALSE | 0.971 | English | train
UPD-00506 | ms_project_update | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: MS Project note: INS-PT08-001 status = NOT STARTED. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.976 | English | train
UPD-00943 | word_document | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-24 Discipline: Piping Observation: Today's Install Valve V12 activity has been cancelled. Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.941 | English | train
UPD-00556 | email | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting held up by insufficient manpower. Regards, Site Supervisor | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 80 |  |  | insufficient manpower | mobilise crew | FALSE | 0.963 | English | train
UPD-01272 | site_diary | mobile | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-29 ¦ Unit 2 ¦ Weld Line 23 will not be executed today. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.949 | English | train
UPD-00451 | plain_text | document | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Today's Road R02 subgrade preparation activity has been cancelled. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.987 | English | train
UPD-00126 | excel_note | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | Today: PIP-L24-003 ¦ Hydrotest Line 24 ¦ RESUMED ¦ NA | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 10 | 2026-09-24 |  |  | receive material | FALSE | 0.901 | English | train
UPD-00890 | excel_note | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: CIV-F15-003 ¦ Foundation F15 concreting ¦ DELAYED ¦ equipment breakdown FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 80 |  |  | equipment breakdown | mobilise crew | FALSE | 0.944 | English | train
UPD-00496 | whatsapp | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Supervisor update - Sir, today's install pressure transmitter pt08 activity has been cancelled. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.928 | English | train
UPD-00371 | email | mobile | 2026-09-25 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Crew resumed Install 30-inch header after clearance. Regards, Site Supervisor Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 10 | 2026-09-25 |  |  | receive material | FALSE | 0.907 | English | train
UPD-00215 | pdf_text | document | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 partially completed today. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 40 | 2026-09-25 |  |  | obtain permit | FALSE | 0.929 | English | train
UPD-01019 | voice_transcript | document | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, foundation f15 concreting commenced at unit 2. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 40 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.926 | English | train
UPD-01134 | pdf_text | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 is in progress. For information. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-18 |  |  | resume after clearance | FALSE | 0.938 | English | train
UPD-01497 | site_diary | document | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-27 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 resumed today after crane unavailable was cleared. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 20 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.985 | English | train
UPD-01543 | ms_project_update | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Today: MS Project update: MEC-P04-001 Actual % Complete = 50% as of 2026-09-11. Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 50 | 2026-09-11 |  |  | mobilise crew | FALSE | 0.954 | English | train
UPD-00912 | pdf_text | DPR | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 02-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 remains on hold due to work permit not issued. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | mobilise crew | FALSE | 0.949 | English | train
UPD-01153 | voice_transcript | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Uh, install compressor c01 partially completed today. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 80 | 2026-09-25 |  |  | resume after clearance | FALSE | 0.939 | English | train
UPD-00414 | word_document | document | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-07 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 has not started yet. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.966 | English | train
UPD-01486 | ms_project_update | DPR | 2026-09-21 | OIL-UNIT2-DEMO | MS Project update: ELE-LTG02-001 Actual % Complete = 30% as of 2026-09-21. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-21 |  |  | planner review | FALSE | 0.904 | English | train
UPD-01359 | excel_note | DPR | 2026-09-12 | OIL-UNIT2-DEMO | INS-T04-001 ¦ Install Temperature Transmitter T04 ¦ RESUMED ¦ NA For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 40 | 2026-09-12 |  |  | continue work | FALSE | 0.959 | English | train
UPD-01098 | ms_project_update | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: MS Project update: MEC-P04-001 marked 100% complete. Actual Finish: 2026-09-03. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-03 | 2026-09-03 |  | resume after clearance | FALSE | 0.952 | English | train
UPD-01658 | ms_project_update | site_diary | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - MS Project update: PIP-L23-001 Actual % Complete = 25% as of 2026-09-03. FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.948 | English | train
UPD-00051 | site_diary | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-17 ¦ Unit 2 ¦ Crew mobilised and started Erect Line 23. Kindly update the plan. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.907 | English | train
UPD-00735 | email | email | 2026-09-14 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - HSE-001-001 Dear Team, Work is continuing on Complete work-at-height inspection. Regards, Site Supervisor Kindly update the plan. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-14 |  |  | resume after clearance | FALSE | 0.945 | English | train
UPD-00457 | plain_text | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Foundation F15 concreting partially completed today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-20 |  |  | complete inspection | FALSE | 0.96 | English | train
UPD-00212 | site_diary | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Date 2026-09-19 ¦ Unit 2 ¦ Install Temperature Transmitter T04 is complete as of today. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | continue work | FALSE | 0.917 | English | train
UPD-00037 | word_document | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-19 Discipline: Instrumentation Observation: Partial progress achieved on Install Pressure Transmitter PT08. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 75 | 2026-09-19 |  |  | complete inspection | FALSE | 0.954 | English | train
UPD-00313 | plain_text | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Erect Line 23 completed today. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | receive material | FALSE | 0.902 | English | train
UPD-00891 | email | document | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting is delayed bcoz of late material inspection. Regards, Site Supervisor Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 10 |  |  | late material inspection | resume after clearance | FALSE | 0.974 | English | train
UPD-00329 | voice_transcript | document | 2026-09-09 | OIL-UNIT2-DEMO | Just to update you, work on tank t01 foundation completion restarted today. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 80 | 2026-09-09 |  |  | resume after clearance | FALSE | 0.904 | English | train
UPD-01547 | site_diary | MS_Project | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-25 ¦ Unit 2 ¦ Crew mobilised and started Complete work-at-height inspection. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | start | STARTED | 40 | 2026-09-25 |  |  | obtain permit | FALSE | 0.919 | English | train
UPD-00083 | pdf_text | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ HSE-002-001 ¦ Crew is currently working on Close scaffold inspection actions. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | progress | IN_PROGRESS | 70 | 2026-09-28 |  |  | planner review | FALSE | 0.95 | English | train
UPD-01356 | word_document | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-07 Discipline: Mechanical Observation: Cannot continue Install Tank T02 internals until scaffold not ready is resolved. Material expected tomorrow. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | blockage | BLOCKED | 0 |  |  | scaffold not ready | receive material | FALSE | 0.901 | English | train
UPD-01774 | site_diary | email | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-28 ¦ Unit 2 ¦ Execution of Foundation F15 excavation is blocked by rainfall at site. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | planner review | FALSE | 0.958 | English | train
UPD-01587 | voice_transcript | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Today: Uh, road r02 pcc laying remains on hold due to rainfall at site. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | rainfall at site | resume after clearance | FALSE | 0.939 | English | train
UPD-01189 | plain_text | email | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - No progress on Hydrotest Line 24 today due to crane unavailable. Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | crane unavailable | resume after clearance | FALSE | 0.974 | English | train
UPD-00389 | site_diary | mobile | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-20 ¦ Unit 1 ¦ Install Heat Exchanger HX01 completed today. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | obtain permit | FALSE | 0.93 | English | train
UPD-00993 | email | email | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - MEC-P03-001 Dear Team, Install Pump P03 is complete as of today. Regards, Site Supervisor Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | resume after clearance | FALSE | 0.919 | English | train
UPD-01265 | pdf_text | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ CIV-F15-003 ¦ Partial progress achieved on Foundation F15 concreting. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.93 | English | train
UPD-00087 | ms_project_update | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: CIV-F15-003 progress affected by crane unavailable; expected finish to move. Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 60 |  |  | crane unavailable | resume after clearance | FALSE | 0.934 | English | train
UPD-01633 | whatsapp | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | Progress note: Team finished Install Temperature Transmitter T04. 👍 Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | mobilise crew | FALSE | 0.928 | English | train
UPD-01474 | excel_note | spreadsheet | 2026-09-21 | OIL-UNIT2-DEMO | MEC-P03-001 ¦ Install Pump P03 ¦ PARTIAL ¦ NA | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 60 | 2026-09-21 |  |  | mobilise crew | FALSE | 0.937 | English | train
UPD-01708 | email | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - PIP-L24-001 Dear Team, Erect Line 24 remains not started. Regards, Site Supervisor For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.976 | English | train
UPD-01186 | excel_note | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: INS-PT08-001 ¦ Install Pressure Transmitter PT08 ¦ RESUMED ¦ NA | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 60 | 2026-09-29 |  |  | obtain permit | FALSE | 0.911 | English | train
UPD-01494 | plain_text | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | Install Unit 2 lighting is blocked pending late material inspection. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | obtain permit | FALSE | 0.929 | English | train
UPD-01733 | ms_project_update | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Today: MS Project note: PIP-L24-002 status = NOT STARTED. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.934 | English | train
UPD-00198 | plain_text | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Progress note: Work is continuing on Install 30-inch header. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 80 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.95 | English | train
UPD-00907 | plain_text | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Today: Foundation F15 reinforcement will not be executed today. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.963 | English | train
UPD-00285 | whatsapp | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: Hi, partial progress achieved on tank t01 foundation completion. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 20 | 2026-09-24 |  |  | complete inspection | FALSE | 0.966 | English | train
UPD-01266 | ms_project_update | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: MS Project note: ELE-TR02-001 progress affected by safety clearance pending; expected finish to move. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | delay | DELAYED | 80 |  |  | safety clearance pending | planner review | FALSE | 0.979 | English | train
UPD-00831 | email | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - HSE-001-001 Dear Team, Complete work-at-height inspection will not be executed today. Regards, Site Supervisor | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.908 | English | train
UPD-00034 | excel_note | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | Daily Progress: CIV-F15-003 ¦ Foundation F15 concreting ¦ COMPLETED ¦ NA | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | update schedule | FALSE | 0.946 | English | train
UPD-01128 | plain_text | document | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: Only part of Install Control Valve CV11 could be completed today. Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-10 |  |  | receive material | FALSE | 0.945 | English | train
UPD-01278 | word_document | document | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-08 Discipline: Electrical Observation: Today's Install Unit 2 lighting activity has been cancelled. FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.927 | English | train
UPD-00268 | excel_note | mobile | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: MEC-P03-001 ¦ Install Pump P03 ¦ IN PROGRESS ¦ NA Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 80 | 2026-09-24 |  |  | resume after clearance | FALSE | 0.987 | English | train
UPD-01413 | email | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation is complete as of today. Regards, Site Supervisor For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | planner review | FALSE | 0.966 | English | train
UPD-01546 | site_diary | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Date 2026-09-30 ¦ Unit 2 ¦ Install Control Valve CV11 remains not started. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.936 | English | train
UPD-00956 | voice_transcript | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Uh, install tank t02 internals remains on hold due to matl not received. FYI. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | blockage | BLOCKED | 0 |  |  | material not received | update schedule | FALSE | 0.917 | English | train
UPD-00064 | plain_text | document | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: Tank T01 foundation completion resumed today after QA/QC hold point not cleared was cleared. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 60 | 2026-09-18 |  |  | complete inspection | FALSE | 0.923 | English | train
UPD-00387 | email | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - CIV-F15-001 Dear Team, Cannot continue Foundation F15 excavation until client approval pending is resolved. Regards, Site Supervisor Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | continue work | FALSE | 0.959 | English | train
UPD-01158 | word_document | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-27 Discipline: Mechanical Observation: Install Pump P03 is about 60% complete. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 60 | 2026-09-27 |  |  | complete inspection | FALSE | 0.919 | English | train
UPD-00871 | plain_text | mobile | 2026-09-20 | OIL-UNIT2-DEMO | Supervisor update - Cannot continue Install Pressure Transmitter PT08 until valve not available at site is resolved. Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | valve not available at site | planner review | FALSE | 0.962 | English | train
UPD-00214 | plain_text | mobile | 2026-09-10 | OIL-UNIT2-DEMO | DPR Update: Install Control Valve CV11 partially completed today. Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-10 |  |  | update schedule | FALSE | 0.945 | English | train
UPD-00419 | whatsapp | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | Hi, crew resumed terminate junction box jb05 after clearance. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | resumption | RESUMED | 60 | 2026-09-07 |  |  | complete inspection | FALSE | 0.957 | English | train
UPD-01400 | ms_project_update | email | 2026-09-11 | OIL-UNIT2-DEMO | DPR Update: MS Project note: INS-T04-001 status = RESUMED. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 80 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.945 | English | train
UPD-01696 | email | MS_Project | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Install MCC Panel 3 progressing as planned. Regards, Site Supervisor Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 40 | 2026-09-26 |  |  | obtain permit | FALSE | 0.973 | English | train
UPD-00723 | whatsapp | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: Sir, only part of install pump p03 could be completed today. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 70 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.969 | English | train
UPD-00431 | email | document | 2026-09-19 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - PIP-V12-001 Dear Team, Work for Install Valve V12 is finished. Regards, Site Supervisor | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | planner review | FALSE | 0.929 | English | train
UPD-00740 | plain_text | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: Install Temperature Transmitter T04 will not be executed today. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.94 | English | train
UPD-00343 | ms_project_update | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-L24-003 status = CANCELLED. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.939 | English | train
UPD-00275 | ms_project_update | email | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: MS Project update: MEC-P03-001 marked 100% complete. Actual Finish: 2026-09-18. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | update schedule | FALSE | 0.981 | English | train
UPD-00267 | whatsapp | MS_Project | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: Line/area update: cannot continue install 30-inch header until insufficient manpower is resolved. Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | insufficient manpower | receive material | FALSE | 0.932 | English | train
UPD-00169 | site_diary | document | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-23 ¦ Unit 2 ¦ Work for Install Temperature Transmitter T04 is finished. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | receive material | FALSE | 0.973 | English | train
UPD-00295 | pdf_text | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ INS-CV11-001 ¦ Execution of Install Control Valve CV11 is blocked by client approval pending. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | receive material | FALSE | 0.971 | English | train
UPD-01363 | ms_project_update | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: MS Project note: MEC-HX01-001 progress affected by safety clearance pending; expected finish to move. Kindly update the plan. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | safety clearance pending | update schedule | FALSE | 0.941 | English | train
UPD-01671 | excel_note | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: HSE-001-001 ¦ Complete work-at-height inspection ¦ DELAYED ¦ welding machine under maintenance Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | delay | DELAYED | 30 |  |  | welding machine under maintenance | mobilise crew | FALSE | 0.944 | English | train
UPD-01537 | ms_project_update | DPR | 2026-09-17 | OIL-UNIT2-DEMO | MS Project update: CIV-F15-003 marked 100% complete. Actual Finish: 2026-09-17. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | continue work | FALSE | 0.953 | English | train
UPD-01111 | whatsapp | mobile | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: Sir, erect line 23 resumed today after safety clearance pending was cleared. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | resumption | RESUMED | 80 | 2026-09-20 |  |  | continue work | FALSE | 0.974 | English | train
UPD-01410 | plain_text | mobile | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: Today's Install Pump P03 activity has been cancelled. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.969 | English | train
UPD-01120 | voice_transcript | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: Uh, around 50% work completed on road r02 pcc laying; balance is ongoing. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 60 | 2026-09-16 |  |  | continue work | FALSE | 0.924 | English | train
UPD-00397 | voice_transcript | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that align pump p04 will not be executed today. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.936 | English | train
UPD-00108 | excel_note | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ BLOCKED ¦ inspection clearance pending For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | update schedule | FALSE | 0.918 | English | train
UPD-01083 | pdf_text | site_diary | 2026-09-09 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 will not be executed today. For information. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.967 | English | train
UPD-00255 | email | document | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Install MCC Panel 3 cancelled for today. Regards, Site Supervisor Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.943 | English | train
UPD-00131 | plain_text | spreadsheet | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: Road R02 PCC laying started today. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 70 | 2026-09-02 |  |  | continue work | FALSE | 0.904 | English | train
UPD-00114 | ms_project_update | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Today: MS Project update: HSE-001-001 marked 100% complete. Actual Finish: 2026-09-27. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | continue work | FALSE | 0.974 | English | train
UPD-01216 | email | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 is complete as of today. Regards, Site Supervisor For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | resume after clearance | FALSE | 0.946 | English | train
UPD-00210 | whatsapp | document | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: Hi, only part of tank t01 foundation completion could be completed today. Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 25 | 2026-09-03 |  |  | planner review | FALSE | 0.988 | English | train
UPD-00078 | excel_note | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Daily Progress: CIV-R02-001 ¦ Road R02 subgrade preparation ¦ BLOCKED ¦ safety clearance pending Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | safety clearance pending | planner review | FALSE | 0.937 | English | train
UPD-00073 | whatsapp | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: Hi, work is continuing on lay cable route 7. For information. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-28 |  |  | complete inspection | FALSE | 0.971 | English | train
UPD-01692 | site_diary | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-24 ¦ Electrical Room ¦ Install MCC Panel 3 has resumed following resolution of the earlier issue. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 10 | 2026-09-24 |  |  | obtain permit | FALSE | 0.986 | English | train
UPD-01431 | pdf_text | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 has not started yet. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.938 | English | train
UPD-01343 | pdf_text | email | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 partially completed today. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-28 |  |  | complete inspection | FALSE | 0.931 | English | train
UPD-01011 | ms_project_update | email | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: MS Project note: MEC-C01-001 status = RESUMED. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 30 | 2026-09-28 |  |  | receive material | FALSE | 0.965 | English | train
UPD-01719 | email | document | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - HSE-002-001 Dear Team, Close scaffold inspection actions is delayed because of design revision pending. Regards, Site Supervisor | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 60 |  |  | design revision pending | complete inspection | FALSE | 0.981 | English | train
UPD-00997 | email | mobile | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-TK01-001 Dear Team, Crew is currently working on Tank T01 foundation completion. Regards, Site Supervisor Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | progress | IN_PROGRESS | 70 | 2026-09-24 |  |  | resume after clearance | FALSE | 0.978 | English | train
UPD-00461 | site_diary | email | 2026-09-02 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-02 ¦ Unit 2 ¦ Only part of Erect Line 24 could be completed today. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-02 |  |  | planner review | FALSE | 0.944 | English | train
UPD-01732 | voice_transcript | email | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that install compressor c01 is behind plan owing to design revision pending. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 10 |  |  | design revision pending | update schedule | FALSE | 0.926 | English | train
UPD-00175 | plain_text | MS_Project | 2026-09-16 | OIL-UNIT2-DEMO | Work on Weld Line 23 has begun. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-16 |  |  | obtain permit | FALSE | 0.961 | English | train
UPD-01424 | plain_text | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: No progress on Foundation F15 excavation today due to shortage of 24-inch pipes. Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | delay | DELAYED | 10 |  |  | shortage of 24-inch pipes | continue work | FALSE | 0.948 | English | train
UPD-01193 | plain_text | DPR | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Weld Line 23 remains not started. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.915 | English | train
UPD-00235 | pdf_text | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ CIV-R02-001 ¦ Crew resumed Road R02 subgrade preparation after clearance. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 60 | 2026-09-09 |  |  | resume after clearance | FALSE | 0.92 | English | train
UPD-00902 | ms_project_update | DPR | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: MS Project update: INS-JB05-001 Actual % Complete = 60% as of 2026-09-14. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-14 |  |  | mobilise crew | FALSE | 0.945 | English | train
UPD-00937 | plain_text | document | 2026-09-06 | OIL-UNIT2-DEMO | Supervisor update - Partial progress achieved on Complete work-at-height inspection. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-06 |  |  | complete inspection | FALSE | 0.946 | English | train
UPD-00762 | whatsapp | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Crew resumed Foundation F15 concreting after clearance. 👍 Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 30 | 2026-09-25 |  |  | update schedule | FALSE | 0.924 | English | train
UPD-00990 | voice_transcript | email | 2026-09-19 | OIL-UNIT2-DEMO | Today: Just to update you, started install pressure transmitter pt08 this morning. Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | start | STARTED | 80 | 2026-09-19 |  |  | continue work | FALSE | 0.927 | English | train
UPD-00618 | excel_note | document | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: CIV-R02-002 ¦ Road R02 PCC laying ¦ CANCELLED ¦ NA Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.943 | English | train
UPD-00720 | excel_note | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: CIV-R02-002 ¦ Road R02 PCC laying ¦ IN PROGRESS ¦ NA Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 20 | 2026-09-29 |  |  | update schedule | FALSE | 0.91 | English | train
UPD-00668 | voice_transcript | email | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that work on complete work-at-height inspection was stopped because safety clearance pending. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | delay | DELAYED | 50 |  |  | safety clearance pending | continue work | FALSE | 0.975 | English | train
UPD-00141 | voice_transcript | email | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - Uh, complete work-at-height inspection has not started yet. Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.939 | English | train
UPD-01454 | whatsapp | email | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Foundation F15 reinforcement will not be executed today. 👍 FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.93 | English | train
UPD-01800 | email | document | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - HSE-001-001 Dear Team, Complete work-at-height inspection kicked off today. Regards, Site Supervisor Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | start | STARTED | 60 | 2026-09-07 |  |  | planner review | FALSE | 0.904 | English | train
UPD-01177 | email | document | 2026-09-16 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - INS-T04-001 Dear Team, Execution of Install Temperature Transmitter T04 is blocked by design revision pending. Regards, Site Supervisor Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | mobilise crew | FALSE | 0.967 | English | train
UPD-00190 | pdf_text | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 ongoing at Pump House. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.968 | English | train
UPD-00966 | plain_text | document | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Foundation F15 concreting started today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 40 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.942 | English | train
UPD-00362 | whatsapp | email | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - Hi, today's install pressure transmitter pt08 activity has been cancelled. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.975 | English | train
UPD-00323 | pdf_text | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ PIP-L24-001 ¦ Work is continuing on Erect Line 24. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-29 |  |  | continue work | FALSE | 0.938 | English | train
UPD-01097 | email | mobile | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Install Heat Exchanger HX01 done at site. Regards, Site Supervisor Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-21 | 2026-09-21 |  | receive material | FALSE | 0.97 | English | train
UPD-00538 | excel_note | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Site Update: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ NOT STARTED ¦ NA For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.966 | English | train
UPD-01004 | word_document | DPR | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-07 Discipline: Mechanical Observation: Today's Install Heat Exchanger HX01 activity has been cancelled. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.987 | English | train
UPD-00925 | plain_text | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | Today: Foundation F15 concreting cancelled for today. Material expected tomorrow. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.946 | English | train
UPD-00374 | plain_text | document | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Work is continuing on Erect Line 24. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-26 |  |  | complete inspection | FALSE | 0.971 | English | train
UPD-00707 | voice_transcript | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that tank t01 foundation completion held up by power supply interruption. Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 60 |  |  | power supply interruption | complete inspection | FALSE | 0.913 | English | train
UPD-00763 | email | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - CIV-F15-003 Dear Team, Foundation F15 concreting remains not started. Regards, Site Supervisor Material expected tomorrow. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.907 | English | train
UPD-00014 | email | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - ELE-CBL07-001 Dear Team, Only part of Lay Cable Route 7 could be completed today. Regards, Site Supervisor Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-22 |  |  | mobilise crew | FALSE | 0.923 | English | train
UPD-01681 | pdf_text | mobile | 2026-09-30 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 30-09-2026 ¦ PIP-L30-001 ¦ Install 30-inch header is in progress. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 50 | 2026-09-30 |  |  | complete inspection | FALSE | 0.908 | English | train
UPD-00178 | whatsapp | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - Work on Terminate Junction Box JB05 has begun. 👍 Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 10 | 2026-09-18 |  |  | receive material | FALSE | 0.969 | English | train
UPD-00421 | ms_project_update | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | MS Project update: CIV-R02-001 Actual % Complete = 80% as of 2026-09-17. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 80 | 2026-09-17 |  |  | mobilise crew | FALSE | 0.906 | English | train
UPD-01491 | plain_text | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Hydrotest Line 23 is behind plan owing to equipment breakdown. Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | equipment breakdown | receive material | FALSE | 0.975 | English | train
UPD-00022 | word_document | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-23 Discipline: Piping Observation: Erect Line 24 is in progress. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-23 |  |  | update schedule | FALSE | 0.913 | English | train
UPD-01421 | plain_text | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Erect Line 24 resumed today after vendor technician not available was cleared. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-03 |  |  | continue work | FALSE | 0.923 | English | train
UPD-01353 | whatsapp | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - Install Valve V12 is complete as of today. 👍 | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | complete inspection | FALSE | 0.912 | English | train
UPD-00332 | voice_transcript | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: Uh, foundation f15 concreting cancelled for today. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.979 | English | train
UPD-00814 | site_diary | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Today: Date 2026-09-21 ¦ Plant Area ¦ Road R02 PCC laying progressing as planned. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 40 | 2026-09-21 |  |  | continue work | FALSE | 0.972 | English | train
UPD-00004 | word_document | mobile | 2026-09-05 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-05 Discipline: Civil Observation: Planned work Tank T01 foundation completion did not commence. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.916 | English | train
UPD-00683 | pdf_text | DPR | 2026-09-20 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ CIV-F15-002 ¦ Around 50% work comp. on Foundation F15 reinforcement; balance is ongoing. FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-20 |  |  | continue work | FALSE | 0.981 | English | train
UPD-01441 | whatsapp | mobile | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Around 50% work completed on Install Temperature Transmitter T04; balance is ongoing. 👍 Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-08 |  |  | mobilise crew | FALSE | 0.979 | English | train
UPD-01267 | email | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - INS-T04-001 Dear Team, Crew mobilised and started Install Temperature Transmitter T04. Regards, Site Supervisor FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 80 | 2026-09-25 |  |  | obtain permit | FALSE | 0.987 | English | train
UPD-01025 | plain_text | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Today's Road R02 subgrade preparation activity has been cancelled. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.934 | English | train
UPD-00537 | site_diary | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-17 ¦ Unit 2 ¦ No start for Erect Line 24 today. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.963 | English | train
UPD-00941 | word_document | document | 2026-09-02 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-02 Discipline: Piping Observation: Work is continuing on Weld Line 23. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-02 |  |  | receive material | FALSE | 0.91 | English | train
UPD-00888 | ms_project_update | document | 2026-09-18 | OIL-UNIT2-DEMO | MS Project note: INS-CV11-001 status = CANCELLED. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.908 | English | train
UPD-00220 | plain_text | document | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: Work on Install Heat Exchanger HX01 was stopped because equipment breakdown. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | delay | DELAYED | 20 |  |  | equipment breakdown | obtain permit | FALSE | 0.96 | English | train
UPD-00895 | whatsapp | document | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Hi, hydrotest line 23 is blocked pending equipment breakdown. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | update schedule | FALSE | 0.944 | English | train
UPD-01688 | voice_transcript | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Uh, execution of tank t01 foundation completion is blocked by drawing approval pending. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | drawing approval pending | receive material | FALSE | 0.901 | English | train
UPD-00999 | whatsapp | email | 2026-09-06 | OIL-UNIT2-DEMO | Supervisor update - Line/area update: crew mobilised and started install compressor c01. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 30 | 2026-09-06 |  |  | resume after clearance | FALSE | 0.929 | English | train
UPD-01324 | plain_text | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - Install Heat Exchanger HX01 is about 30% complete. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | partial_progress | PARTIAL | 30 | 2026-09-28 |  |  | resume after clearance | FALSE | 0.986 | English | train
UPD-01754 | pdf_text | email | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ CIV-R02-002 ¦ Only part of Road R02 PCC laying could be comp. today. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 20 | 2026-09-11 |  |  | planner review | FALSE | 0.907 | English | train
UPD-01016 | excel_note | email | 2026-09-17 | OIL-UNIT2-DEMO | HSE-001-001 ¦ Complete work-at-height inspection ¦ COMPLETED ¦ NA | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | obtain permit | FALSE | 0.901 | English | train
UPD-00372 | site_diary | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-14 ¦ Unit 2 ¦ Hydrotest Line 24 commenced at Unit 2. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-14 |  |  | receive material | FALSE | 0.929 | English | train
UPD-00205 | pdf_text | document | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ PIP-L30-001 ¦ No start for Install 30-inch header today. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.957 | English | train
UPD-01058 | pdf_text | document | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ PIP-L24-002 ¦ Execution of Weld Line 24 is blocked by safety clearance pending. Material expected tomorrow. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | continue work | FALSE | 0.914 | English | train
UPD-00115 | word_document | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-03 Discipline: Piping Observation: Install Valve V12 held up by late material inspection. Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | delay | DELAYED | 10 |  |  | late material inspection | mobilise crew | FALSE | 0.978 | English | train
UPD-00359 | plain_text | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Supervisor update - Foundation F15 concreting has not started yet. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.905 | English | train
UPD-01456 | email | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - INS-PT08-001 Dear Team, Install Pressure Transmitter PT08 has resumed following resolution of the earlier issue. Regards, Site Supervisor FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 40 | 2026-09-14 |  |  | receive material | FALSE | 0.985 | English | train
UPD-01465 | whatsapp | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Line/area update: work is continuing on road r02 subgrade preparation. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 70 | 2026-09-03 |  |  | obtain permit | FALSE | 0.964 | English | train
UPD-01255 | excel_note | email | 2026-09-20 | OIL-UNIT2-DEMO | Supervisor update - ELE-TR02-001 ¦ Install Transformer TR02 ¦ IN PROGRESS ¦ NA Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 40 | 2026-09-20 |  |  | receive material | FALSE | 0.946 | English | train
UPD-00219 | whatsapp | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Install Valve V12 cancelled for today. 👍 For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.9 | English | train
UPD-00776 | pdf_text | mobile | 2026-09-12 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ HSE-002-001 ¦ Close scaffold inspection actions remains not started. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.92 | English | train
UPD-00248 | ms_project_update | document | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: ELE-TR02-001 status = IN PROGRESS. Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 40 | 2026-09-10 |  |  | obtain permit | FALSE | 0.982 | English | train
UPD-01116 | excel_note | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: MEC-P03-001 ¦ Install Pump P03 ¦ NOT STARTED ¦ NA Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.904 | English | train
UPD-01581 | ms_project_update | document | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-R02-002 status = NOT STARTED. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.909 | English | train
UPD-01380 | whatsapp | MS_Project | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: Line/area update: supervisor confirms hydrotest line 24 completed. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | continue work | FALSE | 0.914 | English | train
UPD-00309 | word_document | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-30 Discipline: Piping Observation: Install Valve V12 commenced at Unit 2. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-30 |  |  | mobilise crew | FALSE | 0.961 | English | train
UPD-01481 | excel_note | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Today: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ IN PROGRESS ¦ NA Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 80 | 2026-09-25 |  |  | resume after clearance | FALSE | 0.978 | English | train
UPD-00873 | excel_note | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: MEC-P04-001 ¦ Align Pump P04 ¦ IN PROGRESS ¦ NA Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 30 | 2026-09-03 |  |  | receive material | FALSE | 0.923 | English | train
UPD-00507 | plain_text | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Around 50% work completed on Road R02 PCC laying; balance is ongoing. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 50 | 2026-09-19 |  |  | update schedule | FALSE | 0.964 | English | train
UPD-01395 | site_diary | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-08 ¦ Pump House ¦ Crew is currently working on Align Pump P04. For information. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 70 | 2026-09-08 |  |  | mobilise crew | FALSE | 0.962 | English | train
UPD-01744 | word_document | document | 2026-09-11 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-11 Discipline: Piping Observation: Erect Line 23 held up by insufficient manpower. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | insufficient manpower | obtain permit | FALSE | 0.971 | English | train
UPD-00044 | ms_project_update | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: MS Project note: CIV-R02-002 status = RESUMED. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 10 | 2026-09-05 |  |  | complete inspection | FALSE | 0.934 | English | train
UPD-00526 | pdf_text | mobile | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ INS-JB05-001 ¦ Around 50% work completed on Terminate Junction Box JB05; balance is ongoing. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.983 | English | train
UPD-00696 | email | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - HSE-001-001 Dear Team, Cannot continue Complete work-at-height inspection until safety clearance pending is resolved. Regards, Site Supervisor Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | receive material | FALSE | 0.979 | English | train
UPD-00206 | site_diary | DPR | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-15 ¦ Unit 2 ¦ Weld Line 24 is behind plan owing to material not received. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | material not received | receive material | FALSE | 0.971 | English | train
UPD-00748 | ms_project_update | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-TK01-001 status = NOT STARTED. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.962 | English | train
UPD-00468 | site_diary | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-12 ¦ Unit 1 ¦ Install 30-inch header will not be executed today. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.919 | English | train
UPD-01502 | pdf_text | DPR | 2026-09-10 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ MEC-P04-001 ¦ Cannot continue Align Pump P04 until design revision pending is resolved. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | design revision pending | resume after clearance | FALSE | 0.942 | English | train
UPD-01500 | voice_transcript | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Just to update you, hydrotest line 23 has not started yet. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.93 | English | train
UPD-01444 | ms_project_update | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: HSE-002-001 progress affected by drawing approval pending; expected finish to move. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | drawing approval pending | mobilise crew | FALSE | 0.982 | English | train
UPD-01592 | plain_text | mobile | 2026-09-12 | OIL-UNIT2-DEMO | DPR Update: Weld Line 23 commenced at Unit 2. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-12 |  |  | continue work | FALSE | 0.979 | English | train
UPD-00145 | ms_project_update | email | 2026-09-22 | OIL-UNIT2-DEMO | Today: MS Project note: MEC-P03-001 progress affected by drawing approval pending; expected finish to move. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 10 |  |  | drawing approval pending | obtain permit | FALSE | 0.914 | English | train
UPD-00167 | excel_note | email | 2026-09-06 | OIL-UNIT2-DEMO | Today: PIP-L23-002 ¦ Weld Line 23 ¦ COMPLETED ¦ NA FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | resume after clearance | FALSE | 0.933 | English | train
UPD-00805 | site_diary | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-08 ¦ Electrical Room ¦ Install MCC Panel 3 resumed today after crane unavailable was cleared. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 60 | 2026-09-08 |  |  | planner review | FALSE | 0.968 | English | train
UPD-00543 | voice_transcript | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that cannot continue align pump p04 until work permit not issued is resolved. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | work permit not issued | receive material | FALSE | 0.932 | English | train
UPD-00217 | word_document | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-29 Discipline: Mechanical Observation: Install Pump P03 is delayed because of equipment breakdown. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 60 |  |  | equipment breakdown | mobilise crew | FALSE | 0.969 | English | train
UPD-00225 | ms_project_update | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Daily Progress: MS Project update: ELE-LTG02-001 actual start = 2026-09-20; work commenced. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 50 | 2026-09-20 |  |  | update schedule | FALSE | 0.952 | English | train
UPD-01208 | voice_transcript | email | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: Uh, road r02 subgrade preparation is about 25% complete. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 25 | 2026-09-20 |  |  | complete inspection | FALSE | 0.95 | English | train
UPD-00038 | voice_transcript | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: So, basically, install tank t02 internals will not be executed today. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.909 | English | train
UPD-00404 | whatsapp | email | 2026-09-30 | OIL-UNIT2-DEMO | Sir, work for weld line 24 is finished. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-30 | 2026-09-30 |  | update schedule | FALSE | 0.977 | English | train
UPD-00799 | pdf_text | document | 2026-09-10 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ HSE-002-001 ¦ Close scaffold inspection actions has been comp. at Unit 1. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | resume after clearance | FALSE | 0.911 | English | train
UPD-01171 | whatsapp | document | 2026-09-04 | OIL-UNIT2-DEMO | Crew is currently working on Weld Line 23. 👍 Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-04 |  |  | continue work | FALSE | 0.943 | English | train
UPD-00338 | voice_transcript | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Site Update: Uh, install mcc panel 3 is about 50% complete. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 50 | 2026-09-09 |  |  | planner review | FALSE | 0.979 | English | train
UPD-01039 | word_document | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-19 Discipline: Piping Observation: Weld Line 24 is complete as of today. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | resume after clearance | FALSE | 0.977 | English | train
UPD-01685 | excel_note | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: CIV-F15-001 ¦ Foundation F15 excavation ¦ COMPLETED ¦ NA Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | resume after clearance | FALSE | 0.932 | English | train
UPD-00350 | voice_transcript | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Today: So, basically, erect line 23 started today. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-27 |  |  | update schedule | FALSE | 0.92 | English | train
UPD-01349 | ms_project_update | document | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: PIP-L24-001 status = IN PROGRESS. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.923 | English | train
UPD-00142 | email | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 is behind plan owing to access road blocked. Regards, Site Supervisor Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 40 |  |  | access road blocked | mobilise crew | FALSE | 0.969 | English | train
UPD-00367 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ MEC-T02-001 ¦ Only part of Install Tank T02 internals could be comp. today. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 70 | 2026-09-04 |  |  | mobilise crew | FALSE | 0.927 | English | train
UPD-00546 | whatsapp | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - Lay Cable Route 7 cancelled for today. 👍 | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.983 | English | train
UPD-01068 | voice_transcript | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Uh, install pump p03 has not started yet. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.987 | English | train
UPD-00563 | plain_text | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Supervisor update - Hydrotest Line 24 will not be executed today. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.904 | English | train
UPD-01600 | pdf_text | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ CIV-TK01-001 ¦ No start for Tank T01 foundation completion today. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.956 | English | train
UPD-00783 | excel_note | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: PIP-L24-003 ¦ Hydrotest Line 24 ¦ IN PROGRESS ¦ NA Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-07 |  |  | complete inspection | FALSE | 0.919 | English | train
UPD-00494 | site_diary | mobile | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-28 ¦ Unit 1 ¦ Install 30-inch header cancelled for today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.984 | English | train
UPD-00080 | ms_project_update | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: MS Project note: CIV-TK01-001 progress affected by material not received; expected finish to move. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 10 |  |  | material not received | receive material | FALSE | 0.924 | English | train
UPD-01661 | excel_note | document | 2026-09-11 | OIL-UNIT2-DEMO | Supervisor update - CIV-R02-002 ¦ Road R02 PCC laying ¦ DELAYED ¦ welding machine under maintenance FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | delay | DELAYED | 40 |  |  | welding machine under maintenance | update schedule | FALSE | 0.931 | English | train
UPD-01686 | word_document | email | 2026-09-05 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-05 Discipline: Instrumentation Observation: Planned work Install Temperature Transmitter T04 did not commence. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.987 | English | train
UPD-01219 | site_diary | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-29 ¦ Unit 1 ¦ Work on Install Heat Exchanger HX01 has begun. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 20 | 2026-09-29 |  |  | obtain permit | FALSE | 0.925 | English | train
UPD-00476 | email | document | 2026-09-02 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - CIV-F15-003 Dear Team, Foundation F15 concreting partially completed today. Regards, Site Supervisor FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-02 |  |  | obtain permit | FALSE | 0.938 | English | train
UPD-00093 | excel_note | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - PIP-L24-002 ¦ Weld Line 24 ¦ STARTED ¦ NA Material expected tomorrow. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-04 |  |  | resume after clearance | FALSE | 0.955 | English | train
UPD-01295 | voice_transcript | mobile | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - Okay, today's update is that work on install tank t02 internals has begun. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | start | STARTED | 70 | 2026-09-08 |  |  | update schedule | FALSE | 0.939 | English | train
UPD-00819 | pdf_text | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 remains not started. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.909 | English | train
UPD-01498 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ CIV-F15-002 ¦ Crew mobilised and started Foundation F15 reinforcement. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 40 | 2026-09-04 |  |  | continue work | FALSE | 0.944 | English | train
UPD-01541 | site_diary | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Date 2026-09-24 ¦ Unit 1 ¦ Install 30-inch header completed today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | complete inspection | FALSE | 0.956 | English | train
UPD-01783 | email | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 cancelled for today. Regards, Site Supervisor FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.978 | English | train
UPD-01798 | site_diary | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-29 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 held up by equipment breakdown. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | delay | DELAYED | 80 |  |  | equipment breakdown | mobilise crew | FALSE | 0.901 | English | train
UPD-00611 | ms_project_update | email | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: MS Project update: PIP-L24-002 Actual % Complete = 25% as of 2026-09-22. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-22 |  |  | complete inspection | FALSE | 0.957 | English | train
UPD-00593 | email | document | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - PIP-L23-003 Dear Team, Hydrotest Line 23 will not be executed today. Regards, Site Supervisor For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.904 | English | train
UPD-01297 | pdf_text | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ INS-JB05-001 ¦ Terminate Junction Box JB05 progressing as planned. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-27 |  |  | update schedule | FALSE | 0.916 | English | train
UPD-00842 | email | DPR | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - HSE-002-001 Dear Team, Close scaffold inspection actions resumed today after work permit not issued was cleared. Regards, Site Supervisor Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 20 | 2026-09-24 |  |  | planner review | FALSE | 0.964 | English | train
UPD-01653 | site_diary | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-15 ¦ Unit 2 ¦ Today's Install Control Valve CV11 activity has been cancelled. Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.917 | English | train
UPD-00829 | whatsapp | document | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: Weld Line 24 is about 20% complete. 👍 FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-26 |  |  | resume after clearance | FALSE | 0.9 | English | train
UPD-00105 | email | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - ELE-CBL07-001 Dear Team, Only part of Lay Cable Route 7 could be completed today. Regards, Site Supervisor Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-06 |  |  | obtain permit | FALSE | 0.91 | English | train
UPD-01683 | whatsapp | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Today: Sir, partial progress achieved on road r02 subgrade preparation. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 50 | 2026-09-01 |  |  | mobilise crew | FALSE | 0.964 | English | train
UPD-01236 | voice_transcript | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Just to update you, install 30-inch header will not be executed today. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.924 | English | train
UPD-00153 | ms_project_update | mobile | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: PIP-L24-002 status = RESUMED. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-03 |  |  | obtain permit | FALSE | 0.924 | English | train
UPD-00399 | plain_text | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: Work on Terminate Junction Box JB05 restarted today. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | resumption | RESUMED | 60 | 2026-09-26 |  |  | complete inspection | FALSE | 0.925 | English | train
UPD-01089 | pdf_text | email | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ HSE-002-001 ¦ No progress on Close scaffold inspection actions today due to material not received. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 10 |  |  | material not received | mobilise crew | FALSE | 0.98 | English | train
UPD-00193 | pdf_text | document | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ ELE-LTG02-001 ¦ Team finished Install Unit 2 lighting. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | obtain permit | FALSE | 0.915 | English | train
UPD-00982 | voice_transcript | email | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: So, basically, started weld line 23 this morning. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-26 |  |  | continue work | FALSE | 0.933 | English | train
UPD-01458 | voice_transcript | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Progress note: Okay, today's update is that foundation f15 concreting has resumed following resolution of the earlier issue. Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 80 | 2026-09-01 |  |  | continue work | FALSE | 0.961 | English | train
UPD-00896 | excel_note | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Today: PIP-L23-002 ¦ Weld Line 23 ¦ PARTIAL ¦ NA Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-30 |  |  | resume after clearance | FALSE | 0.916 | English | train
UPD-00039 | pdf_text | document | 2026-09-11 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ MEC-P04-001 ¦ Crew mobilised and started Align Pump P04. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 20 | 2026-09-11 |  |  | complete inspection | FALSE | 0.969 | English | train
UPD-00879 | voice_transcript | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: Okay, today's update is that install heat exchanger hx01 remains on hold due to insufficient manpower. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | insufficient manpower | resume after clearance | FALSE | 0.961 | English | train
UPD-00132 | site_diary | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Date 2026-09-14 ¦ Unit 1 ¦ No start for Install Heat Exchanger HX01 today. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.984 | English | train
UPD-00501 | site_diary | email | 2026-09-05 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-05 ¦ Plant Area ¦ Crew mobilised and started Road R02 subgrade preparation. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 40 | 2026-09-05 |  |  | continue work | FALSE | 0.973 | English | train
UPD-01734 | ms_project_update | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: PIP-L23-001 progress affected by inspection clearance pending; expected finish to move. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | inspection clearance pending | continue work | FALSE | 0.986 | English | train
UPD-01110 | pdf_text | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ CIV-TK01-001 ¦ Tank T01 foundation completion is in progress. Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | progress | IN_PROGRESS | 40 | 2026-09-08 |  |  | obtain permit | FALSE | 0.976 | English | train
UPD-00664 | excel_note | document | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: ELE-CBL07-001 ¦ Lay Cable Route 7 ¦ IN PROGRESS ¦ NA Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-08 |  |  | receive material | FALSE | 0.914 | English | train
UPD-01117 | word_document | document | 2026-09-21 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-21 Discipline: Instrumentation Observation: Install Pressure Transmitter PT08 has not started yet. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.965 | English | train
UPD-01305 | excel_note | document | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: CIV-F15-003 ¦ Foundation F15 concreting ¦ IN PROGRESS ¦ NA Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-13 |  |  | receive material | FALSE | 0.932 | English | train
UPD-01695 | pdf_text | mobile | 2026-09-03 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ PIP-L23-001 ¦ Around 50% work completed on Erect Line 23; balance is ongoing. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.906 | English | train
UPD-00979 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ HSE-002-001 ¦ Close scaffold inspection actions is blocked pending insufficient manpower. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | insufficient manpower | complete inspection | FALSE | 0.933 | English | train
UPD-01531 | voice_transcript | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: So, basically, install pump p03 is about 50% complete. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 50 | 2026-09-25 |  |  | update schedule | FALSE | 0.921 | English | train
UPD-00324 | word_document | document | 2026-09-17 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-17 Discipline: HSE Observation: Complete work-at-height inspection has resumed following resolution of the earlier issue. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | resumption | RESUMED | 10 | 2026-09-17 |  |  | planner review | FALSE | 0.988 | English | train
UPD-01594 | pdf_text | email | 2026-09-01 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ CIV-R02-002 ¦ Road R02 PCC laying done at site. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-01 | 2026-09-01 |  | receive material | FALSE | 0.975 | English | train
UPD-01141 | ms_project_update | mobile | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: MEC-C01-001 progress affected by insufficient manpower; expected finish to move. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | insufficient manpower | planner review | FALSE | 0.913 | English | train
UPD-00149 | excel_note | DPR | 2026-09-25 | OIL-UNIT2-DEMO | CIV-F15-002 ¦ Foundation F15 reinforcement ¦ BLOCKED ¦ QA/QC hold point not cleared Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | planner review | FALSE | 0.979 | English | train
UPD-00050 | word_document | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-21 Discipline: Instrumentation Observation: Install Control Valve CV11 partially completed today. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-21 |  |  | planner review | FALSE | 0.99 | English | train
UPD-01784 | word_document | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-05 Discipline: Civil Observation: Execution of Road R02 subgrade preparation is blocked by inspection clearance pending. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | inspection clearance pending | mobilise crew | FALSE | 0.938 | English | train
UPD-00485 | word_document | mobile | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-20 Discipline: Piping Observation: Crew mobilised and started Weld Line 23. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-20 |  |  | mobilise crew | FALSE | 0.947 | English | train
UPD-00356 | whatsapp | email | 2026-09-13 | OIL-UNIT2-DEMO | Sir, work for erect line 24 is finished. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | update schedule | FALSE | 0.979 | English | train
UPD-00331 | ms_project_update | mobile | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-002 status = NOT STARTED. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.939 | English | train
UPD-00744 | ms_project_update | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: MS Project update: PIP-L23-002 actual start = 2026-09-12; work commenced. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-12 |  |  | planner review | FALSE | 0.954 | English | train
UPD-01152 | site_diary | email | 2026-09-28 | OIL-UNIT2-DEMO | Date 2026-09-28 ¦ Unit 2 ¦ No progress on Complete work-at-height inspection today due to equipment breakdown. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | delay | DELAYED | 80 |  |  | equipment breakdown | update schedule | FALSE | 0.989 | English | train
UPD-00089 | site_diary | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-27 ¦ Plant Area ¦ Cannot continue Road R02 subgrade preparation until power supply interruption is resolved. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | power supply interruption | planner review | FALSE | 0.923 | English | train
UPD-00183 | ms_project_update | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: MEC-C01-001 status = NOT STARTED. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.983 | English | train
UPD-00226 | excel_note | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: PIP-L24-003 ¦ Hydrotest Line 24 ¦ DELAYED ¦ safety clearance pending | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | safety clearance pending | receive material | FALSE | 0.935 | English | train
UPD-00495 | site_diary | spreadsheet | 2026-09-18 | OIL-UNIT2-DEMO | Today: Date 2026-09-18 ¦ Unit 1 ¦ Team finished Close scaffold inspection actions. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | resume after clearance | FALSE | 0.935 | English | train
UPD-00823 | whatsapp | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Hi, crew mobilised and started align pump p04. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 10 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.921 | English | train
UPD-00585 | whatsapp | DPR | 2026-09-20 | OIL-UNIT2-DEMO | Line/area update: no progress on foundation f15 concreting today due to work permit not issued. FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 30 |  |  | work permit not issued | resume after clearance | FALSE | 0.953 | English | train
UPD-00068 | site_diary | DPR | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-29 ¦ Unit 2 ¦ Terminate Junction Box JB05 will not be executed today. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.983 | English | train
UPD-01699 | voice_transcript | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, started install heat exchanger hx01 this morning. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 60 | 2026-09-26 |  |  | resume after clearance | FALSE | 0.978 | English | train
UPD-00265 | site_diary | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Today: Date 2026-09-07 ¦ Tank Farm ¦ Partial progress achieved on Install Tank T02 internals. For information. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 25 | 2026-09-07 |  |  | obtain permit | FALSE | 0.91 | English | train
UPD-00232 | pdf_text | mobile | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 cancelled for today. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.989 | English | train
UPD-01080 | plain_text | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Road R02 PCC laying resumed today after safety clearance pending was cleared. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 30 | 2026-09-25 |  |  | resume after clearance | FALSE | 0.911 | English | train
UPD-01412 | pdf_text | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 17-09-2026 ¦ INS-CV11-001 ¦ Team finished Install Control Valve CV11. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | planner review | FALSE | 0.902 | English | train
UPD-01702 | whatsapp | email | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - Hi, today's road r02 subgrade preparation activity has been cancelled. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.903 | English | train
UPD-00961 | excel_note | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Today: INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ CANCELLED ¦ NA | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.973 | English | train
UPD-01161 | site_diary | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-23 ¦ Unit 2 ¦ Erect Line 24 partially completed today. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-23 |  |  | planner review | FALSE | 0.935 | English | train
UPD-00991 | email | document | 2026-09-09 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Install Tank T02 internals has not started yet. Regards, Site Supervisor Material expected tomorrow. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.92 | English | train
UPD-00721 | word_document | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-24 Discipline: Civil Observation: Planned work Road R02 PCC laying did not commence. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.973 | English | train
UPD-00308 | whatsapp | document | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Hi, install 30-inch header could not proceed today due to welding machine under maintenance. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 30 |  |  | welding machine under maintenance | receive material | FALSE | 0.935 | English | train
UPD-00428 | voice_transcript | document | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: Just to update you, hydrotest line 24 remains on hold due to qa/qc hold point not cleared. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | resume after clearance | FALSE | 0.929 | English | train
UPD-01028 | pdf_text | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ HSE-001-001 ¦ Complete work-at-height inspection partially completed today. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-25 |  |  | complete inspection | FALSE | 0.914 | English | train
UPD-01104 | excel_note | spreadsheet | 2026-09-17 | OIL-UNIT2-DEMO | Today: PIP-L23-002 ¦ Weld Line 23 ¦ PARTIAL ¦ NA For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-17 |  |  | obtain permit | FALSE | 0.902 | English | train
UPD-00487 | site_diary | mobile | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-25 ¦ Electrical Room ¦ Install MCC Panel 3 completed today. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | mobilise crew | FALSE | 0.906 | English | train
UPD-00580 | email | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-V12-001 Dear Team, Execution of Install Valve V12 is blocked by shortage of 24-inch pipes. Regards, Site Supervisor Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | planner review | FALSE | 0.989 | English | train
UPD-01249 | ms_project_update | email | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: MS Project update: PIP-V12-001 Actual % Complete = 25% as of 2026-09-23. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-23 |  |  | mobilise crew | FALSE | 0.909 | English | train
UPD-00278 | site_diary | mobile | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-28 ¦ Compressor Area ¦ Work on Install Compressor C01 restarted today. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 30 | 2026-09-28 |  |  | complete inspection | FALSE | 0.918 | English | train
UPD-00390 | site_diary | email | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-16 ¦ Pump House ¦ Install Pump P03 is blocked pending scaffold not ready. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | scaffold not ready | mobilise crew | FALSE | 0.905 | English | train
UPD-00471 | site_diary | document | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-03 ¦ Electrical Room ¦ Install MCC Panel 3 partially completed today. For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 10 | 2026-09-03 |  |  | planner review | FALSE | 0.956 | English | train
UPD-01549 | email | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation has not started yet. Regards, Site Supervisor Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.968 | English | train
UPD-01062 | plain_text | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Today: Planned work Hydrotest Line 23 did not commence. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.938 | English | train
UPD-01723 | ms_project_update | document | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: MS Project note: MEC-P04-001 status = CANCELLED. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.933 | English | train
UPD-00595 | plain_text | email | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: Team finished Hydrotest Line 23. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | continue work | FALSE | 0.933 | English | train
UPD-00134 | excel_note | email | 2026-09-23 | OIL-UNIT2-DEMO | Today: CIV-R02-002 ¦ Road R02 PCC laying ¦ BLOCKED ¦ inspection clearance pending For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | inspection clearance pending | complete inspection | FALSE | 0.926 | English | train
UPD-00478 | pdf_text | MS_Project | 2026-09-25 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ PIP-L24-001 ¦ Today's Erect Line 24 activity has been cancelled. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.956 | English | train
UPD-01731 | ms_project_update | document | 2026-09-14 | OIL-UNIT2-DEMO | Today: MS Project note: INS-CV11-001 status = IN PROGRESS. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-14 |  |  | obtain permit | FALSE | 0.971 | English | train
UPD-01597 | ms_project_update | document | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: MS Project note: ELE-MCC03-001 status = IN PROGRESS. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 30 | 2026-09-07 |  |  | complete inspection | FALSE | 0.937 | English | train
UPD-00951 | pdf_text | document | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 kicked off today. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 70 | 2026-09-28 |  |  | complete inspection | FALSE | 0.979 | English | train
UPD-00187 | plain_text | email | 2026-09-01 | OIL-UNIT2-DEMO | 10-Sep update: Install Heat Exchanger HX01 could not proceed today due to valve not available at site. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | delay | DELAYED | 50 |  |  | valve not available at site | obtain permit | FALSE | 0.922 | English | train
UPD-01607 | pdf_text | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ HSE-001-001 ¦ Only part of Complete work-at-height inspection could be completed today. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-01 |  |  | planner review | FALSE | 0.953 | English | train
UPD-00316 | voice_transcript | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, crew mobilised and started erect line 23. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-06 |  |  | resume after clearance | FALSE | 0.948 | English | train
UPD-00645 | plain_text | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Install Compressor C01 will not be executed today. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.95 | English | train
UPD-00005 | excel_note | document | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: PIP-V12-001 ¦ Install Valve V12 ¦ STARTED ¦ NA Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 60 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.913 | English | train
UPD-01282 | voice_transcript | document | 2026-09-19 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, foundation f15 concreting resumed today after client approval pending was cleared. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 20 | 2026-09-19 |  |  | complete inspection | FALSE | 0.976 | English | train
UPD-01303 | email | email | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Road R02 PCC laying is blocked pending drawing approval pending. Regards, Site Supervisor For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | drawing approval pending | resume after clearance | FALSE | 0.975 | English | train
UPD-00652 | excel_note | mobile | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: MEC-C01-001 ¦ Install Compressor C01 ¦ IN PROGRESS ¦ NA Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 60 | 2026-09-30 |  |  | receive material | FALSE | 0.979 | English | train
UPD-01467 | site_diary | mobile | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-01 ¦ Unit 2 ¦ Complete work-at-height inspection completed today. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-01 | 2026-09-01 |  | resume after clearance | FALSE | 0.968 | English | train
UPD-00792 | whatsapp | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: Sir, no progress on hydrotest line 23 today due to shortage of 24-inch pipes. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | shortage of 24-inch pipes | mobilise crew | FALSE | 0.911 | English | train
UPD-01711 | ms_project_update | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | MS Project note: CIV-F15-002 progress affected by rainfall at site; expected finish to move. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | update schedule | FALSE | 0.983 | English | train
UPD-00307 | voice_transcript | document | 2026-09-24 | OIL-UNIT2-DEMO | Just to update you, no start for road r02 pcc laying today. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.977 | English | train
UPD-01053 | whatsapp | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Hi, install mcc panel 3 remains on hold due to scaffold not ready. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | blockage | BLOCKED | 0 |  |  | scaffold not ready | update schedule | FALSE | 0.983 | English | train
UPD-00373 | voice_transcript | mobile | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: So, basically, foundation f15 excavation will not be executed today. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.952 | English | train
UPD-01263 | ms_project_update | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Unit update: MS Project update: CIV-F15-001 marked 100% complete. Actual Finish: 2026-09-09. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | mobilise crew | FALSE | 0.962 | English | train
UPD-00514 | pdf_text | MS_Project | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ PIP-L24-002 ¦ Weld Line 24 resumed today after safety clearance pending was cleared. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 60 | 2026-09-19 |  |  | update schedule | FALSE | 0.968 | English | train
UPD-01382 | pdf_text | mobile | 2026-09-05 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ CIV-R02-001 ¦ Started Road R02 subgrade preparation this morning. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 50 | 2026-09-05 |  |  | obtain permit | FALSE | 0.934 | English | train
UPD-01797 | ms_project_update | document | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: MS Project update: INS-PT08-001 Actual % Complete = 70% as of 2026-09-13. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 70 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.963 | English | train
UPD-01693 | pdf_text | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 07-09-2026 ¦ ELE-LTG02-001 ¦ Team finished Install Unit 2 lighting. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | mobilise crew | FALSE | 0.949 | English | train
UPD-01771 | ms_project_update | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: CIV-TK01-001 progress affected by QA/QC hold point not cleared; expected finish to move. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | continue work | FALSE | 0.921 | English | train
UPD-01403 | site_diary | site_diary | 2026-09-09 | OIL-UNIT2-DEMO | Date 2026-09-09 ¦ Tank Farm ¦ Cannot continue Install Tank T02 internals until inspection clearance pending is resolved. Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | blockage | BLOCKED | 0 |  |  | inspection clearance pending | complete inspection | FALSE | 0.91 | English | train
UPD-01338 | site_diary | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-14 ¦ Unit 2 ¦ Weld Line 23 is about 80% complete. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-14 |  |  | update schedule | FALSE | 0.968 | English | train
UPD-00719 | plain_text | DPR | 2026-09-06 | OIL-UNIT2-DEMO | Unit update: Weld Line 23 started today. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-06 |  |  | obtain permit | FALSE | 0.988 | English | train
UPD-00436 | plain_text | email | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: Cannot continue Erect Line 23 until equipment breakdown is resolved. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | continue work | FALSE | 0.933 | English | train
UPD-00176 | plain_text | document | 2026-09-25 | OIL-UNIT2-DEMO | Install Transformer TR02 remains not started. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.962 | English | train
UPD-00573 | word_document | document | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-20 Discipline: Piping Observation: Weld Line 24 cancelled for today. For information. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.981 | English | train
UPD-01598 | ms_project_update | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Unit update: MS Project update: PIP-L24-001 actual start = 2026-09-26; work commenced. Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-26 |  |  | continue work | FALSE | 0.955 | English | train
UPD-00196 | plain_text | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: Erect Line 24 is delayed because of safety clearance pending. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | safety clearance pending | continue work | FALSE | 0.948 | English | train
UPD-00368 | excel_note | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Today: CIV-R02-002 ¦ Road R02 PCC laying ¦ RESUMED ¦ NA | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 10 | 2026-09-29 |  |  | planner review | FALSE | 0.958 | English | train
UPD-01706 | whatsapp | email | 2026-09-15 | OIL-UNIT2-DEMO | Progress note: Hi, install tank t02 internals remains not started. Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.9 | English | train
UPD-01342 | email | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - CIV-TK01-001 Dear Team, Started Tank T01 foundation completion this morning. Regards, Site Supervisor Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | start | STARTED | 60 | 2026-09-18 |  |  | complete inspection | FALSE | 0.989 | English | train
UPD-00340 | voice_transcript | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Site Update: So, basically, started terminate junction box jb05 this morning. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 10 | 2026-09-15 |  |  | resume after clearance | FALSE | 0.973 | English | train
UPD-01129 | site_diary | document | 2026-09-16 | OIL-UNIT2-DEMO | Today: Date 2026-09-16 ¦ Compressor Area ¦ Work on Install Compressor C01 has begun. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 20 | 2026-09-16 |  |  | complete inspection | FALSE | 0.95 | English | train
UPD-00413 | excel_note | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: PIP-L23-001 ¦ Erect Line 23 ¦ CANCELLED ¦ NA For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.941 | English | train
UPD-01172 | plain_text | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - Install Compressor C01 is in progress. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 20 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.953 | English | train
UPD-01329 | pdf_text | email | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ CIV-R02-001 ¦ Road R02 subgrade preparation is in progress. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 20 | 2026-09-24 |  |  | planner review | FALSE | 0.982 | English | train
UPD-00874 | ms_project_update | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Progress note: MS Project note: ELE-MCC03-001 progress affected by rainfall at site; expected finish to move. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | blockage | BLOCKED | 0 |  |  | rainfall at site | complete inspection | FALSE | 0.913 | English | train
UPD-01366 | site_diary | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-22 ¦ Tank Farm ¦ Work on Install Tank T02 internals restarted today. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | resumption | RESUMED | 70 | 2026-09-22 |  |  | receive material | FALSE | 0.928 | English | train
UPD-01478 | site_diary | email | 2026-09-08 | OIL-UNIT2-DEMO | Date 2026-09-08 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 is blocked pending valve not available at site. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | valve not available at site | resume after clearance | FALSE | 0.989 | English | train
UPD-00234 | plain_text | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Unit update: Work for Hydrotest Line 24 is finished. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | obtain permit | FALSE | 0.918 | English | train
UPD-00815 | word_document | mobile | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-07 Discipline: Piping Observation: No start for Hydrotest Line 24 today. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.989 | English | train
UPD-00380 | ms_project_update | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Today: MS Project update: ELE-MCC03-001 marked 100% complete. Actual Finish: 2026-09-10. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | obtain permit | FALSE | 0.953 | English | train
UPD-01563 | site_diary | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-08 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 has not started yet. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.911 | English | train
UPD-01018 | pdf_text | spreadsheet | 2026-09-11 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ ELE-TR02-001 ¦ Install Transformer TR02 is about 70% complete. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 70 | 2026-09-11 |  |  | continue work | FALSE | 0.975 | English | train
UPD-00717 | voice_transcript | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Today: Just to update you, today's foundation f15 excavation activity has been cancelled. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.917 | English | train
UPD-01608 | site_diary | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Today: Date 2026-09-10 ¦ Unit 2 ¦ Erect Line 24 is blocked pending valve not available at site. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | update schedule | FALSE | 0.95 | English | train
UPD-01621 | plain_text | document | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Install Control Valve CV11 started today. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-02 |  |  | planner review | FALSE | 0.949 | English | train
UPD-01052 | site_diary | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | Date 2026-09-13 ¦ Unit 2 ¦ Erect Line 24 ongoing at Unit 2. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-13 |  |  | receive material | FALSE | 0.926 | English | train
UPD-00045 | email | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - MEC-P03-001 Dear Team, Install Pump P03 cancelled for today. Regards, Site Supervisor | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.98 | English | train
UPD-00630 | site_diary | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-23 ¦ Unit 2 ¦ Work is continuing on Install Temperature Transmitter T04. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-23 |  |  | continue work | FALSE | 0.916 | English | train
UPD-00764 | voice_transcript | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Today: Okay, today's update is that execution of install valve v12 is blocked by crane unavailable. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | crane unavailable | resume after clearance | FALSE | 0.902 | English | train
UPD-01284 | plain_text | document | 2026-09-05 | OIL-UNIT2-DEMO | Daily Progress: Execution of Install Valve V12 is blocked by safety clearance pending. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | planner review | FALSE | 0.985 | English | train
UPD-00770 | email | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L23-003 Dear Team, Work for Hydrotest Line 23 is finished. Regards, Site Supervisor Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | obtain permit | FALSE | 0.965 | English | train
UPD-01393 | excel_note | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ BLOCKED ¦ equipment breakdown For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | equipment breakdown | resume after clearance | FALSE | 0.967 | English | train
UPD-00369 | voice_transcript | mobile | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Just to update you, road r02 pcc laying partially completed today. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 80 | 2026-09-17 |  |  | receive material | FALSE | 0.961 | English | train
UPD-00787 | voice_transcript | site_diary | 2026-09-26 | OIL-UNIT2-DEMO | DPR Update: Okay, today's update is that erect line 23 is delayed because of late material inspection. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | late material inspection | planner review | FALSE | 0.978 | English | train
UPD-01251 | pdf_text | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ ELE-CBL07-001 ¦ Only part of Lay Cable Route 7 could be completed today. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 70 | 2026-09-19 |  |  | resume after clearance | FALSE | 0.965 | English | train
UPD-01402 | ms_project_update | email | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - MS Project update: ELE-LTG02-001 marked 100% complete. Actual Finish: 2026-09-26. FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | complete inspection | FALSE | 0.988 | English | train
UPD-00003 | excel_note | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: MEC-T02-001 ¦ Install Tank T02 internals ¦ STARTED ¦ NA Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | start | STARTED | 60 | 2026-09-08 |  |  | receive material | FALSE | 0.969 | English | train
UPD-00821 | voice_transcript | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Today: Okay, today's update is that work for install valve v12 is finished. Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | resume after clearance | FALSE | 0.961 | English | train
UPD-00391 | whatsapp | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: Line/area update: only part of terminate junction box jb05 could be completed today. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-27 |  |  | receive material | FALSE | 0.975 | English | train
UPD-01439 | voice_transcript | spreadsheet | 2026-09-01 | OIL-UNIT2-DEMO | Just to update you, erect line 24 is blocked pending qa/qc hold point not cleared. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | receive material | FALSE | 0.935 | English | train
UPD-00455 | site_diary | mobile | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-30 ¦ Unit 2 ¦ Work on Foundation F15 excavation has begun. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | start | STARTED | 20 | 2026-09-30 |  |  | complete inspection | FALSE | 0.981 | English | train
UPD-00609 | whatsapp | document | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Sir, crew mobilised and started install mcc panel 3. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 30 | 2026-09-04 |  |  | obtain permit | FALSE | 0.907 | English | train
UPD-00351 | ms_project_update | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Today: MS Project note: MEC-P04-001 status = CANCELLED. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.981 | English | train
UPD-01175 | plain_text | email | 2026-09-08 | OIL-UNIT2-DEMO | Install Valve V12 has resumed following resolution of the earlier issue. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | resumption | RESUMED | 70 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.958 | English | train
UPD-00497 | voice_transcript | email | 2026-09-14 | OIL-UNIT2-DEMO | DPR Update: Okay, today's update is that work for install pump p03 is finished. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | continue work | FALSE | 0.937 | English | train
UPD-00447 | excel_note | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Today: INS-CV11-001 ¦ Install Control Valve CV11 ¦ BLOCKED ¦ rainfall at site For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | receive material | FALSE | 0.952 | English | train
UPD-00675 | voice_transcript | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: Uh, team finished tank t01 foundation completion. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | resume after clearance | FALSE | 0.987 | English | train
UPD-01555 | voice_transcript | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | Uh, started install unit 2 lighting this morning. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 40 | 2026-09-15 |  |  | mobilise crew | FALSE | 0.97 | English | train
UPD-00446 | pdf_text | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ PIP-L30-001 ¦ Work on Install 30-inch header restarted today. Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 60 | 2026-09-29 |  |  | update schedule | FALSE | 0.907 | English | train
UPD-01391 | whatsapp | email | 2026-09-27 | OIL-UNIT2-DEMO | Today: Install Transformer TR02 started today. 👍 | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 30 | 2026-09-27 |  |  | planner review | FALSE | 0.901 | English | train
UPD-01566 | ms_project_update | document | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: MS Project note: INS-JB05-001 progress affected by safety clearance pending; expected finish to move. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 50 |  |  | safety clearance pending | obtain permit | FALSE | 0.972 | English | train
UPD-01212 | pdf_text | DPR | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 is behind plan owing to rainfall at site. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | rainfall at site | mobilise crew | FALSE | 0.927 | English | train
UPD-01167 | plain_text | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Crew resumed Hydrotest Line 23 after clearance. For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 40 | 2026-09-03 |  |  | receive material | FALSE | 0.989 | English | train
UPD-01506 | email | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-F15-003 Dear Team, Foundation F15 concreting has resumed following resolution of the earlier issue. Regards, Site Supervisor Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 70 | 2026-09-07 |  |  | planner review | FALSE | 0.957 | English | train
UPD-00761 | pdf_text | document | 2026-09-03 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 is blocked pending power supply interruption. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | blockage | BLOCKED | 0 |  |  | power supply interruption | continue work | FALSE | 0.906 | English | train
UPD-01149 | plain_text | document | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Erect Line 23 is blocked pending power supply interruption. FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | continue work | FALSE | 0.986 | English | train
UPD-01445 | site_diary | DPR | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-18 ¦ Plant Area ¦ Work on Road R02 subgrade preparation has begun. Please note. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 30 | 2026-09-18 |  |  | continue work | FALSE | 0.916 | English | train
UPD-01231 | plain_text | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Install MCC Panel 3 will not be executed today. For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.956 | English | train
UPD-01260 | excel_note | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: PIP-L24-001 ¦ Erect Line 24 ¦ STARTED ¦ NA Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-09 |  |  | continue work | FALSE | 0.915 | English | train
UPD-01182 | pdf_text | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ CIV-R02-002 ¦ Partial progress achieved on Road R02 PCC laying. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 60 | 2026-09-28 |  |  | continue work | FALSE | 0.945 | English | train
UPD-01328 | whatsapp | site_diary | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Sir, no progress on foundation f15 reinforcement today due to vendor technician not available. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | delay | DELAYED | 10 |  |  | vendor technician not available | resume after clearance | FALSE | 0.912 | English | train
UPD-00583 | word_document | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-22 Discipline: Piping Observation: Hydrotest Line 23 remains on hold due to power supply interruption. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | obtain permit | FALSE | 0.942 | English | train
UPD-01066 | ms_project_update | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Today: MS Project note: INS-JB05-001 progress affected by insufficient manpower; expected finish to move. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | resume after clearance | FALSE | 0.938 | English | train
UPD-01143 | whatsapp | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: Line/area update: weld line 23 is complete as of today. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-04 | 2026-09-04 |  | complete inspection | FALSE | 0.959 | English | train
UPD-00281 | excel_note | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: MEC-P04-001 ¦ Align Pump P04 ¦ RESUMED ¦ NA Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 40 | 2026-09-01 |  |  | obtain permit | FALSE | 0.926 | English | train
UPD-01392 | email | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - PIP-L24-002 Dear Team, Weld Line 24 resumed today after insufficient manpower was cleared. Regards, Site Supervisor FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-05 |  |  | planner review | FALSE | 0.95 | English | train
UPD-01749 | pdf_text | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ CIV-R02-002 ¦ Started Road R02 PCC laying this morning. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 30 | 2026-09-27 |  |  | complete inspection | FALSE | 0.926 | English | train
UPD-01135 | ms_project_update | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Today: MS Project note: CIV-TK01-001 progress affected by insufficient manpower; expected finish to move. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | insufficient manpower | receive material | FALSE | 0.971 | English | train
UPD-00963 | site_diary | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | Date 2026-09-06 ¦ Unit 2 ¦ No progress on Install Valve V12 today due to crane unavailable. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | delay | DELAYED | 30 |  |  | crane unavailable | resume after clearance | FALSE | 0.938 | English | train
UPD-00666 | ms_project_update | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | MS Project note: ELE-CBL07-001 progress affected by access road blocked; expected finish to move. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 20 |  |  | access road blocked | planner review | FALSE | 0.937 | English | train
UPD-00926 | whatsapp | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Complete work-at-height insp. remains not started. 👍 Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.96 | English | train
UPD-00534 | site_diary | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-13 ¦ Unit 2 ¦ Hydrotest Line 23 is blocked pending work permit not issued. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | mobilise crew | FALSE | 0.951 | English | train
UPD-00689 | email | document | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-F15-003 Dear Team, No start for Foundation F15 concreting today. Regards, Site Supervisor | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.924 | English | train
UPD-00229 | ms_project_update | document | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-003 status = CANCELLED. Material expected tomorrow. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.988 | English | train
UPD-01463 | ms_project_update | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: MEC-P04-001 progress affected by design revision pending; expected finish to move. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 50 |  |  | design revision pending | continue work | FALSE | 0.923 | English | train
UPD-01521 | email | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L23-003 Dear Team, Only part of Hydrotest Line 23 could be completed today. Regards, Site Supervisor Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-16 |  |  | planner review | FALSE | 0.915 | English | train
UPD-01071 | site_diary | email | 2026-09-21 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-21 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 is about 30% complete. Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 30 | 2026-09-21 |  |  | complete inspection | FALSE | 0.944 | English | train
UPD-01300 | site_diary | spreadsheet | 2026-09-02 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-02 ¦ Unit 2 ¦ Hydrotest Line 24 has resumed following resolution of the earlier issue. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 50 | 2026-09-02 |  |  | resume after clearance | FALSE | 0.963 | English | train
UPD-00228 | site_diary | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Today: Date 2026-09-14 ¦ Tank Farm ¦ Tank T01 foundation completion is delayed because of safety clearance pending. Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 30 |  |  | safety clearance pending | update schedule | FALSE | 0.988 | English | train
UPD-00511 | excel_note | email | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: PIP-L23-003 ¦ Hydrotest Line 23 ¦ RESUMED ¦ NA For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.971 | English | train
UPD-00775 | word_document | document | 2026-09-09 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-09 Discipline: Civil Observation: Around 50% work done on Foundation F15 reinforcement; balance is ongoing. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-09 |  |  | continue work | FALSE | 0.959 | English | train
UPD-00545 | whatsapp | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: Sir, install 30-inch header has resumed following resolution of the earlier issue. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 50 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.927 | English | train
UPD-00780 | site_diary | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-03 ¦ Compressor Area ¦ Install Compressor C01 is about 50% complete. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 50 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.926 | English | train
UPD-00995 | email | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Install MCC Panel 3 commenced at Electrical Room. Regards, Site Supervisor FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 80 | 2026-09-16 |  |  | update schedule | FALSE | 0.957 | English | train
UPD-00012 | ms_project_update | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: HSE-002-001 status = IN PROGRESS. Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | progress | IN_PROGRESS | 20 | 2026-09-20 |  |  | resume after clearance | FALSE | 0.938 | English | train
UPD-00502 | word_document | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-28 Discipline: Civil Observation: Today's Foundation F15 excavation activity has been cancelled. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.977 | English | train
UPD-00798 | plain_text | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Today: Install Pump P03 partially completed today. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 90 | 2026-09-24 |  |  | mobilise crew | FALSE | 0.981 | English | train
UPD-01242 | voice_transcript | document | 2026-09-11 | OIL-UNIT2-DEMO | Unit update: Uh, execution of install heat exchanger hx01 is blocked by valve not available at site. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | valve not available at site | mobilise crew | FALSE | 0.951 | English | train
UPD-00327 | pdf_text | document | 2026-09-23 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ CIV-R02-002 ¦ Work for Road R02 PCC laying is finished. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | receive material | FALSE | 0.973 | English | train
UPD-00972 | word_document | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-29 Discipline: Civil Observation: Road R02 subgrade preparation progressing as planned. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 80 | 2026-09-29 |  |  | update schedule | FALSE | 0.955 | English | train
UPD-01163 | whatsapp | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Today: Line/area update: no progress on install 30-inch header today due to drawing approval pending. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 50 |  |  | drawing approval pending | receive material | FALSE | 0.955 | English | train
UPD-01147 | email | email | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-F15-001 Dear Team, Foundation F15 excavation could not proceed today due to design revision pending. Regards, Site Supervisor FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | delay | DELAYED | 30 |  |  | design revision pending | resume after clearance | FALSE | 0.956 | English | train
UPD-01142 | plain_text | DPR | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: Hydrotest Line 24 held up by client approval pending. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | client approval pending | planner review | FALSE | 0.94 | English | train
UPD-00109 | word_document | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-29 Discipline: HSE Observation: Cannot continue Complete work-at-height inspection until access road blocked is resolved. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | access road blocked | planner review | FALSE | 0.925 | English | train
UPD-00731 | site_diary | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-13 ¦ Unit 2 ¦ Only part of Hydrotest Line 24 could be completed today. Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-13 |  |  | update schedule | FALSE | 0.921 | English | train
UPD-00127 | ms_project_update | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-F15-001 status = CANCELLED. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.934 | English | train
UPD-01037 | plain_text | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Crew resumed Foundation F15 excavation after clearance. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.983 | English | train
UPD-00195 | plain_text | email | 2026-09-04 | OIL-UNIT2-DEMO | Today: Install Transformer TR02 is behind plan owing to late material inspection. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | delay | DELAYED | 80 |  |  | late material inspection | complete inspection | FALSE | 0.945 | English | train
UPD-01750 | ms_project_update | DPR | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: MS Project update: ELE-MCC03-001 Actual % Complete = 60% as of 2026-09-11. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 60 | 2026-09-11 |  |  | complete inspection | FALSE | 0.971 | English | train
UPD-01213 | ms_project_update | document | 2026-09-29 | OIL-UNIT2-DEMO | Today: MS Project update: MEC-P03-001 actual start = 2026-09-29; work commenced. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 40 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.941 | English | train
UPD-01484 | site_diary | document | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-17 ¦ Unit 2 ¦ Install Unit 2 lighting cancelled for today. FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.912 | English | train
UPD-01130 | pdf_text | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ PIP-L24-003 ¦ Work on Hydrotest Line 24 was stopped because material not received. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | material not received | obtain permit | FALSE | 0.959 | English | train
UPD-01567 | voice_transcript | document | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that install transformer tr02 partially comp. today. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 20 | 2026-09-18 |  |  | update schedule | FALSE | 0.976 | English | train
UPD-01446 | voice_transcript | MS_Project | 2026-09-19 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, erect line 24 has not started yet. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.908 | English | train
UPD-00852 | excel_note | email | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - CIV-TK01-001 ¦ Tank T01 foundation completion ¦ CANCELLED ¦ NA Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.907 | English | train
UPD-00244 | plain_text | document | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Only part of Foundation F15 concreting could be completed today. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-21 |  |  | obtain permit | FALSE | 0.91 | English | train
UPD-01773 | word_document | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-30 Discipline: Civil Observation: Road R02 PCC laying will not be executed today. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.964 | English | train
UPD-01677 | pdf_text | DPR | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 is complete as of today. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | resume after clearance | FALSE | 0.946 | English | train
UPD-01623 | plain_text | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | Today: Terminate Junction Box JB05 held up by material not received. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 60 |  |  | material not received | complete inspection | FALSE | 0.907 | English | train
UPD-00493 | plain_text | DPR | 2026-09-10 | OIL-UNIT2-DEMO | Progress note: Partial progress achieved on Complete work-at-height inspection. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-10 |  |  | update schedule | FALSE | 0.96 | English | train
UPD-00625 | plain_text | mobile | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Hydrotest Line 24 progressing as planned. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-22 |  |  | receive material | FALSE | 0.97 | English | train
UPD-00973 | whatsapp | email | 2026-09-24 | OIL-UNIT2-DEMO | Site Update: Hi, planned work close scaffold inspection actions did not commence. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.99 | English | train
UPD-00121 | site_diary | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-19 ¦ Unit 2 ¦ Complete work-at-height inspection has been completed at Unit 2. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | mobilise crew | FALSE | 0.986 | English | train
UPD-00092 | email | mobile | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - PIP-V12-001 Dear Team, Execution of Install Valve V12 is blocked by inspection clearance pending. Regards, Site Supervisor For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | continue work | FALSE | 0.971 | English | train
UPD-00606 | whatsapp | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Progress note: Sir, crew resumed install 30-inch header after clearance. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 20 | 2026-09-30 |  |  | update schedule | FALSE | 0.978 | English | train
UPD-00360 | email | email | 2026-09-29 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L30-001 Dear Team, Execution of Install 30-inch header is blocked by valve not available at site. Regards, Site Supervisor Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | valve not available at site | continue work | FALSE | 0.909 | English | train
UPD-00260 | plain_text | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Only part of Erect Line 23 could be completed today. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-30 |  |  | resume after clearance | FALSE | 0.973 | English | train
UPD-01055 | email | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Crew mobilised and started Install MCC Panel 3. Regards, Site Supervisor For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 60 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.923 | English | train
UPD-01524 | site_diary | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-16 ¦ Unit 2 ¦ No start for Hydrotest Line 24 today. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.955 | English | train
UPD-00432 | email | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - MEC-P03-001 Dear Team, Work on Install Pump P03 has begun. Regards, Site Supervisor Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 20 | 2026-09-10 |  |  | continue work | FALSE | 0.927 | English | train
UPD-00379 | plain_text | DPR | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: Crew mobilised and started Install Pump P03. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 80 | 2026-09-12 |  |  | mobilise crew | FALSE | 0.914 | English | train
UPD-01604 | whatsapp | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Today: Work is continuing on Erect Line 23. 👍 FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-27 |  |  | continue work | FALSE | 0.927 | English | train
UPD-00849 | plain_text | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Partial progress achieved on Install Valve V12. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-24 |  |  | continue work | FALSE | 0.959 | English | train
UPD-00728 | plain_text | DPR | 2026-09-10 | OIL-UNIT2-DEMO | No start for Erect Line 24 today. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.951 | English | train
UPD-01309 | plain_text | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Install 30-inch header commenced at Unit 1. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 20 | 2026-09-29 |  |  | continue work | FALSE | 0.939 | English | train
UPD-01411 | email | document | 2026-09-27 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - MEC-P04-001 Dear Team, No start for Align Pump P04 today. Regards, Site Supervisor Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.979 | English | train
UPD-00653 | site_diary | mobile | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-11 ¦ Unit 2 ¦ Hydrotest Line 24 is about 75% complete. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-11 |  |  | planner review | FALSE | 0.908 | English | train
UPD-01136 | ms_project_update | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Today: MS Project note: INS-JB05-001 progress affected by crane unavailable; expected finish to move. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | crane unavailable | receive material | FALSE | 0.951 | English | train
UPD-01336 | site_diary | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-20 ¦ Unit 2 ¦ Started Foundation F15 reinforcement this morning. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 20 | 2026-09-20 |  |  | obtain permit | FALSE | 0.973 | English | train
UPD-01479 | word_document | mobile | 2026-09-17 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-17 Discipline: Piping Observation: Weld Line 23 cancelled for today. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.929 | English | train
UPD-01195 | pdf_text | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 is in progress. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 80 | 2026-09-19 |  |  | receive material | FALSE | 0.911 | English | train
UPD-01471 | pdf_text | document | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ INS-CV11-001 ¦ Crew resumed Install Control Valve CV11 after clearance. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 30 | 2026-09-27 |  |  | obtain permit | FALSE | 0.965 | English | train
UPD-01589 | pdf_text | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ CIV-R02-002 ¦ Road R02 PCC laying progressing as planned. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 30 | 2026-09-12 |  |  | update schedule | FALSE | 0.914 | English | train
UPD-01632 | site_diary | mobile | 2026-09-09 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-09 ¦ Unit 1 ¦ Planned work Install 30-inch header did not commence. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.911 | English | train
UPD-01081 | plain_text | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Work is continuing on Lay Cable Route 7. Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-04 |  |  | mobilise crew | FALSE | 0.919 | English | train
UPD-01164 | plain_text | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Daily Progress: Install Valve V12 commenced at Unit 2. Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-17 |  |  | update schedule | FALSE | 0.96 | English | train
UPD-01259 | email | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Install Heat Exchanger HX01 partially completed today. Regards, Site Supervisor Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | partial_progress | PARTIAL | 60 | 2026-09-05 |  |  | continue work | FALSE | 0.903 | English | train
UPD-00605 | pdf_text | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ PIP-L23-001 ¦ Erect Line 23 resumed today after material not received was cleared. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | resumption | RESUMED | 10 | 2026-09-08 |  |  | receive material | FALSE | 0.924 | English | train
UPD-01554 | word_document | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-23 Discipline: HSE Observation: No progress on Complete work-at-height inspection today due to vendor technician not available. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | delay | DELAYED | 60 |  |  | vendor technician not available | mobilise crew | FALSE | 0.965 | English | train
UPD-00010 | word_document | email | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-05 Discipline: Civil Observation: Foundation F15 concreting will not be executed today. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.904 | English | train
UPD-00097 | site_diary | mobile | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-12 ¦ Unit 1 ¦ Work on Install Pressure Transmitter PT08 was stopped because welding machine under maintenance. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | delay | DELAYED | 10 |  |  | welding machine under maintenance | update schedule | FALSE | 0.945 | English | train
UPD-01544 | plain_text | DPR | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: Started Install Compressor C01 this morning. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 20 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.984 | English | train
UPD-01020 | whatsapp | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Road R02 subgrade preparation has been completed at Plant Area. 👍 FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | mobilise crew | FALSE | 0.965 | English | train
UPD-00154 | site_diary | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-11 ¦ Pump House ¦ Install Pump P03 has resumed following resolution of the earlier issue. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 10 | 2026-09-11 |  |  | complete inspection | FALSE | 0.944 | English | train
UPD-00795 | ms_project_update | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | MS Project update: CIV-F15-001 Actual % Complete = 90% as of 2026-09-11. Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-11 |  |  | continue work | FALSE | 0.928 | English | train
UPD-01460 | site_diary | mobile | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-11 ¦ Unit 1 ¦ Install 30-inch header resumed today after material not received was cleared. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 40 | 2026-09-11 |  |  | update schedule | FALSE | 0.929 | English | train
UPD-00836 | plain_text | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | DPR Update: Team finished Install Control Valve CV11. Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | resume after clearance | FALSE | 0.919 | English | train
UPD-00549 | voice_transcript | email | 2026-09-25 | OIL-UNIT2-DEMO | So, basically, install mcc panel 3 has resumed following resolution of the earlier issue. Material expected tomorrow. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 70 | 2026-09-25 |  |  | continue work | FALSE | 0.989 | English | train
UPD-01453 | site_diary | DPR | 2026-09-30 | OIL-UNIT2-DEMO | Date 2026-09-30 ¦ Unit 2 ¦ Terminate Junction Box JB05 is blocked pending shortage of 24-inch pipes. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | complete inspection | FALSE | 0.953 | English | train
UPD-00117 | pdf_text | document | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ PIP-L24-002 ¦ Execution of Weld Line 24 is blocked by equipment breakdown. Material expected tomorrow. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | continue work | FALSE | 0.966 | English | train
UPD-00319 | email | email | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 done at site. Regards, Site Supervisor Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | update schedule | FALSE | 0.956 | English | train
UPD-00897 | whatsapp | email | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Sir, only part of road r02 subgrade preparation could be comp. today. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 80 | 2026-09-09 |  |  | update schedule | FALSE | 0.947 | English | train
UPD-01409 | word_document | mobile | 2026-09-05 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-05 Discipline: Piping Observation: Hydrotest Line 23 done at site. Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | update schedule | FALSE | 0.972 | English | train
UPD-00567 | site_diary | DPR | 2026-09-01 | OIL-UNIT2-DEMO | Today: Date 2026-09-01 ¦ Unit 2 ¦ Only part of Install Unit 2 lighting could be comp. today. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-01 |  |  | obtain permit | FALSE | 0.951 | English | train
UPD-01304 | excel_note | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | DPR Update: CIV-TK01-001 ¦ Tank T01 foundation completion ¦ COMPLETED ¦ NA Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | planner review | FALSE | 0.945 | English | train
UPD-00344 | site_diary | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-22 ¦ Unit 1 ¦ Work on Close scaffold inspection actions has begun. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | start | STARTED | 60 | 2026-09-22 |  |  | obtain permit | FALSE | 0.937 | English | train
UPD-01437 | pdf_text | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 17-09-2026 ¦ MEC-C01-001 ¦ Install Compressor C01 is about 25% complete. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 25 | 2026-09-17 |  |  | continue work | FALSE | 0.911 | English | train
UPD-01713 | ms_project_update | email | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: MS Project note: MEC-C01-001 status = NOT STARTED. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.91 | English | train
UPD-01258 | word_document | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-11 Discipline: Civil Observation: Foundation F15 concreting completed today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | mobilise crew | FALSE | 0.934 | English | train
UPD-01002 | site_diary | mobile | 2026-09-20 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-20 ¦ Unit 2 ¦ Terminate Junction Box JB05 done at site. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | mobilise crew | FALSE | 0.97 | English | train
UPD-00388 | word_document | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-02 Discipline: Mechanical Observation: Align Pump P04 has not started yet. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.928 | English | train
UPD-00258 | site_diary | email | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-13 ¦ Pump House ¦ Partial progress achieved on Align Pump P04. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.901 | English | train
UPD-01371 | site_diary | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-15 ¦ Unit 2 ¦ Weld Line 24 started today. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-15 |  |  | update schedule | FALSE | 0.944 | English | train
UPD-01286 | site_diary | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-18 ¦ Unit 2 ¦ Work on Foundation F15 reinforcement was stopped because material not received. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | delay | DELAYED | 80 |  |  | material not received | mobilise crew | FALSE | 0.962 | English | train
UPD-00427 | ms_project_update | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: MS Project note: ELE-TR02-001 status = NOT STARTED. Please note. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.956 | English | train
UPD-01123 | excel_note | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Unit update: PIP-L24-001 ¦ Erect Line 24 ¦ BLOCKED ¦ client approval pending Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | complete inspection | FALSE | 0.917 | English | train
UPD-00826 | pdf_text | DPR | 2026-09-03 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ CIV-F15-002 ¦ Foundation F15 reinforcement remains on hold due to design revision pending. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | mobilise crew | FALSE | 0.902 | English | train
UPD-00159 | pdf_text | email | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 14-09-2026 ¦ CIV-R02-001 ¦ Partial progress achieved on Road R02 subgrade preparation. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 75 | 2026-09-14 |  |  | obtain permit | FALSE | 0.974 | English | train
UPD-01490 | plain_text | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: Crew resumed Install 30-inch header after clearance. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 30 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.948 | English | train
UPD-01109 | excel_note | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: PIP-L24-002 ¦ Weld Line 24 ¦ BLOCKED ¦ material not received For information. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | continue work | FALSE | 0.967 | English | train
UPD-00570 | pdf_text | site_diary | 2026-09-13 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ INS-PT08-001 ¦ Partial progress achieved on Install Pressure Transmitter PT08. Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 60 | 2026-09-13 |  |  | continue work | FALSE | 0.906 | English | train
UPD-00992 | site_diary | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-08 ¦ Unit 2 ¦ Complete work-at-height inspection commenced at Unit 2. Kindly update the plan. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | start | STARTED | 80 | 2026-09-08 |  |  | receive material | FALSE | 0.963 | English | train
UPD-01021 | site_diary | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Today: Date 2026-09-27 ¦ Unit 2 ¦ Around 50% work completed on Install Control Valve CV11; balance is ongoing. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-27 |  |  | obtain permit | FALSE | 0.924 | English | train
UPD-01331 | word_document | MS_Project | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-25 Discipline: Piping Observation: Hydrotest Line 24 is blocked pending QA/QC hold point not cleared. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | obtain permit | FALSE | 0.924 | English | train
UPD-01508 | site_diary | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Date 2026-09-19 ¦ Unit 2 ¦ Crew resumed Foundation F15 concreting after clearance. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-19 |  |  | receive material | FALSE | 0.923 | English | train
UPD-00532 | plain_text | document | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: Weld Line 23 held up by client approval pending. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | client approval pending | complete inspection | FALSE | 0.925 | English | train
UPD-00643 | word_document | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-13 Discipline: Mechanical Observation: Install Heat Exchanger HX01 partially completed today. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | obtain permit | FALSE | 0.989 | English | train
UPD-01315 | email | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - CIV-TK01-001 Dear Team, Today's Tank T01 foundation completion activity has been cancelled. Regards, Site Supervisor Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.918 | English | train
UPD-00555 | site_diary | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-24 ¦ Unit 2 ¦ Erect Line 23 is behind plan owing to QA/QC hold point not cleared. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | QA/QC hold point not cleared | planner review | FALSE | 0.967 | English | train
UPD-00591 | ms_project_update | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: MS Project update: CIV-R02-001 actual start = 2026-09-01; work commenced. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 50 | 2026-09-01 |  |  | resume after clearance | FALSE | 0.935 | English | train
UPD-01072 | pdf_text | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ CIV-F15-003 ¦ Foundation F15 concreting started today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 10 | 2026-09-05 |  |  | complete inspection | FALSE | 0.976 | English | train
UPD-01280 | voice_transcript | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Today: So, basically, started install temperature transmitter t04 this morning. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-08 |  |  | complete inspection | FALSE | 0.921 | English | train
UPD-00330 | ms_project_update | mobile | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: MS Project note: INS-JB05-001 progress affected by rainfall at site; expected finish to move. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 40 |  |  | rainfall at site | receive material | FALSE | 0.935 | English | train
UPD-01014 | excel_note | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: INS-CV11-001 ¦ Install Control Valve CV11 ¦ PARTIAL ¦ NA Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-18 |  |  | obtain permit | FALSE | 0.902 | English | train
UPD-01493 | voice_transcript | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - So, basically, tank t01 foundation completion partially completed today. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 25 | 2026-09-26 |  |  | obtain permit | FALSE | 0.91 | English | train
UPD-00601 | email | document | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Crew mobilised and started Install Heat Exchanger HX01. Regards, Site Supervisor FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 70 | 2026-09-17 |  |  | continue work | FALSE | 0.935 | English | train
UPD-00194 | whatsapp | mobile | 2026-09-30 | OIL-UNIT2-DEMO | Unit update: Hi, install valve v12 remains not started. Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.989 | English | train
UPD-01027 | excel_note | email | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: HSE-001-001 ¦ Complete work-at-height inspection ¦ BLOCKED ¦ insufficient manpower Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | mobilise crew | FALSE | 0.923 | English | train
UPD-01042 | ms_project_update | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: PIP-L24-003 status = CANCELLED. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.971 | English | train
UPD-00622 | voice_transcript | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Daily Progress: Uh, crew resumed close scaffold inspection actions after clearance. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 80 | 2026-09-24 |  |  | continue work | FALSE | 0.956 | English | train
UPD-01226 | whatsapp | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Hi, crew is currently working on road r02 pcc laying. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 50 | 2026-09-02 |  |  | complete inspection | FALSE | 0.912 | English | train
UPD-00349 | email | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting has been completed at Unit 2. Regards, Site Supervisor | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-01 | 2026-09-01 |  | update schedule | FALSE | 0.905 | English | train
UPD-01747 | voice_transcript | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Uh, cannot continue hydrotest line 24 until safety clearance pending is resolved. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | planner review | FALSE | 0.902 | English | train
UPD-01332 | email | mobile | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - INS-CV11-001 Dear Team, Install Control Valve CV11 has resumed following resolution of the earlier issue. Regards, Site Supervisor For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 70 | 2026-09-24 |  |  | mobilise crew | FALSE | 0.917 | English | train
UPD-01107 | site_diary | mobile | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-13 ¦ Pump House ¦ Align Pump P04 remains not started. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.928 | English | train
UPD-00536 | whatsapp | mobile | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Install Compressor C01 is blocked pending inspection clearance pending. 👍 Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | inspection clearance pending | resume after clearance | FALSE | 0.905 | English | train
UPD-01791 | word_document | document | 2026-09-18 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-18 Discipline: Mechanical Observation: Cannot continue Align Pump P04 until insufficient manpower is resolved. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | insufficient manpower | complete inspection | FALSE | 0.951 | English | train
UPD-01040 | pdf_text | email | 2026-09-23 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ INS-PT08-001 ¦ Partial progress achieved on Install Pressure Transmitter PT08. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 10 | 2026-09-23 |  |  | update schedule | FALSE | 0.963 | English | train
UPD-01283 | ms_project_update | document | 2026-09-22 | OIL-UNIT2-DEMO | MS Project note: PIP-L30-001 progress affected by valve not available at site; expected finish to move. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | valve not available at site | mobilise crew | FALSE | 0.922 | English | train
UPD-00750 | ms_project_update | email | 2026-09-29 | OIL-UNIT2-DEMO | MS Project note: INS-PT08-001 status = CANCELLED. Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.914 | English | train
UPD-01023 | voice_transcript | email | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that install pump p03 has resumed following resolution of the earlier issue. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 40 | 2026-09-09 |  |  | resume after clearance | FALSE | 0.909 | English | train
UPD-00778 | ms_project_update | email | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: MS Project note: CIV-TK01-001 status = RESUMED. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 60 | 2026-09-29 |  |  | planner review | FALSE | 0.948 | English | train
UPD-01680 | plain_text | document | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Around 50% work complete on Foundation F15 excavation; balance is ongoing. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-02 |  |  | planner review | FALSE | 0.987 | English | train
UPD-01187 | site_diary | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-26 ¦ Pump House ¦ Work on Align Pump P04 has begun. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 80 | 2026-09-26 |  |  | obtain permit | FALSE | 0.976 | English | train
UPD-01374 | pdf_text | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ ELE-LTG02-001 ¦ Work is continuing on Install Unit 2 lighting. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-04 |  |  | mobilise crew | FALSE | 0.962 | English | train
UPD-01459 | word_document | document | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-24 Discipline: Civil Observation: Only part of Road R02 PCC laying could be completed today. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 25 | 2026-09-24 |  |  | continue work | FALSE | 0.915 | English | train
UPD-00184 | plain_text | DPR | 2026-09-28 | OIL-UNIT2-DEMO | Today: Planned work Weld Line 24 did not commence. FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.903 | English | train
UPD-01736 | voice_transcript | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Site Update: Just to update you, install 30-inch header partially completed today. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 25 | 2026-09-30 |  |  | mobilise crew | FALSE | 0.956 | English | train
UPD-01362 | ms_project_update | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: INS-JB05-001 status = IN PROGRESS. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.919 | English | train
UPD-00989 | whatsapp | email | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Hydrotest Line 24 completed today. 👍 Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | obtain permit | FALSE | 0.926 | English | train
UPD-01514 | site_diary | email | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-13 ¦ Unit 1 ¦ Started Install 30-inch header this morning. Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 10 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.913 | English | train
UPD-00144 | pdf_text | mobile | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-V12-001 ¦ Install Valve V12 progressing as planned. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-22 |  |  | continue work | FALSE | 0.914 | English | train
UPD-01678 | whatsapp | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Sir, weld line 23 partially completed today. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-18 |  |  | update schedule | FALSE | 0.967 | English | train
UPD-00091 | plain_text | email | 2026-09-02 | OIL-UNIT2-DEMO | Today: Erect Line 23 is complete as of today. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | resume after clearance | FALSE | 0.934 | English | train
UPD-01165 | site_diary | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-21 ¦ Compressor Area ¦ Work on Install Compressor C01 restarted today. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 80 | 2026-09-21 |  |  | mobilise crew | FALSE | 0.945 | English | train
UPD-00335 | email | mobile | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Planned work Road R02 PCC laying did not commence. Regards, Site Supervisor Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.928 | English | train
UPD-00718 | voice_transcript | DPR | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that foundation f15 excavation resumed today after insufficient manpower was cleared. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 60 | 2026-09-16 |  |  | continue work | FALSE | 0.905 | English | train
UPD-00173 | word_document | mobile | 2026-09-11 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-11 Discipline: Piping Observation: Crew is currently working on Weld Line 23. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-11 |  |  | planner review | FALSE | 0.943 | English | train
UPD-00676 | word_document | email | 2026-09-28 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-28 Discipline: Civil Observation: Foundation F15 reinforcement remains on hold due to safety clearance pending. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | complete inspection | FALSE | 0.945 | English | train
UPD-00339 | word_document | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-13 Discipline: Civil Observation: Foundation F15 excavation remains on hold due to inspection clearance pending. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | receive material | FALSE | 0.927 | English | train
UPD-01067 | site_diary | document | 2026-09-08 | OIL-UNIT2-DEMO | Today: Date 2026-09-08 ¦ Electrical Room ¦ Work on Install MCC Panel 3 restarted today. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 10 | 2026-09-08 |  |  | planner review | FALSE | 0.919 | English | train
UPD-00452 | voice_transcript | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | So, basically, install pump p03 held up by vendor technician not available. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 30 |  |  | vendor technician not available | complete inspection | FALSE | 0.94 | English | train
UPD-00381 | pdf_text | document | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ CIV-F15-001 ¦ Work on Foundation F15 excavation was stopped because valve not available at site. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | delay | DELAYED | 20 |  |  | valve not available at site | mobilise crew | FALSE | 0.94 | English | train
UPD-00909 | voice_transcript | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Daily Progress: So, basically, foundation f15 concreting commenced at unit 2. Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 30 | 2026-09-01 |  |  | resume after clearance | FALSE | 0.937 | English | train
UPD-00711 | plain_text | document | 2026-09-17 | OIL-UNIT2-DEMO | Install Heat Exchanger HX01 cancelled for today. Material expected tomorrow. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.976 | English | train
UPD-00088 | site_diary | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-23 ¦ Unit 2 ¦ Crew mobilised and started Erect Line 24. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-23 |  |  | update schedule | FALSE | 0.904 | English | train
UPD-01033 | email | DPR | 2026-09-28 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - MEC-C01-001 Dear Team, Team finished Install Compressor C01. Regards, Site Supervisor | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | resume after clearance | FALSE | 0.906 | English | train
UPD-00274 | site_diary | mobile | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-03 ¦ Unit 2 ¦ Complete work-at-height inspection has resumed following resolution of the earlier issue. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | resumption | RESUMED | 10 | 2026-09-03 |  |  | continue work | FALSE | 0.949 | English | train
UPD-00560 | whatsapp | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Sir, planned work install transformer tr02 did not commence. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.957 | English | train
UPD-01401 | pdf_text | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ ELE-TR02-001 ¦ Install Transformer TR02 remains not started. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.924 | English | train
UPD-00535 | email | email | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Work is continuing on Road R02 PCC laying. Regards, Site Supervisor | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 10 | 2026-09-29 |  |  | planner review | FALSE | 0.907 | English | train
UPD-00400 | site_diary | email | 2026-09-15 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-15 ¦ Tank Farm ¦ Work on Tank T01 foundation completion has begun. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | start | STARTED | 30 | 2026-09-15 |  |  | resume after clearance | FALSE | 0.953 | English | train
UPD-00277 | site_diary | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-03 ¦ Unit 2 ¦ Today's Foundation F15 reinforcement activity has been cancelled. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.96 | English | train
UPD-00113 | whatsapp | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: Line/area update: no start for install compressor c01 today. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.989 | English | train
UPD-00031 | pdf_text | email | 2026-09-06 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ CIV-F15-002 ¦ Foundation F15 reinforcement remains on hold due to late material inspection. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | obtain permit | FALSE | 0.974 | English | train
UPD-00483 | ms_project_update | email | 2026-09-15 | OIL-UNIT2-DEMO | Today: MS Project note: PIP-L30-001 status = CANCELLED. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.988 | English | train
UPD-00147 | email | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 has not started yet. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.924 | English | train
UPD-00480 | email | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - HSE-001-001 Dear Team, Complete work-at-height inspection is about 20% complete. Regards, Site Supervisor For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-04 |  |  | planner review | FALSE | 0.913 | English | train
UPD-00693 | voice_transcript | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Okay, today's update is that today's install heat exchanger hx01 activity has been cancelled. Material expected tomorrow. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.907 | English | train
UPD-00568 | email | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Today's Install Heat Exchanger HX01 activity has been cancelled. Regards, Site Supervisor FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.919 | English | train
UPD-01311 | ms_project_update | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: MS Project update: ELE-CBL07-001 Actual % Complete = 20% as of 2026-09-07. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-07 |  |  | update schedule | FALSE | 0.905 | English | train
UPD-00962 | pdf_text | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ ELE-TR02-001 ¦ Install Transformer TR02 complete today. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | resume after clearance | FALSE | 0.934 | English | train
UPD-00011 | pdf_text | site_diary | 2026-09-13 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ ELE-LTG02-001 ¦ Supervisor confirms Install Unit 2 lighting completed. FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | receive material | FALSE | 0.919 | English | train
UPD-01036 | email | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - CIV-F15-002 Dear Team, Today's Foundation F15 reinforcement activity has been cancelled. Regards, Site Supervisor For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.944 | English | train
UPD-00463 | plain_text | document | 2026-09-29 | OIL-UNIT2-DEMO | Today: Terminate Junction Box JB05 progressing as planned. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-29 |  |  | obtain permit | FALSE | 0.911 | English | train
UPD-00692 | plain_text | document | 2026-09-11 | OIL-UNIT2-DEMO | Today: Around 50% work done on Weld Line 24; balance is ongoing. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.989 | English | train
UPD-01043 | site_diary | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Today: Date 2026-09-13 ¦ Unit 2 ¦ Work on Hydrotest Line 24 has begun. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-13 |  |  | receive material | FALSE | 0.951 | English | train
UPD-00423 | ms_project_update | document | 2026-09-26 | OIL-UNIT2-DEMO | Unit update: MS Project update: ELE-CBL07-001 marked 100% complete. Actual Finish: 2026-09-26. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | receive material | FALSE | 0.949 | English | train
UPD-00026 | site_diary | document | 2026-09-18 | OIL-UNIT2-DEMO | Date 2026-09-18 ¦ Tank Farm ¦ Install Tank T02 internals progressing as planned. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | progress | IN_PROGRESS | 10 | 2026-09-18 |  |  | receive material | FALSE | 0.937 | English | train
UPD-01703 | voice_transcript | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: So, basically, foundation f15 excavation remains on hold due to qa/qc hold point not cleared. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | update schedule | FALSE | 0.977 | English | train
UPD-00801 | site_diary | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-13 ¦ Unit 2 ¦ Only part of Hydrotest Line 24 could be completed today. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-13 |  |  | update schedule | FALSE | 0.945 | English | train
UPD-01154 | site_diary | spreadsheet | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-01 ¦ Unit 2 ¦ Crew resumed Hydrotest Line 23 after clearance. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 70 | 2026-09-01 |  |  | complete inspection | FALSE | 0.978 | English | train
UPD-00710 | whatsapp | email | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: Hi, around 50% work completed on terminate junction box jb05; balance is ongoing. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-06 |  |  | obtain permit | FALSE | 0.973 | English | train
UPD-00706 | word_document | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-22 Discipline: Mechanical Observation: Started Install Pump P03 this morning. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 60 | 2026-09-22 |  |  | obtain permit | FALSE | 0.939 | English | train
UPD-01217 | word_document | document | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-25 Discipline: HSE Observation: Complete work-at-height inspection is behind plan owing to drawing approval pending. Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | delay | DELAYED | 20 |  |  | drawing approval pending | obtain permit | FALSE | 0.921 | English | train
UPD-00965 | whatsapp | document | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Line/area update: hydrotest line 23 is complete as of today. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | receive material | FALSE | 0.969 | English | train
UPD-00685 | site_diary | site_diary | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-26 ¦ Unit 2 ¦ Crew is currently working on Terminate Junction Box JB05. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-26 |  |  | mobilise crew | FALSE | 0.937 | English | train
UPD-00445 | word_document | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-02 Discipline: Civil Observation: Today's Foundation F15 excavation activity has been cancelled. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.942 | English | train
UPD-00247 | excel_note | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: MEC-P04-001 ¦ Align Pump P04 ¦ CANCELLED ¦ NA FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.983 | English | train
UPD-00908 | excel_note | DPR | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: ELE-LTG02-001 ¦ Install Unit 2 lighting ¦ NOT STARTED ¦ NA FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.915 | English | train
UPD-00505 | voice_transcript | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Today: Just to update you, planned work close scaffold inspection actions did not commence. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.945 | English | train
UPD-00539 | email | email | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Today's Install Tank T02 internals activity has been cancelled. Regards, Site Supervisor Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.927 | English | train
UPD-01663 | whatsapp | DPR | 2026-09-02 | OIL-UNIT2-DEMO | Site Update: Crew is currently working on Install Transformer TR02. 👍 | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 10 | 2026-09-02 |  |  | resume after clearance | FALSE | 0.909 | English | train
UPD-01591 | plain_text | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - Crew is currently working on Hydrotest Line 23. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-07 |  |  | resume after clearance | FALSE | 0.972 | English | train
UPD-00066 | plain_text | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: Work is continuing on Foundation F15 reinforcement. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-03 |  |  | complete inspection | FALSE | 0.944 | English | train
UPD-00954 | plain_text | email | 2026-09-09 | OIL-UNIT2-DEMO | Today: Install 30-inch header has resumed following resolution of the earlier issue. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 80 | 2026-09-09 |  |  | update schedule | FALSE | 0.906 | English | train
UPD-01334 | site_diary | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-09 ¦ Unit 2 ¦ Started Hydrotest Line 24 this morning. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-09 |  |  | planner review | FALSE | 0.971 | English | train
UPD-00769 | voice_transcript | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: Uh, terminate junction box jb05 cancelled for today. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.986 | English | train
UPD-00620 | voice_transcript | email | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Uh, weld line 23 is about 10% complete. Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-02 |  |  | continue work | FALSE | 0.947 | English | train
UPD-01779 | email | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 has not started yet. Regards, Site Supervisor For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.965 | English | train
UPD-01361 | pdf_text | email | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ PIP-L23-001 ¦ Planned work Erect Line 23 did not commence. Material expected tomorrow. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.938 | English | train
UPD-01223 | ms_project_update | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | DPR Update: MS Project note: ELE-MCC03-001 progress affected by crane unavailable; expected finish to move. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | delay | DELAYED | 60 |  |  | crane unavailable | complete inspection | FALSE | 0.921 | English | train
UPD-01641 | excel_note | document | 2026-09-04 | OIL-UNIT2-DEMO | HSE-001-001 ¦ Complete work-at-height inspection ¦ NOT STARTED ¦ NA FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.961 | English | train
UPD-01059 | plain_text | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Crew resumed Erect Line 24 after clearance. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | resumption | RESUMED | 70 | 2026-09-03 |  |  | update schedule | FALSE | 0.924 | English | train
UPD-00322 | word_document | mobile | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-22 Discipline: Piping Observation: Hydrotest Line 23 is delayed because of equipment breakdown. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | equipment breakdown | complete inspection | FALSE | 0.901 | English | train
UPD-00616 | ms_project_update | email | 2026-09-25 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L30-001 status = RESUMED. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 70 | 2026-09-25 |  |  | planner review | FALSE | 0.939 | English | train
UPD-00370 | email | email | 2026-09-05 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-F15-002 Dear Team, Around 50% work comp. on Foundation F15 reinforcement; balance is ongoing. Regards, Site Supervisor | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-05 |  |  | obtain permit | FALSE | 0.923 | English | train
UPD-01674 | voice_transcript | DPR | 2026-09-20 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that crew is currently working on erect line 24. Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-20 |  |  | planner review | FALSE | 0.962 | English | train
UPD-01215 | email | DPR | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-C01-001 Dear Team, Install Compressor C01 commenced at Compressor Area. Regards, Site Supervisor Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 80 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.969 | English | train
UPD-01684 | pdf_text | email | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 is complete as of today. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | obtain permit | FALSE | 0.953 | English | train
UPD-00857 | excel_note | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Daily Progress: PIP-L23-003 ¦ Hydrotest Line 23 ¦ CANCELLED ¦ NA Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.936 | English | train
UPD-01170 | ms_project_update | DPR | 2026-09-15 | OIL-UNIT2-DEMO | MS Project note: MEC-HX01-001 progress affected by scaffold not ready; expected finish to move. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | scaffold not ready | obtain permit | FALSE | 0.97 | English | train
UPD-00946 | plain_text | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Install 30-inch header done at site. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | continue work | FALSE | 0.952 | English | train
UPD-00347 | ms_project_update | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: HSE-001-001 status = IN PROGRESS. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.917 | English | train
UPD-00385 | email | DPR | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-F15-003 Dear Team, Foundation F15 concreting started today. Regards, Site Supervisor Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 40 | 2026-09-30 |  |  | receive material | FALSE | 0.905 | English | train
UPD-00433 | word_document | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-14 Discipline: Mechanical Observation: Crew mobilised and started Install Heat Exchanger HX01. Material expected tomorrow. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 70 | 2026-09-14 |  |  | continue work | FALSE | 0.958 | English | train
UPD-01443 | excel_note | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: PIP-L24-003 ¦ Hydrotest Line 24 ¦ COMPLETED ¦ NA FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | complete inspection | FALSE | 0.96 | English | train
UPD-00245 | whatsapp | document | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: Line/area update: foundation f15 reinforcement completed today. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | mobilise crew | FALSE | 0.935 | English | train
UPD-01590 | site_diary | document | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-11 ¦ Unit 2 ¦ Lay Cable Route 7 partially completed today. Planner action required. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.949 | English | train
UPD-01480 | email | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Work on Road R02 subgrade preparation restarted today. Regards, Site Supervisor Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 50 | 2026-09-15 |  |  | continue work | FALSE | 0.957 | English | train
UPD-01620 | email | email | 2026-09-02 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - ELE-TR02-001 Dear Team, Install Transformer TR02 kicked off today. Regards, Site Supervisor Please note. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 80 | 2026-09-02 |  |  | receive material | FALSE | 0.921 | English | train
UPD-00246 | pdf_text | spreadsheet | 2026-09-05 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ CIV-R02-001 ¦ Road R02 subgrade preparation cancelled for today. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.941 | English | train
UPD-00185 | voice_transcript | email | 2026-09-28 | OIL-UNIT2-DEMO | Unit update: Uh, road r02 subgrade preparation has not started yet. Kindly update the plan. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.99 | English | train
UPD-01347 | excel_note | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: HSE-001-001 ¦ Complete work-at-height inspection ¦ PARTIAL ¦ NA For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-27 |  |  | complete inspection | FALSE | 0.987 | English | train
UPD-00976 | excel_note | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Supervisor update - PIP-L24-003 ¦ Hydrotest Line 24 ¦ COMPLETED ¦ NA FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | receive material | FALSE | 0.97 | English | train
UPD-01384 | email | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header could not proceed today due to drawing approval pending. Regards, Site Supervisor Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 80 |  |  | drawing approval pending | mobilise crew | FALSE | 0.925 | English | train
UPD-00749 | ms_project_update | DPR | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: PIP-L30-001 status = IN PROGRESS. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 10 | 2026-09-03 |  |  | receive material | FALSE | 0.901 | English | train
UPD-00942 | excel_note | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ CANCELLED ¦ NA | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.965 | English | train
UPD-00302 | site_diary | DPR | 2026-09-06 | OIL-UNIT2-DEMO | Today: Date 2026-09-06 ¦ Pump House ¦ Install Pump P03 complete today. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | planner review | FALSE | 0.901 | English | train
UPD-00658 | plain_text | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | Crew resumed Install Control Valve CV11 after clearance. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 70 | 2026-09-03 |  |  | complete inspection | FALSE | 0.983 | English | train
UPD-01499 | plain_text | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | Unit update: Install Heat Exchanger HX01 will not be executed today. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.926 | English | train
UPD-00102 | pdf_text | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 will not be executed today. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.981 | English | train
UPD-01627 | whatsapp | document | 2026-09-02 | OIL-UNIT2-DEMO | Daily Progress: Crew resumed Foundation F15 excavation after clearance. 👍 FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-02 |  |  | update schedule | FALSE | 0.96 | English | train
UPD-00221 | plain_text | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Foundation F15 reinforcement kicked off today. FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 20 | 2026-09-30 |  |  | obtain permit | FALSE | 0.976 | English | train
UPD-00233 | email | DPR | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - INS-JB05-001 Dear Team, Terminate Junction Box JB05 commenced at Unit 2. Regards, Site Supervisor For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 40 | 2026-09-15 |  |  | continue work | FALSE | 0.916 | English | train
UPD-01079 | ms_project_update | document | 2026-09-21 | OIL-UNIT2-DEMO | Today: MS Project update: ELE-LTG02-001 actual start = 2026-09-21; work commenced. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 60 | 2026-09-21 |  |  | update schedule | FALSE | 0.934 | English | train
UPD-00094 | excel_note | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: MEC-C01-001 ¦ Install Compressor C01 ¦ IN PROGRESS ¦ NA Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 20 | 2026-09-14 |  |  | planner review | FALSE | 0.908 | English | train
UPD-00491 | excel_note | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | Site Update: INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ BLOCKED ¦ design revision pending Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | complete inspection | FALSE | 0.952 | English | train
UPD-01648 | email | email | 2026-09-02 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - PIP-L23-001 Dear Team, Erect Line 23 has been completed at Unit 2. Regards, Site Supervisor Please note. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | complete inspection | FALSE | 0.98 | English | train
UPD-01157 | site_diary | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-10 ¦ Unit 1 ¦ Execution of Install 30-inch header is blocked by rainfall at site. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | rainfall at site | mobilise crew | FALSE | 0.958 | English | train
UPD-00040 | plain_text | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Install Transformer TR02 has not started yet. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.953 | English | train
UPD-00018 | plain_text | DPR | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Work on Install Unit 2 lighting restarted today. FYI. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | resumption | RESUMED | 30 | 2026-09-01 |  |  | receive material | FALSE | 0.972 | English | train
UPD-01429 | plain_text | mobile | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: Weld Line 24 started today. Material expected tomorrow. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 40 | 2026-09-01 |  |  | update schedule | FALSE | 0.961 | English | train
UPD-01085 | ms_project_update | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Progress note: MS Project update: ELE-MCC03-001 actual start = 2026-09-11; work commenced. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 20 | 2026-09-11 |  |  | continue work | FALSE | 0.973 | English | train
UPD-00204 | whatsapp | email | 2026-09-08 | OIL-UNIT2-DEMO | Today: Line/area update: work on close scaffold inspection actions was stopped because drawing approval pending. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 60 |  |  | drawing approval pending | obtain permit | FALSE | 0.94 | English | train
UPD-01656 | voice_transcript | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that complete work-at-height inspection is about 30% complete. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-19 |  |  | continue work | FALSE | 0.936 | English | train
UPD-01032 | site_diary | email | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-18 ¦ Unit 2 ¦ No start for Install Valve V12 today. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.965 | English | train
UPD-00530 | pdf_text | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ PIP-L23-003 ¦ Execution of Hydrotest Line 23 is blocked by late material inspection. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | continue work | FALSE | 0.94 | English | train
UPD-00596 | plain_text | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: Today's Install Tank T02 internals activity has been cancelled. Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.901 | English | train
UPD-01114 | voice_transcript | spreadsheet | 2026-09-05 | OIL-UNIT2-DEMO | DPR Update: Uh, complete work-at-height inspection started today. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | start | STARTED | 40 | 2026-09-05 |  |  | continue work | FALSE | 0.959 | English | train
UPD-01501 | site_diary | email | 2026-09-14 | OIL-UNIT2-DEMO | Date 2026-09-14 ¦ Plant Area ¦ Road R02 PCC laying done at site. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | obtain permit | FALSE | 0.961 | English | train
UPD-00540 | word_document | document | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-12 Discipline: Electrical Observation: Lay Cable Route 7 held up by design revision pending. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 70 |  |  | design revision pending | complete inspection | FALSE | 0.943 | English | train
UPD-00614 | ms_project_update | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: MEC-P04-001 status = CANCELLED. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.921 | English | train
UPD-01717 | word_document | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-14 Discipline: Electrical Observation: Lay Cable Route 7 has been complete at Unit 2. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | continue work | FALSE | 0.903 | English | train
UPD-01396 | site_diary | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Date 2026-09-28 ¦ Unit 2 ¦ Partial progress achieved on Weld Line 24. For information. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-28 |  |  | obtain permit | FALSE | 0.944 | English | train
UPD-01761 | excel_note | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Site Update: HSE-002-001 ¦ Close scaffold inspection actions ¦ CANCELLED ¦ NA Material expected tomorrow. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.901 | English | train
UPD-00682 | email | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - PIP-L24-003 Dear Team, No start for Hydrotest Line 24 today. Regards, Site Supervisor For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.927 | English | train
UPD-00286 | ms_project_update | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: MS Project note: ELE-LTG02-001 status = IN PROGRESS. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-25 |  |  | mobilise crew | FALSE | 0.984 | English | train
UPD-01370 | ms_project_update | mobile | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: MS Project note: MEC-P04-001 status = IN PROGRESS. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 80 | 2026-09-24 |  |  | update schedule | FALSE | 0.981 | English | train
UPD-00624 | voice_transcript | DPR | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: Uh, hydrotest line 24 is behind plan owing to inspection clearance pending. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 30 |  |  | inspection clearance pending | complete inspection | FALSE | 0.972 | English | train
UPD-00865 | excel_note | mobile | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: HSE-002-001 ¦ Close scaffold inspection actions ¦ NOT STARTED ¦ NA Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.961 | English | train
UPD-00822 | pdf_text | email | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ INS-T04-001 ¦ Install Temperature Transmitter T04 commenced at Unit 2. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 60 | 2026-09-19 |  |  | resume after clearance | FALSE | 0.987 | English | train
UPD-00714 | pdf_text | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ ELE-TR02-001 ¦ Install Transformer TR02 remains on hold due to safety clearance pending. Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | blockage | BLOCKED | 0 |  |  | safety clearance pending | receive material | FALSE | 0.919 | English | train
UPD-01748 | ms_project_update | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L23-002 status = NOT STARTED. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.911 | English | train
UPD-00416 | whatsapp | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Today: Line/area update: weld line 23 kicked off today. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 60 | 2026-09-03 |  |  | planner review | FALSE | 0.985 | English | train
UPD-00270 | ms_project_update | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Daily Progress: MS Project update: PIP-L30-001 Actual % Complete = 70% as of 2026-09-19. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 70 | 2026-09-19 |  |  | continue work | FALSE | 0.958 | English | train
UPD-00090 | email | document | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - PIP-L24-002 Dear Team, Work is continuing on Weld Line 24. Regards, Site Supervisor FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-08 |  |  | planner review | FALSE | 0.985 | English | train
UPD-01264 | email | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 will not be executed today. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.973 | English | train
UPD-00341 | voice_transcript | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Okay, today's update is that road r02 pcc laying commenced at plant area. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 10 | 2026-09-26 |  |  | mobilise crew | FALSE | 0.951 | English | train
UPD-01489 | pdf_text | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ ELE-TR02-001 ¦ Around 50% work completed on Install Transformer TR02; balance is ongoing. Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 40 | 2026-09-18 |  |  | planner review | FALSE | 0.921 | English | train
UPD-00197 | voice_transcript | email | 2026-09-28 | OIL-UNIT2-DEMO | So, basically, weld line 24 partially done today. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-28 |  |  | planner review | FALSE | 0.943 | English | train
UPD-01452 | word_document | document | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-25 Discipline: Mechanical Observation: Install Pump P03 is behind plan owing to drawing approval pending. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 20 |  |  | drawing approval pending | planner review | FALSE | 0.987 | English | train
UPD-01227 | site_diary | mobile | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-01 ¦ Unit 2 ¦ Complete work-at-height inspection remains not started. Kindly update the plan. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.922 | English | train
UPD-00342 | site_diary | DPR | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-20 ¦ Tank Farm ¦ Execution of Tank T01 foundation completion is blocked by power supply interruption. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | power supply interruption | continue work | FALSE | 0.964 | English | train
UPD-01795 | excel_note | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ PARTIAL ¦ NA FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 10 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.953 | English | train
UPD-01275 | ms_project_update | document | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: MS Project note: INS-PT08-001 progress affected by access road blocked; expected finish to move. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | access road blocked | mobilise crew | FALSE | 0.962 | English | train
UPD-00171 | plain_text | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Planned work Install Pump P03 did not commence. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.967 | English | train
UPD-01113 | word_document | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-12 Discipline: HSE Observation: Close scaffold inspection actions is blocked pending design revision pending. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | design revision pending | resume after clearance | FALSE | 0.906 | English | train
UPD-01548 | voice_transcript | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Okay, today's update is that install compressor c01 remains on hold due to vendor technician not available. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | vendor technician not available | mobilise crew | FALSE | 0.912 | English | train
UPD-00084 | pdf_text | email | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ ELE-MCC03-001 ¦ Supervisor confirms Install MCC Panel 3 completed. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | receive material | FALSE | 0.958 | English | train
UPD-00442 | voice_transcript | spreadsheet | 2026-09-16 | OIL-UNIT2-DEMO | Today: Uh, weld line 24 could not proceed today due to insufficient manpower. FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | insufficient manpower | continue work | FALSE | 0.969 | English | train
UPD-01122 | pdf_text | mobile | 2026-09-06 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ HSE-002-001 ¦ Close scaffold inspection actions remains not started. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.975 | English | train
UPD-00128 | voice_transcript | email | 2026-09-17 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that install tank t02 internals has resumed following resolution of the earlier issue. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | resumption | RESUMED | 30 | 2026-09-17 |  |  | mobilise crew | FALSE | 0.903 | English | train
UPD-01268 | voice_transcript | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: So, basically, work on install 30-inch header has begun. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 10 | 2026-09-16 |  |  | planner review | FALSE | 0.988 | English | train
UPD-01156 | plain_text | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Today: Install Unit 2 lighting held up by QA/QC hold point not cleared. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 10 |  |  | QA/QC hold point not cleared | continue work | FALSE | 0.906 | English | train
UPD-00076 | pdf_text | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ ELE-TR02-001 ¦ Work for Install Transformer TR02 is finished. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | update schedule | FALSE | 0.915 | English | train
UPD-00123 | site_diary | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-07 ¦ Plant Area ¦ Road R02 subgrade preparation cancelled for today. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.976 | English | train
UPD-00636 | plain_text | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Install MCC Panel 3 has resumed following resolution of the earlier issue. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 40 | 2026-09-02 |  |  | complete inspection | FALSE | 0.901 | English | train
UPD-01005 | excel_note | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - INS-T04-001 ¦ Install Temperature Transmitter T04 ¦ CANCELLED ¦ NA Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.986 | English | train
UPD-00138 | ms_project_update | document | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: MS Project update: MEC-P03-001 actual start = 2026-09-08; work commenced. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 50 | 2026-09-08 |  |  | obtain permit | FALSE | 0.981 | English | train
UPD-00886 | email | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L23-001 Dear Team, Erect Line 23 has been completed at Unit 2. Regards, Site Supervisor FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | receive material | FALSE | 0.928 | English | train
UPD-01269 | word_document | mobile | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-11 Discipline: Civil Observation: Work on Foundation F15 reinforcement has begun. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 70 | 2026-09-11 |  |  | obtain permit | FALSE | 0.963 | English | train
UPD-01740 | voice_transcript | DPR | 2026-09-24 | OIL-UNIT2-DEMO | Today: Uh, work on weld line 23 has begun. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-24 |  |  | planner review | FALSE | 0.989 | English | train
UPD-01013 | site_diary | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-22 ¦ Unit 2 ¦ Work on Erect Line 23 restarted today. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | resumption | RESUMED | 80 | 2026-09-22 |  |  | planner review | FALSE | 0.97 | English | train
UPD-01752 | email | email | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - MEC-P03-001 Dear Team, Crew mobilised and started Install Pump P03. Regards, Site Supervisor Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 30 | 2026-09-02 |  |  | update schedule | FALSE | 0.912 | English | train
UPD-01635 | plain_text | mobile | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Foundation F15 excavation will not be executed today. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.931 | English | train
UPD-00440 | excel_note | document | 2026-09-01 | OIL-UNIT2-DEMO | Today: PIP-L23-002 ¦ Weld Line 23 ¦ STARTED ¦ NA For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-01 |  |  | receive material | FALSE | 0.988 | English | train
UPD-00945 | whatsapp | DPR | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Work for Install Temperature Transmitter T04 is finished. 👍 Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | mobilise crew | FALSE | 0.99 | English | train
UPD-01360 | plain_text | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: Foundation F15 reinforcement is blocked pending drawing approval pending. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | drawing approval pending | planner review | FALSE | 0.93 | English | train
UPD-00589 | word_document | email | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-01 Discipline: Piping Observation: Only part of Weld Line 24 could be completed today. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-01 |  |  | complete inspection | FALSE | 0.939 | English | train
UPD-00527 | ms_project_update | DPR | 2026-09-25 | OIL-UNIT2-DEMO | MS Project note: INS-JB05-001 progress affected by safety clearance pending; expected finish to move. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 60 |  |  | safety clearance pending | mobilise crew | FALSE | 0.932 | English | train
UPD-01530 | ms_project_update | DPR | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-001 status = CANCELLED. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.98 | English | train
UPD-01254 | ms_project_update | DPR | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-001 progress affected by scaffold not ready; expected finish to move. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | delay | DELAYED | 10 |  |  | scaffold not ready | complete inspection | FALSE | 0.975 | English | train
UPD-00293 | word_document | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-15 Discipline: Mechanical Observation: Install Pump P03 could not proceed today due to late material inspection. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 70 |  |  | late material inspection | resume after clearance | FALSE | 0.916 | English | train
UPD-00848 | email | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 partially completed today. Regards, Site Supervisor Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 50 | 2026-09-28 |  |  | mobilise crew | FALSE | 0.938 | English | train
UPD-01318 | email | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header is complete as of today. Regards, Site Supervisor | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | resume after clearance | FALSE | 0.901 | English | train
UPD-01106 | voice_transcript | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Unit update: Just to update you, install 30-inch header started today. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 20 | 2026-09-25 |  |  | receive material | FALSE | 0.937 | English | train
UPD-01247 | ms_project_update | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: MS Project update: ELE-TR02-001 Actual % Complete = 50% as of 2026-09-29. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 50 | 2026-09-29 |  |  | resume after clearance | FALSE | 0.943 | English | train
UPD-01788 | ms_project_update | email | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: MS Project note: HSE-002-001 status = RESUMED. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 20 | 2026-09-30 |  |  | receive material | FALSE | 0.933 | English | train
UPD-00239 | voice_transcript | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - Uh, install compressor c01 started today. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 80 | 2026-09-01 |  |  | mobilise crew | FALSE | 0.962 | English | train
UPD-01214 | email | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - ELE-TR02-001 Dear Team, Work on Install Transformer TR02 restarted today. Regards, Site Supervisor Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 40 | 2026-09-16 |  |  | receive material | FALSE | 0.934 | English | train
UPD-00839 | word_document | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-22 Discipline: Piping Observation: Crew is currently working on Install 30-inch header. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 40 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.936 | English | train
UPD-00838 | whatsapp | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: Line/area update: crew mobilised and started install 30-inch header. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 60 | 2026-09-11 |  |  | update schedule | FALSE | 0.985 | English | train
UPD-00489 | word_document | mobile | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-17 Discipline: Mechanical Observation: Install Pump P03 progressing as planned. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-17 |  |  | update schedule | FALSE | 0.989 | English | train
UPD-00009 | plain_text | document | 2026-09-06 | OIL-UNIT2-DEMO | Daily Progress: Tank T01 foundation completion resumed today after shortage of 24-inch pipes was cleared. Material expected tomorrow. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 20 | 2026-09-06 |  |  | obtain permit | FALSE | 0.908 | English | train
UPD-00843 | word_document | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-12 Discipline: Civil Observation: Tank T01 foundation completion has resumed following resolution of the earlier issue. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 20 | 2026-09-12 |  |  | obtain permit | FALSE | 0.942 | English | train
UPD-00227 | site_diary | document | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-16 ¦ Electrical Room ¦ Install MCC Panel 3 remains not started. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.961 | English | train
UPD-01316 | excel_note | DPR | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ COMPLETED ¦ NA Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | continue work | FALSE | 0.976 | English | train
UPD-01758 | voice_transcript | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Okay, today's update is that install heat exchanger hx01 held up by scaffold not ready. Material expected tomorrow. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | delay | DELAYED | 20 |  |  | scaffold not ready | continue work | FALSE | 0.935 | English | train
UPD-01093 | ms_project_update | email | 2026-09-29 | OIL-UNIT2-DEMO | MS Project update: CIV-TK01-001 marked 100% complete. Actual Finish: 2026-09-29. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | planner review | FALSE | 0.901 | English | train
UPD-01125 | plain_text | spreadsheet | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: No start for Close scaffold inspection actions today. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.961 | English | train
UPD-01385 | email | email | 2026-09-20 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L23-003 Dear Team, Hydrotest Line 23 remains not started. Regards, Site Supervisor | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.909 | English | train
UPD-01763 | email | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - INS-CV11-001 Dear Team, Planned work Install Control Valve CV11 did not commence. Regards, Site Supervisor Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.923 | English | train
UPD-01296 | site_diary | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-07 ¦ Unit 2 ¦ Terminate Junction Box JB05 commenced at Unit 2. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 40 | 2026-09-07 |  |  | receive material | FALSE | 0.948 | English | train
UPD-01417 | whatsapp | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: Line/area update: hydrotest line 23 will not be executed today. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.945 | English | train
UPD-00726 | word_document | document | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-29 Discipline: Electrical Observation: Execution of Install MCC Panel 3 is blocked by rainfall at site. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | blockage | BLOCKED | 0 |  |  | rainfall at site | continue work | FALSE | 0.96 | English | train
UPD-01229 | email | DPR | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Work on Install Unit 2 lighting restarted today. Regards, Site Supervisor Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | resumption | RESUMED | 30 | 2026-09-28 |  |  | obtain permit | FALSE | 0.944 | English | train
UPD-00420 | pdf_text | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ ELE-LTG02-001 ¦ Crew is currently working on Install Unit 2 lighting. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-27 |  |  | mobilise crew | FALSE | 0.989 | English | train
UPD-01241 | pdf_text | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ CIV-R02-002 ¦ Road R02 PCC laying is about 40% complete. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 40 | 2026-09-09 |  |  | receive material | FALSE | 0.904 | English | train
UPD-01447 | site_diary | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-16 ¦ Unit 2 ¦ Weld Line 23 ongoing at Unit 2. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-16 |  |  | resume after clearance | FALSE | 0.983 | English | train
UPD-00938 | site_diary | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-29 ¦ Unit 2 ¦ Work on Erect Line 24 has begun. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 40 | 2026-09-29 |  |  | obtain permit | FALSE | 0.931 | English | train
UPD-00383 | ms_project_update | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: MS Project note: INS-JB05-001 status = IN PROGRESS. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-12 |  |  | resume after clearance | FALSE | 0.946 | English | train
UPD-01757 | whatsapp | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Line/area update: work is continuing on hydrotest line 23. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-07 |  |  | continue work | FALSE | 0.903 | English | train
UPD-00994 | email | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - CIV-TK01-001 Dear Team, Tank T01 foundation completion will not be executed today. Regards, Site Supervisor Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.925 | English | train
UPD-00263 | excel_note | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Progress note: CIV-F15-003 ¦ Foundation F15 concreting ¦ PARTIAL ¦ NA Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-07 |  |  | mobilise crew | FALSE | 0.909 | English | train
UPD-00462 | email | document | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation resumed today after safety clearance pending was cleared. Regards, Site Supervisor Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 30 | 2026-09-24 |  |  | receive material | FALSE | 0.959 | English | train
UPD-00473 | plain_text | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - Erect Line 23 is behind plan owing to welding machine under maintenance. Please note. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | welding machine under maintenance | mobilise crew | FALSE | 0.91 | English | train
UPD-01408 | pdf_text | email | 2026-09-03 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 is about 70% complete. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 70 | 2026-09-03 |  |  | complete inspection | FALSE | 0.958 | English | train
UPD-00680 | voice_transcript | document | 2026-09-27 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, no progress on close scaffold inspection actions today due to vendor technician not available. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 70 |  |  | vendor technician not available | mobilise crew | FALSE | 0.93 | English | train
UPD-01794 | pdf_text | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ CIV-R02-001 ¦ Road R02 subgrade preparation started today. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 10 | 2026-09-01 |  |  | continue work | FALSE | 0.954 | English | train
UPD-00746 | word_document | site_diary | 2026-09-03 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-03 Discipline: Electrical Observation: Install Transformer TR02 is about 20% complete. Please note. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 20 | 2026-09-03 |  |  | update schedule | FALSE | 0.963 | English | train
UPD-00353 | email | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Started Install Unit 2 lighting this morning. Regards, Site Supervisor | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 60 | 2026-09-11 |  |  | planner review | FALSE | 0.901 | English | train
UPD-01520 | word_document | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-25 Discipline: Piping Observation: Erect Line 23 will not be executed today. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.906 | English | train
UPD-01660 | voice_transcript | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Unit update: Uh, partial progress achieved on road r02 subgrade preparation. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 25 | 2026-09-30 |  |  | receive material | FALSE | 0.962 | English | train
UPD-00055 | plain_text | email | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: Execution of Lay Cable Route 7 is blocked by QA/QC hold point not cleared. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | mobilise crew | FALSE | 0.906 | English | train
UPD-00656 | site_diary | document | 2026-09-12 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-12 ¦ Compressor Area ¦ Install Compressor C01 cancelled for today. Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.973 | English | train
UPD-01095 | email | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-V12-001 Dear Team, Install Valve V12 is blocked pending work permit not issued. Regards, Site Supervisor Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | complete inspection | FALSE | 0.942 | English | train
UPD-00375 | plain_text | mobile | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Tank T01 foundation completion has been completed at Tank Farm. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | continue work | FALSE | 0.973 | English | train
UPD-00594 | voice_transcript | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Uh, crew is currently working on install tank t02 internals. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | progress | IN_PROGRESS | 20 | 2026-09-21 |  |  | obtain permit | FALSE | 0.916 | English | train
UPD-00687 | plain_text | MS_Project | 2026-09-26 | OIL-UNIT2-DEMO | Daily Progress: Weld Line 23 remains not started. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.928 | English | train
UPD-01576 | ms_project_update | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: MS Project note: INS-JB05-001 progress affected by welding machine under maintenance; expected finish to move. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | welding machine under maintenance | mobilise crew | FALSE | 0.982 | English | train
UPD-00582 | site_diary | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-10 ¦ Unit 2 ¦ Supervisor confirms Complete work-at-height inspection completed. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | resume after clearance | FALSE | 0.941 | English | train
UPD-01354 | excel_note | mobile | 2026-09-06 | OIL-UNIT2-DEMO | Unit update: ELE-CBL07-001 ¦ Lay Cable Route 7 ¦ CANCELLED ¦ NA Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.96 | English | train
UPD-01738 | voice_transcript | document | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that lay cable route 7 is about 75% complete. FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-18 |  |  | planner review | FALSE | 0.989 | English | train
UPD-01333 | plain_text | document | 2026-09-11 | OIL-UNIT2-DEMO | Work on Install Temperature Transmitter T04 restarted today. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 50 | 2026-09-11 |  |  | receive material | FALSE | 0.911 | English | train
UPD-01477 | ms_project_update | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: CIV-F15-003 status = IN PROGRESS. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-11 |  |  | obtain permit | FALSE | 0.928 | English | train
UPD-01436 | excel_note | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: MEC-C01-001 ¦ Install Compressor C01 ¦ RESUMED ¦ NA For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 70 | 2026-09-06 |  |  | planner review | FALSE | 0.949 | English | train
UPD-00441 | pdf_text | mobile | 2026-09-05 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ MEC-C01-001 ¦ Install Compressor C01 has been completed at Compressor Area. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | receive material | FALSE | 0.905 | English | train
UPD-00835 | word_document | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-29 Discipline: Electrical Observation: Install MCC Panel 3 resumed today after design revision pending was cleared. For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 80 | 2026-09-29 |  |  | mobilise crew | FALSE | 0.955 | English | train
UPD-00571 | voice_transcript | email | 2026-09-05 | OIL-UNIT2-DEMO | Today: Okay, today's update is that foundation f15 reinforcement ongoing at unit 2. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-05 |  |  | complete inspection | FALSE | 0.924 | English | train
UPD-01705 | whatsapp | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | Install MCC Panel 3 has resumed following resolution of the earlier issue. 👍 Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 40 | 2026-09-02 |  |  | obtain permit | FALSE | 0.912 | English | train
UPD-01001 | pdf_text | DPR | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ PIP-L24-001 ¦ Erect Line 24 remains not started. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.901 | English | train
UPD-01730 | pdf_text | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ PIP-V12-001 ¦ Install Valve V12 will not be executed today. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.925 | English | train
UPD-01397 | excel_note | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: CIV-R02-002 ¦ Road R02 PCC laying ¦ BLOCKED ¦ valve not available at site For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | valve not available at site | update schedule | FALSE | 0.906 | English | train
UPD-00598 | email | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - CIV-F15-001 Dear Team, Crew is currently working on Foundation F15 excavation. Regards, Site Supervisor Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-18 |  |  | update schedule | FALSE | 0.957 | English | train
UPD-00517 | site_diary | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-30 ¦ Electrical Room ¦ Install MCC Panel 3 resumed today after access road blocked was cleared. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 70 | 2026-09-30 |  |  | obtain permit | FALSE | 0.955 | English | train
UPD-00678 | email | document | 2026-09-19 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - HSE-001-001 Dear Team, Cannot continue Complete work-at-height inspection until late material inspection is resolved. Regards, Site Supervisor Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | mobilise crew | FALSE | 0.955 | English | train
UPD-00465 | ms_project_update | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: MS Project update: PIP-L23-001 Actual % Complete = 80% as of 2026-09-05. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-05 |  |  | planner review | FALSE | 0.932 | English | train
UPD-00834 | word_document | MS_Project | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-04 Discipline: Piping Observation: Install 30-inch header could not proceed today due to rainfall at site. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 80 |  |  | rainfall at site | planner review | FALSE | 0.905 | English | train
UPD-00425 | pdf_text | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 14-09-2026 ¦ MEC-C01-001 ¦ No progress on Install Compressor C01 today due to equipment breakdown. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 80 |  |  | equipment breakdown | resume after clearance | FALSE | 0.909 | English | train
UPD-00085 | excel_note | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ PARTIAL ¦ NA For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | partial_progress | PARTIAL | 60 | 2026-09-30 |  |  | planner review | FALSE | 0.911 | English | train
UPD-01476 | excel_note | document | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - CIV-F15-001 ¦ Foundation F15 excavation ¦ CANCELLED ¦ NA Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.951 | English | train
UPD-01557 | site_diary | email | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-04 ¦ Unit 2 ¦ Execution of Lay Cable Route 7 is blocked by safety clearance pending. Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | receive material | FALSE | 0.929 | English | train
UPD-00903 | email | MS_Project | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Crew mobilised and started Install MCC Panel 3. Regards, Site Supervisor Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 70 | 2026-09-04 |  |  | update schedule | FALSE | 0.961 | English | train
UPD-01407 | email | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation completed today. Regards, Site Supervisor | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | resume after clearance | FALSE | 0.976 | English | train
UPD-01427 | ms_project_update | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: MS Project note: HSE-001-001 status = NOT STARTED. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.915 | English | train
UPD-00099 | voice_transcript | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: So, basically, foundation f15 excavation is in progress. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-05 |  |  | complete inspection | FALSE | 0.978 | English | train
UPD-01320 | pdf_text | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ INS-T04-001 ¦ Install Temperature Transmitter T04 has resumed following resolution of the earlier issue. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 50 | 2026-09-28 |  |  | planner review | FALSE | 0.964 | English | train
UPD-00189 | email | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 is complete as of today. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | resume after clearance | FALSE | 0.956 | English | train
UPD-01313 | plain_text | document | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: Road R02 subgrade preparation held up by power supply interruption. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 30 |  |  | power supply interruption | receive material | FALSE | 0.962 | English | train
UPD-01419 | voice_transcript | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: Okay, today's update is that install mcc panel 3 is complete as of today. For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | resume after clearance | FALSE | 0.914 | English | train
UPD-00887 | word_document | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-17 Discipline: Mechanical Observation: Crew resumed Install Heat Exchanger HX01 after clearance. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 10 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.933 | English | train
UPD-00939 | voice_transcript | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: Uh, partial progress achieved on install pump p03. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 50 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.94 | English | train
UPD-00964 | excel_note | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: PIP-V12-001 ¦ Install Valve V12 ¦ PARTIAL ¦ NA Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-13 |  |  | obtain permit | FALSE | 0.95 | English | train
UPD-01159 | ms_project_update | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: HSE-001-001 status = NOT STARTED. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.959 | English | train
UPD-00734 | pdf_text | spreadsheet | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 is about 80% complete. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-11 |  |  | receive material | FALSE | 0.923 | English | train
UPD-01351 | plain_text | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Only part of Complete work-at-height inspection could be completed today. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-11 |  |  | planner review | FALSE | 0.921 | English | train
UPD-01291 | whatsapp | email | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Hi, install pressure transmitter pt08 kicked off today. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | start | STARTED | 10 | 2026-09-30 |  |  | update schedule | FALSE | 0.908 | English | train
UPD-00443 | excel_note | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | PIP-L23-003 ¦ Hydrotest Line 23 ¦ CANCELLED ¦ NA FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.971 | English | train
UPD-00812 | whatsapp | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Sir, today's hydrotest line 24 activity has been cancelled. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.91 | English | train
UPD-00850 | site_diary | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-04 ¦ Unit 2 ¦ Complete work-at-height inspection has been completed at Unit 2. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-04 | 2026-09-04 |  | continue work | FALSE | 0.979 | English | train
UPD-00240 | whatsapp | DPR | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Line/area update: erect line 23 is delayed because of scaffold not ready. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | scaffold not ready | update schedule | FALSE | 0.95 | English | train
UPD-01753 | email | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - INS-T04-001 Dear Team, No progress on Install Temperature Transmitter T04 today due to design revision pending. Regards, Site Supervisor Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 20 |  |  | design revision pending | planner review | FALSE | 0.914 | English | train
UPD-01542 | pdf_text | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ INS-JB05-001 ¦ Cannot continue Terminate Junction Box JB05 until power supply interruption is resolved. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | planner review | FALSE | 0.959 | English | train
UPD-00565 | email | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - INS-T04-001 Dear Team, No start for Install Temperature Transmitter T04 today. Regards, Site Supervisor Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.936 | English | train
UPD-01792 | pdf_text | email | 2026-09-20 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ PIP-L30-001 ¦ Install 30-inch header has resumed following resolution of the earlier issue. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 80 | 2026-09-20 |  |  | obtain permit | FALSE | 0.948 | English | train
UPD-01564 | pdf_text | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ CIV-R02-002 ¦ Road R02 PCC laying resumed today after inspection clearance pending was cleared. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 70 | 2026-09-12 |  |  | obtain permit | FALSE | 0.944 | English | train
UPD-00259 | voice_transcript | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: Uh, install temperature transmitter t04 started today. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 60 | 2026-09-29 |  |  | complete inspection | FALSE | 0.901 | English | train
UPD-01776 | email | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Work on Install MCC Panel 3 restarted today. Regards, Site Supervisor | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 30 | 2026-09-26 |  |  | obtain permit | FALSE | 0.923 | English | train
UPD-00081 | word_document | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-29 Discipline: Piping Observation: Install 30-inch header completed today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | obtain permit | FALSE | 0.924 | English | train
UPD-01487 | plain_text | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | DPR Update: Road R02 PCC laying is blocked pending power supply interruption. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | power supply interruption | mobilise crew | FALSE | 0.922 | English | train
UPD-00203 | word_document | email | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-19 Discipline: Piping Observation: Only part of Erect Line 23 could be completed today. Please note. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-19 |  |  | receive material | FALSE | 0.92 | English | train
UPD-01679 | site_diary | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Date 2026-09-15 ¦ Unit 2 ¦ Supervisor confirms Terminate Junction Box JB05 complete. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | obtain permit | FALSE | 0.969 | English | train
UPD-00043 | plain_text | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Only part of Complete work-at-height inspection could be completed today. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | planner review | FALSE | 0.939 | English | train
UPD-00712 | voice_transcript | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: So, basically, hydrotest line 24 done at site. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | mobilise crew | FALSE | 0.926 | English | train
UPD-01512 | pdf_text | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ PIP-V12-001 ¦ No start for Install Valve V12 today. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.954 | English | train
UPD-01638 | word_document | document | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-27 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 is in progress. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.908 | English | train
UPD-00655 | email | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting ongoing at Unit 2. Regards, Site Supervisor Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-13 |  |  | planner review | FALSE | 0.925 | English | train
UPD-01741 | excel_note | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - PIP-L23-003 ¦ Hydrotest Line 23 ¦ IN PROGRESS ¦ NA For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-23 |  |  | receive material | FALSE | 0.924 | English | train
UPD-00745 | pdf_text | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 17-09-2026 ¦ INS-PT08-001 ¦ No start for Install Pressure Transmitter PT08 today. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.958 | English | train
UPD-00062 | plain_text | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | DPR Update: Today's Align Pump P04 activity has been cancelled. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.944 | English | train
UPD-01230 | plain_text | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Road R02 PCC laying is behind plan owing to safety clearance pending. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | delay | DELAYED | 60 |  |  | safety clearance pending | resume after clearance | FALSE | 0.913 | English | train
UPD-00846 | whatsapp | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: Line/area update: planned work install tank t02 internals did not commence. FYI. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.98 | English | train
UPD-01690 | plain_text | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Hydrotest Line 23 has resumed following resolution of the earlier issue. Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 10 | 2026-09-15 |  |  | update schedule | FALSE | 0.968 | English | train
UPD-01799 | plain_text | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Install Unit 2 lighting ongoing at Unit 2. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-18 |  |  | resume after clearance | FALSE | 0.93 | English | train
UPD-01341 | pdf_text | site_diary | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ CIV-F15-001 ¦ Cannot continue Foundation F15 excavation until work permit not issued is resolved. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | update schedule | FALSE | 0.959 | English | train
UPD-01561 | word_document | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-12 Discipline: Piping Observation: Work on Hydrotest Line 23 was stopped because access road blocked. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 10 |  |  | access road blocked | receive material | FALSE | 0.933 | English | train
UPD-01724 | word_document | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-17 Discipline: Piping Observation: Erect Line 24 is behind plan owing to scaffold not ready. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | scaffold not ready | update schedule | FALSE | 0.91 | English | train
UPD-00137 | site_diary | email | 2026-09-21 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-21 ¦ Unit 2 ¦ Hydrotest Line 24 remains not started. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.903 | English | train
UPD-01327 | plain_text | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Road R02 subgrade preparation could not proceed today due to shortage of 24-inch pipes. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 20 |  |  | shortage of 24-inch pipes | update schedule | FALSE | 0.902 | English | train
UPD-01533 | ms_project_update | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Today: MS Project update: INS-T04-001 actual start = 2026-09-17; work commenced. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-17 |  |  | update schedule | FALSE | 0.946 | English | train
UPD-01325 | plain_text | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Today: Planned work Install Pressure Transmitter PT08 did not commence. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.959 | English | train
UPD-00584 | email | DPR | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-TK01-001 Dear Team, Tank T01 foundation completion held up by QA/QC hold point not cleared. Regards, Site Supervisor For information. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 70 |  |  | QA/QC hold point not cleared | planner review | FALSE | 0.951 | English | train
UPD-00968 | excel_note | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: CIV-F15-001 ¦ Foundation F15 excavation ¦ PARTIAL ¦ NA For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-08 |  |  | continue work | FALSE | 0.975 | English | train
UPD-00771 | voice_transcript | DPR | 2026-09-26 | OIL-UNIT2-DEMO | So, basically, install valve v12 done at site. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | continue work | FALSE | 0.986 | English | train
UPD-00641 | word_document | document | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-11 Discipline: Civil Observation: Road R02 PCC laying will not be executed today. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.944 | English | train
UPD-00987 | site_diary | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-19 ¦ Plant Area ¦ Road R02 PCC laying cancelled for today. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.922 | English | train
UPD-00551 | site_diary | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-07 ¦ Unit 1 ¦ Work on Close scaffold inspection actions restarted today. Material expected tomorrow. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 40 | 2026-09-07 |  |  | resume after clearance | FALSE | 0.938 | English | train
UPD-00376 | plain_text | email | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: Today's Erect Line 23 activity has been cancelled. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.91 | English | train
UPD-01015 | word_document | document | 2026-09-09 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-09 Discipline: Instrumentation Observation: Terminate Junction Box JB05 commenced at Unit 2. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | start | STARTED | 40 | 2026-09-09 |  |  | continue work | FALSE | 0.902 | English | train
UPD-01405 | whatsapp | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | Progress note: Sir, foundation f15 excavation is complete as of today. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | complete inspection | FALSE | 0.93 | English | train
UPD-00974 | voice_transcript | document | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - Uh, foundation f15 concreting remains on hold due to power supply interruption. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | complete inspection | FALSE | 0.933 | English | train
UPD-00953 | word_document | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-19 Discipline: Piping Observation: No progress on Install Valve V12 today due to equipment breakdown. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | delay | DELAYED | 30 |  |  | equipment breakdown | planner review | FALSE | 0.942 | English | train
UPD-01756 | plain_text | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Install Pressure Transmitter PT08 remains not started. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.956 | English | train
UPD-00398 | pdf_text | document | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ HSE-002-001 ¦ Close scaffold inspection actions is complete as of today. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | complete inspection | FALSE | 0.904 | English | train
UPD-00186 | voice_transcript | email | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Uh, install pump p03 held up by design revision pending. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 70 |  |  | design revision pending | receive material | FALSE | 0.967 | English | train
UPD-00001 | ms_project_update | DPR | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L30-001 progress affected by inspection clearance pending; expected finish to move. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | mobilise crew | FALSE | 0.958 | English | train
UPD-01553 | excel_note | mobile | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ NOT STARTED ¦ NA Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.909 | English | train
UPD-00312 | ms_project_update | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: MS Project update: CIV-F15-003 Actual % Complete = 80% as of 2026-09-11. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-11 |  |  | complete inspection | FALSE | 0.93 | English | train
UPD-01426 | excel_note | document | 2026-09-10 | OIL-UNIT2-DEMO | Supervisor update - MEC-P03-001 ¦ Install Pump P03 ¦ STARTED ¦ NA Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 40 | 2026-09-10 |  |  | mobilise crew | FALSE | 0.918 | English | train
UPD-00254 | site_diary | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Date 2026-09-12 ¦ Unit 2 ¦ Install Control Valve CV11 has resumed following resolution of the earlier issue. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 60 | 2026-09-12 |  |  | planner review | FALSE | 0.904 | English | train
UPD-01191 | ms_project_update | document | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: MS Project update: MEC-P03-001 marked 100% complete. Actual Finish: 2026-09-02. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | resume after clearance | FALSE | 0.914 | English | train
UPD-01449 | excel_note | spreadsheet | 2026-09-01 | OIL-UNIT2-DEMO | MEC-P03-001 ¦ Install Pump P03 ¦ NOT STARTED ¦ NA Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.988 | English | train
UPD-00870 | word_document | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-04 Discipline: Electrical Observation: Install Unit 2 lighting partially completed today. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-04 |  |  | planner review | FALSE | 0.915 | English | train
UPD-00249 | plain_text | mobile | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Install Temperature Transmitter T04 kicked off today. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-15 |  |  | resume after clearance | FALSE | 0.941 | English | train
UPD-01196 | ms_project_update | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | Today: MS Project update: MEC-T02-001 Actual % Complete = 90% as of 2026-09-05. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 90 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.948 | English | train
UPD-00036 | pdf_text | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ INS-PT08-001 ¦ Install Pressure Transmitter PT08 has been completed at Unit 1. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | complete inspection | FALSE | 0.969 | English | train
UPD-00035 | excel_note | DPR | 2026-09-29 | OIL-UNIT2-DEMO | CIV-R02-001 ¦ Road R02 subgrade preparation ¦ COMPLETED ¦ NA For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | continue work | FALSE | 0.941 | English | train
UPD-00910 | site_diary | mobile | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-21 ¦ Unit 2 ¦ Work is continuing on Foundation F15 excavation. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-21 |  |  | complete inspection | FALSE | 0.92 | English | train
UPD-00365 | word_document | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-13 Discipline: Civil Observation: Work on Foundation F15 reinforcement restarted today. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 20 | 2026-09-13 |  |  | update schedule | FALSE | 0.957 | English | train
UPD-00326 | word_document | email | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-03 Discipline: Instrumentation Observation: Work is continuing on Install Control Valve CV11. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.946 | English | train
UPD-01642 | pdf_text | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ PIP-L24-001 ¦ Erect Line 24 is delayed because of valve not available at site. Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | valve not available at site | resume after clearance | FALSE | 0.99 | English | train
UPD-00759 | whatsapp | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: Sir, crew resumed erect line 24 after clearance. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | resumption | RESUMED | 80 | 2026-09-12 |  |  | update schedule | FALSE | 0.973 | English | train
UPD-00600 | site_diary | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-21 ¦ Unit 2 ¦ Lay Cable Route 7 cancelled for today. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.905 | English | train
UPD-00698 | excel_note | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Progress note: CIV-F15-001 ¦ Foundation F15 excavation ¦ CANCELLED ¦ NA Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.956 | English | train
UPD-00950 | whatsapp | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: Hi, crew is currently working on align pump p04. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-07 |  |  | receive material | FALSE | 0.977 | English | train
UPD-01770 | voice_transcript | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: So, basically, foundation f15 reinforcement has been completed at unit 2. FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | obtain permit | FALSE | 0.915 | English | train
UPD-01337 | excel_note | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - CIV-F15-002 ¦ Foundation F15 reinforcement ¦ RESUMED ¦ NA For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-08 |  |  | update schedule | FALSE | 0.936 | English | train
UPD-00016 | whatsapp | DPR | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: Sir, complete work-at-height inspection has been completed at unit 2. Kindly update the plan. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | resume after clearance | FALSE | 0.955 | English | train
UPD-00647 | voice_transcript | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Uh, foundation f15 reinforcement has resumed following resolution of the earlier issue. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-21 |  |  | update schedule | FALSE | 0.917 | English | train
UPD-01725 | email | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Team finished Install Tank T02 internals. Regards, Site Supervisor Material expected tomorrow. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | resume after clearance | FALSE | 0.92 | English | train
UPD-00019 | ms_project_update | document | 2026-09-24 | OIL-UNIT2-DEMO | Today: MS Project note: CIV-R02-001 status = CANCELLED. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.934 | English | train
UPD-01687 | voice_transcript | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Today: So, basically, crew is currently working on install pump p03. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 70 | 2026-09-22 |  |  | update schedule | FALSE | 0.984 | English | train
UPD-01624 | voice_transcript | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: So, basically, no start for hydrotest line 23 today. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.978 | English | train
UPD-01644 | voice_transcript | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that road r02 subgrade preparation has resumed following resolution of the earlier issue. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 70 | 2026-09-11 |  |  | complete inspection | FALSE | 0.974 | English | train
UPD-00406 | word_document | document | 2026-09-21 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-21 Discipline: Mechanical Observation: Today's Install Heat Exchanger HX01 activity has been cancelled. Material expected tomorrow. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.905 | English | train
UPD-01160 | pdf_text | document | 2026-09-22 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-L30-001 ¦ Install 30-inch header has resumed following resolution of the earlier issue. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 70 | 2026-09-22 |  |  | obtain permit | FALSE | 0.963 | English | train
UPD-01210 | word_document | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-27 Discipline: Piping Observation: No start for Hydrotest Line 24 today. Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.9 | English | train
UPD-01577 | site_diary | spreadsheet | 2026-09-17 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-17 ¦ Unit 2 ¦ Install Temperature Transmitter T04 started today. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 20 | 2026-09-17 |  |  | mobilise crew | FALSE | 0.929 | English | train
UPD-00402 | voice_transcript | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: So, basically, lay cable route 7 is about 60% complete. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-27 |  |  | receive material | FALSE | 0.906 | English | train
UPD-00006 | whatsapp | spreadsheet | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Foundation F15 excavation has not started yet. 👍 | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.906 | English | train
UPD-01367 | ms_project_update | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-L24-003 progress affected by equipment breakdown; expected finish to move. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | complete inspection | FALSE | 0.963 | English | train
UPD-00550 | excel_note | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: PIP-L23-001 ¦ Erect Line 23 ¦ RESUMED ¦ NA Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | resumption | RESUMED | 60 | 2026-09-19 |  |  | update schedule | FALSE | 0.919 | English | train
UPD-00715 | voice_transcript | email | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: Just to update you, install temperature transmitter t04 progressing as planned. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-23 |  |  | complete inspection | FALSE | 0.936 | English | train
UPD-00357 | ms_project_update | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: MS Project update: ELE-TR02-001 actual start = 2026-09-23; work commenced. Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 60 | 2026-09-23 |  |  | complete inspection | FALSE | 0.966 | English | train
UPD-01526 | pdf_text | DPR | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ CIV-TK01-001 ¦ Tank T01 foundation completion is about 80% complete. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 80 | 2026-09-01 |  |  | receive material | FALSE | 0.942 | English | train
UPD-00811 | voice_transcript | document | 2026-09-03 | OIL-UNIT2-DEMO | So, basically, work on weld line 23 restarted today. Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | resumption | RESUMED | 70 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.975 | English | train
UPD-01057 | ms_project_update | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Today: MS Project note: ELE-CBL07-001 status = CANCELLED. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.961 | English | train
UPD-01340 | excel_note | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: PIP-L23-001 ¦ Erect Line 23 ¦ CANCELLED ¦ NA FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.923 | English | train
UPD-00603 | voice_transcript | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Just to update you, install 30-inch header remains on hold due to safety clearance pending. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | safety clearance pending | planner review | FALSE | 0.919 | English | train
UPD-00672 | pdf_text | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ PIP-L23-001 ¦ Erect Line 23 could not proceed today due to design revision pending. Material expected tomorrow. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | design revision pending | obtain permit | FALSE | 0.917 | English | train
UPD-00133 | pdf_text | email | 2026-09-10 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 could not proceed today due to rainfall at site. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | rainfall at site | resume after clearance | FALSE | 0.924 | English | train
UPD-00477 | excel_note | email | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: HSE-002-001 ¦ Close scaffold inspection actions ¦ COMPLETED ¦ NA | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | obtain permit | FALSE | 0.97 | English | train
UPD-01729 | site_diary | MS_Project | 2026-09-16 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-16 ¦ Unit 1 ¦ Install 30-inch header has not started yet. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.981 | English | train
UPD-01065 | pdf_text | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ CIV-F15-001 ¦ Foundation F15 excavation has been completed at Unit 2. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-03 | 2026-09-03 |  | update schedule | FALSE | 0.988 | English | train
UPD-00853 | excel_note | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Today: CIV-F15-001 ¦ Foundation F15 excavation ¦ BLOCKED ¦ client approval pending Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | mobilise crew | FALSE | 0.966 | English | train
UPD-01245 | word_document | document | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-08 Discipline: Civil Observation: Crew resumed Road R02 subgrade preparation after clearance. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 20 | 2026-09-08 |  |  | receive material | FALSE | 0.968 | English | train
UPD-00737 | whatsapp | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: Sir, foundation f15 excavation is delayed because of vendor technician not available. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | delay | DELAYED | 10 |  |  | vendor technician not available | resume after clearance | FALSE | 0.961 | English | train
UPD-01010 | whatsapp | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Sir, crew resumed install pump p03 after clearance. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 80 | 2026-09-22 |  |  | obtain permit | FALSE | 0.954 | English | train
UPD-01288 | pdf_text | mobile | 2026-09-22 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ MEC-P04-001 ¦ Supervisor confirms Align Pump P04 complete. For information. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | obtain permit | FALSE | 0.934 | English | train
UPD-01383 | site_diary | DPR | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-04 ¦ Unit 2 ¦ Work on Install Control Valve CV11 restarted today. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 10 | 2026-09-04 |  |  | obtain permit | FALSE | 0.981 | English | train
UPD-00030 | word_document | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-21 Discipline: Civil Observation: Foundation F15 concreting will not be executed today. FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.962 | English | train
UPD-00125 | voice_transcript | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Just to update you, hydrotest line 23 is blocked pending equipment breakdown. Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | resume after clearance | FALSE | 0.9 | English | train
UPD-01636 | ms_project_update | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Today: MS Project note: INS-PT08-001 progress affected by QA/QC hold point not cleared; expected finish to move. Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | delay | DELAYED | 70 |  |  | QA/QC hold point not cleared | resume after clearance | FALSE | 0.967 | English | train
UPD-00361 | pdf_text | mobile | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 30-09-2026 ¦ PIP-L24-001 ¦ Erect Line 24 remains not started. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.959 | English | train
UPD-01034 | site_diary | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-04 ¦ Plant Area ¦ Road R02 subgrade preparation remains not started. Please note. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.982 | English | train
UPD-01200 | whatsapp | MS_Project | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Sir, weld line 24 remains on hold due to equipment breakdown. Material expected tomorrow. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | resume after clearance | FALSE | 0.901 | English | train
UPD-01562 | site_diary | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-19 ¦ Pump House ¦ Crew resumed Install Pump P03 after clearance. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 10 | 2026-09-19 |  |  | resume after clearance | FALSE | 0.925 | English | train
UPD-01131 | word_document | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-30 Discipline: Instrumentation Observation: Install Control Valve CV11 started today. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 20 | 2026-09-30 |  |  | update schedule | FALSE | 0.952 | English | train
UPD-01048 | word_document | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-18 Discipline: Instrumentation Observation: No progress on Install Pressure Transmitter PT08 today due to crane unavailable. Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | delay | DELAYED | 20 |  |  | crane unavailable | mobilise crew | FALSE | 0.982 | English | train
UPD-00346 | ms_project_update | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-L23-003 progress affected by equipment breakdown; expected finish to move. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | receive material | FALSE | 0.925 | English | train
UPD-00621 | email | DPR | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Team finished Road R02 subgrade preparation. Regards, Site Supervisor Please note. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | complete inspection | FALSE | 0.947 | English | train
UPD-00156 | word_document | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-04 Discipline: Mechanical Observation: Supervisor confirms Install Compressor C01 completed. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-04 | 2026-09-04 |  | mobilise crew | FALSE | 0.939 | English | train
UPD-00106 | ms_project_update | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: ELE-MCC03-001 status = IN PROGRESS. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 50 | 2026-09-18 |  |  | continue work | FALSE | 0.924 | English | train
UPD-00499 | pdf_text | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-L24-003 ¦ Today's Hydrotest Line 24 activity has been cancelled. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.963 | English | train
UPD-00303 | email | document | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 is complete as of today. Regards, Site Supervisor Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | continue work | FALSE | 0.932 | English | train
UPD-01668 | word_document | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-27 Discipline: Piping Observation: Hydrotest Line 24 is complete as of today. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | planner review | FALSE | 0.924 | English | train
UPD-01622 | excel_note | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: CIV-F15-001 ¦ Foundation F15 excavation ¦ PARTIAL ¦ NA Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-08 |  |  | update schedule | FALSE | 0.939 | English | train
UPD-01790 | whatsapp | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Hi, partial progress achieved on install mcc panel 3. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 30 | 2026-09-22 |  |  | continue work | FALSE | 0.937 | English | train
UPD-00103 | pdf_text | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 remains on hold due to scaffold not ready. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | scaffold not ready | update schedule | FALSE | 0.909 | English | train
UPD-00305 | voice_transcript | DPR | 2026-09-26 | OIL-UNIT2-DEMO | So, basically, supervisor confirms tank t01 foundation completion completed. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | obtain permit | FALSE | 0.906 | English | train
UPD-00150 | excel_note | email | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - MEC-P04-001 ¦ Align Pump P04 ¦ CANCELLED ¦ NA Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.965 | English | train
UPD-00572 | word_document | document | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-06 Discipline: Electrical Observation: Today's Install Transformer TR02 activity has been cancelled. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.956 | English | train
UPD-01617 | excel_note | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | PIP-L24-001 ¦ Erect Line 24 ¦ STARTED ¦ NA Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 60 | 2026-09-11 |  |  | update schedule | FALSE | 0.948 | English | train
UPD-00279 | pdf_text | email | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ CIV-F15-001 ¦ Cannot continue Foundation F15 excavation until matl not received is resolved. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | mobilise crew | FALSE | 0.971 | English | train
UPD-01298 | word_document | DPR | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-22 Discipline: HSE Observation: Complete work-at-height inspection is in progress. Kindly update the plan. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.964 | English | train
UPD-01124 | word_document | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-27 Discipline: Piping Observation: Crew mobilised and started Install Valve V12. FYI. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-27 |  |  | obtain permit | FALSE | 0.902 | English | train
UPD-01522 | plain_text | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Terminate Junction Box JB05 has resumed following resolution of the earlier issue. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | resumption | RESUMED | 20 | 2026-09-28 |  |  | mobilise crew | FALSE | 0.922 | English | train
UPD-01588 | whatsapp | email | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: Sir, work on hydrotest line 23 restarted today. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 50 | 2026-09-14 |  |  | resume after clearance | FALSE | 0.919 | English | train
UPD-00070 | ms_project_update | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: MS Project note: MEC-P03-001 status = CANCELLED. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.968 | English | train
UPD-00722 | plain_text | document | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Crew resumed Close scaffold inspection actions after clearance. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 80 | 2026-09-16 |  |  | receive material | FALSE | 0.981 | English | train
UPD-01626 | whatsapp | document | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: Line/area update: complete work-at-height inspection remains not started. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.919 | English | train
UPD-01031 | plain_text | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: Planned work Hydrotest Line 24 did not commence. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.969 | English | train
UPD-01613 | voice_transcript | email | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that weld line 24 will not be executed today. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.976 | English | train
UPD-00061 | whatsapp | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: Install Valve V12 is complete as of today. 👍 Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | planner review | FALSE | 0.914 | English | train
UPD-00521 | site_diary | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-06 ¦ Compressor Area ¦ Execution of Install Compressor C01 is blocked by insufficient manpower. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | insufficient manpower | complete inspection | FALSE | 0.978 | English | train
UPD-01190 | word_document | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-08 Discipline: Civil Observation: Foundation F15 concreting has resumed following resolution of the earlier issue. Material expected tomorrow. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 60 | 2026-09-08 |  |  | planner review | FALSE | 0.964 | English | train
UPD-01550 | excel_note | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: CIV-R02-002 ¦ Road R02 PCC laying ¦ PARTIAL ¦ NA Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 40 | 2026-09-25 |  |  | update schedule | FALSE | 0.987 | English | train
UPD-00960 | whatsapp | document | 2026-09-17 | OIL-UNIT2-DEMO | Today: Align Pump P04 progressing as planned. 👍 | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.948 | English | train
UPD-00021 | email | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 is about 20% complete. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 20 | 2026-09-15 |  |  | update schedule | FALSE | 0.956 | English | train
UPD-01697 | plain_text | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: Work on Hydrotest Line 23 was stopped because vendor technician not available. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | vendor technician not available | obtain permit | FALSE | 0.942 | English | train
UPD-00098 | word_document | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-30 Discipline: Piping Observation: Erect Line 23 has not started yet. Please note. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.954 | English | train
UPD-00472 | ms_project_update | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: MS Project note: ELE-CBL07-001 status = RESUMED. For information. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 40 | 2026-09-25 |  |  | update schedule | FALSE | 0.934 | English | train
UPD-00023 | pdf_text | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ PIP-L24-002 ¦ Crew resumed Weld Line 24 after clearance. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 10 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.933 | English | train
UPD-00418 | plain_text | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Foundation F15 reinforcement is blocked pending scaffold not ready. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | scaffold not ready | mobilise crew | FALSE | 0.907 | English | train
UPD-00557 | word_document | document | 2026-09-01 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-01 Discipline: Instrumentation Observation: Terminate Junction Box JB05 remains not started. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.915 | English | train
UPD-00467 | pdf_text | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ MEC-C01-001 ¦ Install Compressor C01 is blocked pending vendor technician not available. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | vendor technician not available | receive material | FALSE | 0.934 | English | train
UPD-00336 | whatsapp | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | Supervisor update - Sir, work for align pump p04 is finished. For information. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | planner review | FALSE | 0.936 | English | train
UPD-00695 | ms_project_update | DPR | 2026-09-30 | OIL-UNIT2-DEMO | 10-Sep update: MS Project update: INS-CV11-001 actual start = 2026-09-30; work commenced. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 70 | 2026-09-30 |  |  | receive material | FALSE | 0.985 | English | train
UPD-01197 | site_diary | email | 2026-09-29 | OIL-UNIT2-DEMO | Today: Date 2026-09-29 ¦ Tank Farm ¦ Install Tank T02 internals is in progress. Planner action required. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | progress | IN_PROGRESS | 80 | 2026-09-29 |  |  | complete inspection | FALSE | 0.923 | English | train
UPD-00516 | email | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Install MCC Panel 3 is delayed because of client approval pending. Regards, Site Supervisor Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | delay | DELAYED | 30 |  |  | client approval pending | complete inspection | FALSE | 0.907 | English | train
UPD-00918 | ms_project_update | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Site Update: MS Project note: PIP-L24-003 status = CANCELLED. FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.98 | English | train
UPD-01314 | voice_transcript | document | 2026-09-23 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that close scaffold inspection actions held up by late material inspection. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 50 |  |  | late material inspection | obtain permit | FALSE | 0.971 | English | train
UPD-00988 | pdf_text | mobile | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ PIP-L24-001 ¦ Erect Line 24 will not be executed today. Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.918 | English | train
UPD-01274 | whatsapp | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: Line/area update: no progress on install control valve cv11 today due to qa/qc hold point not cleared. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | delay | DELAYED | 20 |  |  | QA/QC hold point not cleared | update schedule | FALSE | 0.933 | English | train
UPD-01372 | ms_project_update | site_diary | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: MS Project update: PIP-L23-001 Actual % Complete = 60% as of 2026-09-26. Kindly update the plan. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 60 | 2026-09-26 |  |  | mobilise crew | FALSE | 0.9 | English | train
UPD-01188 | voice_transcript | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Uh, work on terminate junction box jb05 was stopped because client approval pending. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 70 |  |  | client approval pending | continue work | FALSE | 0.98 | English | train
UPD-00575 | email | DPR | 2026-09-28 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 will not be executed today. Regards, Site Supervisor Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.931 | English | train
UPD-00882 | site_diary | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-30 ¦ Unit 2 ¦ Foundation F15 reinforcement progressing as planned. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-30 |  |  | mobilise crew | FALSE | 0.954 | English | train
UPD-01716 | email | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Around 50% work completed on Align Pump P04; balance is ongoing. Regards, Site Supervisor Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 50 | 2026-09-23 |  |  | receive material | FALSE | 0.972 | English | train
UPD-01198 | voice_transcript | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that today's install compressor c01 activity has been cancelled. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.941 | English | train
UPD-01694 | plain_text | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Crew resumed Foundation F15 excavation after clearance. Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 20 | 2026-09-15 |  |  | continue work | FALSE | 0.916 | English | train
UPD-00162 | voice_transcript | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Uh, only part of install 30-inch header could be comp. today. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 20 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.988 | English | train
UPD-00980 | plain_text | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: Road R02 PCC laying ongoing at Plant Area. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 80 | 2026-09-22 |  |  | planner review | FALSE | 0.989 | English | train
UPD-00439 | excel_note | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: CIV-R02-002 ¦ Road R02 PCC laying ¦ STARTED ¦ NA Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 60 | 2026-09-13 |  |  | obtain permit | FALSE | 0.978 | English | train
UPD-00881 | email | document | 2026-09-26 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation has not started yet. Regards, Site Supervisor FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.944 | English | train
UPD-00558 | email | email | 2026-09-17 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Work is continuing on Install Heat Exchanger HX01. Regards, Site Supervisor FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | progress | IN_PROGRESS | 40 | 2026-09-17 |  |  | mobilise crew | FALSE | 0.922 | English | train
UPD-00617 | voice_transcript | email | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Uh, erect line 24 is delayed because of material not received. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | material not received | obtain permit | FALSE | 0.967 | English | train
UPD-00525 | email | email | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting cancelled for today. Regards, Site Supervisor Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.936 | English | train
UPD-00841 | site_diary | document | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-27 ¦ Pump House ¦ Install Pump P03 remains not started. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.967 | English | train
UPD-00927 | word_document | DPR | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-10 Discipline: Electrical Observation: No start for Install Transformer TR02 today. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.924 | English | train
UPD-01737 | excel_note | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: MEC-P03-001 ¦ Install Pump P03 ¦ IN PROGRESS ¦ NA Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 60 | 2026-09-10 |  |  | planner review | FALSE | 0.924 | English | train
UPD-01094 | whatsapp | email | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Hi, install temperature transmitter t04 remains not started. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.965 | English | train
UPD-01704 | excel_note | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ PARTIAL ¦ NA FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.979 | English | train
UPD-01030 | excel_note | email | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - ELE-LTG02-001 ¦ Install Unit 2 lighting ¦ PARTIAL ¦ NA Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-01 |  |  | update schedule | FALSE | 0.943 | English | train
UPD-01582 | pdf_text | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ PIP-L23-001 ¦ Today's Erect Line 23 activity has been cancelled. Material expected tomorrow. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.93 | English | train
UPD-00318 | whatsapp | DPR | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: Sir, install transformer tr02 is blocked pending work permit not issued. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | blockage | BLOCKED | 0 |  |  | work permit not issued | update schedule | FALSE | 0.984 | English | train
UPD-00250 | voice_transcript | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Unit update: Just to update you, hydrotest line 23 progressing as planned. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-12 |  |  | update schedule | FALSE | 0.958 | English | train
UPD-00898 | word_document | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-05 Discipline: Civil Observation: Road R02 subgrade preparation is about 10% complete. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 10 | 2026-09-05 |  |  | receive material | FALSE | 0.948 | English | train
UPD-00063 | pdf_text | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 07-09-2026 ¦ CIV-F15-002 ¦ Foundation F15 reinforcement has resumed following resolution of the earlier issue. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 10 | 2026-09-07 |  |  | update schedule | FALSE | 0.943 | English | train
UPD-01045 | excel_note | email | 2026-09-20 | OIL-UNIT2-DEMO | CIV-R02-001 ¦ Road R02 subgrade preparation ¦ DELAYED ¦ late material inspection FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 20 |  |  | late material inspection | resume after clearance | FALSE | 0.966 | English | train
UPD-01475 | pdf_text | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ ELE-CBL07-001 ¦ Work on Lay Cable Route 7 restarted today. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 50 | 2026-09-09 |  |  | mobilise crew | FALSE | 0.95 | English | train
UPD-00694 | voice_transcript | document | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: So, basically, work on foundation f15 concreting has begun. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 30 | 2026-09-19 |  |  | mobilise crew | FALSE | 0.953 | English | train
UPD-01667 | excel_note | document | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: MEC-P03-001 ¦ Install Pump P03 ¦ COMPLETED ¦ NA FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | complete inspection | FALSE | 0.948 | English | train
UPD-01292 | ms_project_update | mobile | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: MS Project note: PIP-L24-003 status = RESUMED. Please note. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-30 |  |  | continue work | FALSE | 0.923 | English | train
UPD-01631 | excel_note | email | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: HSE-001-001 ¦ Complete work-at-height insp. ¦ BLOCKED ¦ QA/QC hold point not cleared Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | receive material | FALSE | 0.933 | English | train
UPD-00403 | site_diary | document | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-12 ¦ Unit 2 ¦ Partial progress achieved on Terminate Junction Box JB05. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-12 |  |  | continue work | FALSE | 0.955 | English | train
UPD-00674 | whatsapp | document | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Hi, erect line 24 started today. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-18 |  |  | complete inspection | FALSE | 0.911 | English | train
UPD-00238 | site_diary | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-09 ¦ Unit 1 ¦ Install 30-inch header partially completed today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 70 | 2026-09-09 |  |  | obtain permit | FALSE | 0.944 | English | train
UPD-00905 | email | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - INS-CV11-001 Dear Team, Execution of Install Control Valve CV11 is blocked by QA/QC hold point not cleared. Regards, Site Supervisor Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | mobilise crew | FALSE | 0.978 | English | train
UPD-01710 | plain_text | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Install Valve V12 ongoing at Unit 2. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-29 |  |  | update schedule | FALSE | 0.923 | English | train
UPD-00542 | plain_text | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Hydrotest Line 24 will not be executed today. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.943 | English | train
UPD-01505 | excel_note | email | 2026-09-22 | OIL-UNIT2-DEMO | Today: MEC-C01-001 ¦ Install Compressor C01 ¦ RESUMED ¦ NA Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | resumption | RESUMED | 60 | 2026-09-22 |  |  | complete inspection | FALSE | 0.925 | English | train
UPD-00058 | word_document | document | 2026-09-28 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-28 Discipline: Civil Observation: Road R02 PCC laying will not be executed today. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.948 | English | train
UPD-01026 | pdf_text | MS_Project | 2026-09-16 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ MEC-P03-001 ¦ No start for Install Pump P03 today. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.94 | English | train
UPD-01169 | email | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-R02-001 Dear Team, Execution of Road R02 subgrade preparation is blocked by client approval pending. Regards, Site Supervisor | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | client approval pending | mobilise crew | FALSE | 0.983 | English | train
UPD-01047 | voice_transcript | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Just to update you, crew resumed foundation f15 excavation after clearance. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 80 | 2026-09-26 |  |  | mobilise crew | FALSE | 0.987 | English | train
UPD-00899 | site_diary | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Today: Date 2026-09-17 ¦ Unit 2 ¦ Work is continuing on Install Temperature Transmitter T04. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-17 |  |  | receive material | FALSE | 0.919 | English | train
UPD-00619 | plain_text | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Install Tank T02 internals ongoing at Tank Farm. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | progress | IN_PROGRESS | 40 | 2026-09-04 |  |  | mobilise crew | FALSE | 0.961 | English | train
UPD-00574 | word_document | document | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-05 Discipline: Electrical Observation: Partial progress achieved on Install MCC Panel 3. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 80 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.936 | English | train
UPD-00777 | email | spreadsheet | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - PIP-L23-001 Dear Team, Today's Erect Line 23 activity has been cancelled. Regards, Site Supervisor Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.904 | English | train
UPD-01700 | site_diary | mobile | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-18 ¦ Unit 2 ¦ Cannot continue Erect Line 24 until work permit not issued is resolved. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | complete inspection | FALSE | 0.914 | English | train
UPD-01121 | email | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-L23-001 Dear Team, Erect Line 23 remains not started. Regards, Site Supervisor Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.923 | English | train
UPD-00027 | ms_project_update | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: MS Project update: INS-PT08-001 marked 100% complete. Actual Finish: 2026-09-22. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | update schedule | FALSE | 0.968 | English | train
UPD-00348 | excel_note | email | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: MEC-P03-001 ¦ Install Pump P03 ¦ CANCELLED ¦ NA Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.933 | English | train
UPD-00294 | site_diary | email | 2026-09-19 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-19 ¦ Electrical Room ¦ Install MCC Panel 3 progressing as planned. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 50 | 2026-09-19 |  |  | receive material | FALSE | 0.914 | English | train
UPD-01746 | site_diary | site_diary | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-19 ¦ Unit 2 ¦ Complete work-at-height inspection will not be executed today. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.959 | English | train
UPD-00639 | word_document | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-30 Discipline: Mechanical Observation: Install Heat Exchanger HX01 remains on hold due to crane unavailable. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | crane unavailable | continue work | FALSE | 0.984 | English | train
UPD-01573 | whatsapp | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: Line/area update: install control valve cv11 remains not started. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.94 | English | train
UPD-00644 | plain_text | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Install Tank T02 internals is complete as of today. For information. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | obtain permit | FALSE | 0.928 | English | train
UPD-00612 | site_diary | document | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-17 ¦ Unit 2 ¦ Foundation F15 reinforcement will not be executed today. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.915 | English | train
UPD-01787 | voice_transcript | DPR | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, install control valve cv11 remains on hold due to rainfall at site. Material expected tomorrow. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | update schedule | FALSE | 0.966 | English | train
UPD-01606 | word_document | email | 2026-09-20 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-20 Discipline: Mechanical Observation: Today's Install Heat Exchanger HX01 activity has been cancelled. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.976 | English | train
UPD-00170 | plain_text | email | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Cannot continue Complete work-at-height inspection until design revision pending is resolved. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | receive material | FALSE | 0.915 | English | train
UPD-01673 | pdf_text | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 14-09-2026 ¦ CIV-F15-003 ¦ Foundation F15 concreting progressing as planned. Material expected tomorrow. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-14 |  |  | complete inspection | FALSE | 0.925 | English | train
UPD-00107 | whatsapp | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | Progress note: Install Control Valve CV11 progressing as planned. 👍 Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-01 |  |  | obtain permit | FALSE | 0.978 | English | train
UPD-01112 | ms_project_update | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | Today: MS Project update: MEC-P04-001 marked 100% complete. Actual Finish: 2026-09-09. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | complete inspection | FALSE | 0.914 | English | train
UPD-00119 | voice_transcript | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that install temperature transmitter t04 done at site. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | receive material | FALSE | 0.986 | English | train
UPD-01390 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ ELE-LTG02-001 ¦ Only part of Install Unit 2 lighting could be completed today. Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-04 |  |  | update schedule | FALSE | 0.929 | English | train
UPD-00911 | plain_text | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | 10-Sep update: Erect Line 24 could not proceed today due to scaffold not ready. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | scaffold not ready | mobilise crew | FALSE | 0.981 | English | train
UPD-01100 | site_diary | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-25 ¦ Unit 2 ¦ Lay Cable Route 7 is delayed because of insufficient manpower. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 60 |  |  | insufficient manpower | complete inspection | FALSE | 0.927 | English | train
UPD-00366 | site_diary | mobile | 2026-09-15 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-15 ¦ Unit 2 ¦ Planned work Foundation F15 concreting did not commence. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.967 | English | train
UPD-01655 | site_diary | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-14 ¦ Unit 2 ¦ Erect Line 24 could not proceed today due to scaffold not ready. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | scaffold not ready | resume after clearance | FALSE | 0.964 | English | train
UPD-00649 | whatsapp | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Line/area update: install transformer tr02 is about 75% complete. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 75 | 2026-09-13 |  |  | update schedule | FALSE | 0.904 | English | train
UPD-00701 | plain_text | DPR | 2026-09-01 | OIL-UNIT2-DEMO | 10-Sep update: Only part of Lay Cable Route 7 could be completed today. Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-01 |  |  | resume after clearance | FALSE | 0.987 | English | train
UPD-00325 | pdf_text | email | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ INS-PT08-001 ¦ Install Pressure Transmitter PT08 is blocked pending design revision pending. Please note. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | design revision pending | receive material | FALSE | 0.989 | English | train
UPD-00955 | excel_note | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-001 ¦ Foundation F15 excavation ¦ COMPLETED ¦ NA Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | receive material | FALSE | 0.937 | English | train
UPD-01709 | plain_text | document | 2026-09-03 | OIL-UNIT2-DEMO | Today: Close scaffold inspection actions is complete as of today. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-03 | 2026-09-03 |  | complete inspection | FALSE | 0.986 | English | train
UPD-00180 | voice_transcript | site_diary | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: Just to update you, crew mobilised and started hydrotest line 24. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-27 |  |  | receive material | FALSE | 0.957 | English | train
UPD-00914 | whatsapp | email | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: Line/area update: road r02 pcc laying has been comp. at plant area. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-25 | 2026-09-25 |  | receive material | FALSE | 0.92 | English | train
UPD-01248 | pdf_text | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 14-09-2026 ¦ CIV-R02-002 ¦ Road R02 PCC laying done at site. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | planner review | FALSE | 0.943 | English | train
UPD-01619 | pdf_text | email | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 will not be executed today. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.981 | English | train
UPD-01540 | ms_project_update | email | 2026-09-10 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-003 progress affected by insufficient manpower; expected finish to move. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 20 |  |  | insufficient manpower | continue work | FALSE | 0.986 | English | train
UPD-01035 | whatsapp | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Today: Line/area update: crew is currently working on weld line 23. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-20 |  |  | obtain permit | FALSE | 0.978 | English | train
UPD-00800 | plain_text | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Unit update: Partial progress achieved on Foundation F15 reinforcement. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-23 |  |  | complete inspection | FALSE | 0.986 | English | train
UPD-00576 | plain_text | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: Road R02 subgrade preparation is complete as of today. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | update schedule | FALSE | 0.924 | English | train
UPD-00284 | pdf_text | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 30-09-2026 ¦ MEC-HX01-001 ¦ Crew resumed Install Heat Exchanger HX01 after clearance. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 60 | 2026-09-30 |  |  | obtain permit | FALSE | 0.969 | English | train
UPD-01237 | voice_transcript | email | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - So, basically, install temperature transmitter t04 will not be executed today. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.936 | English | train
UPD-00529 | ms_project_update | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L23-003 progress affected by late material inspection; expected finish to move. For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | continue work | FALSE | 0.97 | English | train
UPD-00165 | ms_project_update | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-F15-001 progress affected by scaffold not ready; expected finish to move. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | scaffold not ready | receive material | FALSE | 0.98 | English | train
UPD-00789 | whatsapp | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: Sir, install mcc panel 3 is about 30% complete. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 30 | 2026-09-13 |  |  | complete inspection | FALSE | 0.926 | English | train
UPD-00877 | word_document | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-22 Discipline: Electrical Observation: Install MCC Panel 3 comp. today. Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | continue work | FALSE | 0.915 | English | train
UPD-00716 | plain_text | mobile | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Install Pump P03 remains on hold due to inspection clearance pending. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | inspection clearance pending | obtain permit | FALSE | 0.904 | English | train
UPD-00827 | whatsapp | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - Line/area update: team finished close scaffold insp. actions. Material expected tomorrow. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | update schedule | FALSE | 0.958 | English | train
UPD-00733 | whatsapp | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Team finished Install 30-inch header. 👍 Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | resume after clearance | FALSE | 0.926 | English | train
UPD-00816 | voice_transcript | email | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Okay, today's update is that planned work close scaffold insp. actions did not commence. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.92 | English | train
UPD-01527 | whatsapp | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Line/area update: work on install compressor c01 has begun. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 20 | 2026-09-05 |  |  | continue work | FALSE | 0.915 | English | train
UPD-00623 | whatsapp | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Today: Sir, no progress on install temperature transmitter t04 today due to safety clearance pending. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 80 |  |  | safety clearance pending | resume after clearance | FALSE | 0.927 | English | train
UPD-00637 | word_document | DPR | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-13 Discipline: Civil Observation: Road R02 subgrade preparation cancelled for today. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.927 | English | train
UPD-01302 | ms_project_update | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Today: MS Project note: MEC-HX01-001 status = RESUMED. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 40 | 2026-09-09 |  |  | planner review | FALSE | 0.956 | English | train
UPD-01029 | whatsapp | email | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Line/area update: install tank t02 internals cancelled for today. Planner action required. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.907 | English | train
UPD-00122 | site_diary | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-16 ¦ Unit 2 ¦ Weld Line 24 held up by power supply interruption. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | power supply interruption | receive material | FALSE | 0.93 | English | train
UPD-01344 | email | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 remains on hold due to insufficient manpower. Regards, Site Supervisor Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | update schedule | FALSE | 0.967 | English | train
UPD-01350 | pdf_text | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ PIP-L24-002 ¦ Started Weld Line 24 this morning. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-05 |  |  | receive material | FALSE | 0.955 | English | train
UPD-00754 | email | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Road R02 subgrade preparation progressing as planned. Regards, Site Supervisor Please note. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 50 | 2026-09-23 |  |  | receive material | FALSE | 0.936 | English | train
UPD-00577 | voice_transcript | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Today: Uh, work is continuing on install temperature transmitter t04. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-23 |  |  | update schedule | FALSE | 0.917 | English | train
UPD-01599 | whatsapp | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Today: Line/area update: align pump p04 resumed today after material not received was cleared. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 50 | 2026-09-05 |  |  | planner review | FALSE | 0.987 | English | train
UPD-00753 | whatsapp | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Line/area update: tank t01 foundation completion cancelled for today. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.912 | English | train
UPD-01504 | plain_text | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Supervisor update - Execution of Install Valve V12 is blocked by insufficient manpower. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | update schedule | FALSE | 0.98 | English | train
UPD-00498 | whatsapp | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Hi, started align pump p04 this morning. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 20 | 2026-09-13 |  |  | update schedule | FALSE | 0.969 | English | train
UPD-00863 | voice_transcript | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: So, basically, partial progress achieved on install temperature transmitter t04. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-08 |  |  | update schedule | FALSE | 0.976 | English | train
UPD-01355 | whatsapp | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Hi, install mcc panel 3 is complete as of today. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | resume after clearance | FALSE | 0.944 | English | train
UPD-00642 | ms_project_update | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-V12-001 status = RESUMED. Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | resumption | RESUMED | 40 | 2026-09-23 |  |  | continue work | FALSE | 0.966 | English | train
UPD-00148 | email | document | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header has resumed following resolution of the earlier issue. Regards, Site Supervisor Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 20 | 2026-09-02 |  |  | complete inspection | FALSE | 0.906 | English | train
UPD-00924 | email | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - CIV-F15-003 Dear Team, Team finished Foundation F15 concreting. Regards, Site Supervisor FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | receive material | FALSE | 0.935 | English | train
UPD-00317 | ms_project_update | email | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-V12-001 status = RESUMED. Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | resumption | RESUMED | 20 | 2026-09-27 |  |  | receive material | FALSE | 0.906 | English | train
UPD-00906 | word_document | MS_Project | 2026-09-28 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-28 Discipline: HSE Observation: Complete work-at-height insp. has resumed following resolution of the earlier issue. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | resumption | RESUMED | 60 | 2026-09-28 |  |  | mobilise crew | FALSE | 0.956 | English | train
UPD-01281 | word_document | spreadsheet | 2026-09-16 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-16 Discipline: Instrumentation Observation: Execution of Install Temperature Transmitter T04 is blocked by QA/QC hold point not cleared. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | receive material | FALSE | 0.915 | English | train
UPD-01070 | ms_project_update | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | Site Update: MS Project note: CIV-F15-001 status = IN PROGRESS. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-04 |  |  | obtain permit | FALSE | 0.913 | English | train
UPD-01574 | ms_project_update | email | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: MS Project note: PIP-L23-003 status = NOT STARTED. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.93 | English | train
UPD-01091 | plain_text | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: Foundation F15 reinforcement is blocked pending design revision pending. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | mobilise crew | FALSE | 0.931 | English | train
UPD-01285 | whatsapp | mobile | 2026-09-06 | OIL-UNIT2-DEMO | Crew is currently working on Align Pump P04. 👍 Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 60 | 2026-09-06 |  |  | resume after clearance | FALSE | 0.983 | English | train
UPD-01654 | word_document | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-25 Discipline: Piping Observation: Partial progress achieved on Hydrotest Line 24. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-25 |  |  | update schedule | FALSE | 0.967 | English | train
UPD-01221 | ms_project_update | DPR | 2026-09-24 | OIL-UNIT2-DEMO | Daily Progress: MS Project update: CIV-TK01-001 marked 100% complete. Actual Finish: 2026-09-24. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | receive material | FALSE | 0.961 | English | train
UPD-00631 | site_diary | document | 2026-09-16 | OIL-UNIT2-DEMO | Date 2026-09-16 ¦ Unit 2 ¦ Complete work-at-height inspection done at site. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | completion | COMPLETED | 100 | 2026-09-16 | 2026-09-16 |  | receive material | FALSE | 0.931 | English | train
UPD-01144 | email | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - PIP-L23-002 Dear Team, Weld Line 23 cancelled for today. Regards, Site Supervisor Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.983 | English | train
UPD-00028 | excel_note | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - PIP-V12-001 ¦ Install Valve V12 ¦ DELAYED ¦ equipment breakdown Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | equipment breakdown | continue work | FALSE | 0.951 | English | train
UPD-01257 | excel_note | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ BLOCKED ¦ material not received Kindly update the plan. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | blockage | BLOCKED | 0 |  |  | material not received | receive material | FALSE | 0.92 | English | train
UPD-00774 | plain_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Install 30-inch header will not be executed today. Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.978 | English | train
UPD-00559 | excel_note | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: PIP-V12-001 ¦ Install Valve V12 ¦ PARTIAL ¦ NA Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-21 |  |  | continue work | FALSE | 0.938 | English | train
UPD-00697 | email | DPR | 2026-09-14 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 partially completed today. Regards, Site Supervisor Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 50 | 2026-09-14 |  |  | continue work | FALSE | 0.936 | English | train
UPD-00944 | excel_note | MS_Project | 2026-09-26 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ BLOCKED ¦ drawing approval pending Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | drawing approval pending | resume after clearance | FALSE | 0.921 | English | train
UPD-00736 | excel_note | email | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: ELE-LTG02-001 ¦ Install Unit 2 lighting ¦ BLOCKED ¦ material not received Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | update schedule | FALSE | 0.935 | English | train
UPD-00456 | whatsapp | document | 2026-09-05 | OIL-UNIT2-DEMO | 10-Sep update: Sir, started install control valve cv11 this morning. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 50 | 2026-09-05 |  |  | continue work | FALSE | 0.951 | English | train
UPD-00177 | word_document | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-04 Discipline: Civil Observation: Planned work Foundation F15 excavation did not commence. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.963 | English | train
UPD-01345 | word_document | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-04 Discipline: Civil Observation: Foundation F15 excavation is blocked pending client approval pending. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | continue work | FALSE | 0.979 | English | train
UPD-01233 | plain_text | document | 2026-09-15 | OIL-UNIT2-DEMO | Only part of Install Transformer TR02 could be completed today. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 10 | 2026-09-15 |  |  | mobilise crew | FALSE | 0.962 | English | train
UPD-01580 | excel_note | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - CIV-TK01-001 ¦ Tank T01 foundation completion ¦ RESUMED ¦ NA | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 60 | 2026-09-07 |  |  | update schedule | FALSE | 0.916 | English | train
UPD-00566 | excel_note | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Daily Progress: MEC-C01-001 ¦ Install Compressor C01 ¦ DELAYED ¦ design revision pending Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 80 |  |  | design revision pending | mobilise crew | FALSE | 0.95 | English | train
UPD-00628 | email | email | 2026-09-26 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-R02-001 Dear Team, Crew resumed Road R02 subgrade preparation after clearance. Regards, Site Supervisor Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 40 | 2026-09-26 |  |  | receive material | FALSE | 0.985 | English | train
UPD-01092 | ms_project_update | document | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-F15-002 progress affected by safety clearance pending; expected finish to move. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | resume after clearance | FALSE | 0.905 | English | train
UPD-00996 | voice_transcript | document | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Just to update you, today's hydrotest line 24 activity has been cancelled. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.949 | English | train
UPD-00969 | plain_text | site_diary | 2026-09-03 | OIL-UNIT2-DEMO | Progress note: Supervisor confirms Install Heat Exchanger HX01 completed. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-03 | 2026-09-03 |  | mobilise crew | FALSE | 0.978 | English | train
UPD-01722 | ms_project_update | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | MS Project update: ELE-MCC03-001 actual start = 2026-09-27; work commenced. Material expected tomorrow. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 40 | 2026-09-27 |  |  | update schedule | FALSE | 0.97 | English | train
UPD-01307 | plain_text | document | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor confirms Install Pump P03 completed. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | obtain permit | FALSE | 0.934 | English | train
UPD-00615 | site_diary | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-15 ¦ Unit 2 ¦ Work for Hydrotest Line 24 is finished. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | complete inspection | FALSE | 0.97 | English | train
UPD-01414 | voice_transcript | email | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: Uh, terminate junction box jb05 done at site. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-21 | 2026-09-21 |  | receive material | FALSE | 0.948 | English | train
UPD-01206 | whatsapp | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Planned work Weld Line 24 did not commence. 👍 Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.929 | English | train
UPD-00900 | word_document | email | 2026-09-22 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-22 Discipline: Civil Observation: Foundation F15 reinforcement is delayed because of material not received. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | delay | DELAYED | 60 |  |  | material not received | complete inspection | FALSE | 0.969 | English | train
UPD-01755 | ms_project_update | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | MS Project note: MEC-P04-001 progress affected by vendor technician not available; expected finish to move. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | vendor technician not available | receive material | FALSE | 0.989 | English | train
UPD-00049 | voice_transcript | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that planned work weld line 24 did not commence. FYI. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.968 | English | train
UPD-00172 | whatsapp | MS_Project | 2026-09-02 | OIL-UNIT2-DEMO | Unit update: Line/area update: install 30-inch header has been completed at unit 1. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | resume after clearance | FALSE | 0.902 | English | train
UPD-01301 | whatsapp | email | 2026-09-29 | OIL-UNIT2-DEMO | Today: Hi, install valve v12 remains on hold due to valve not available at site. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | planner review | FALSE | 0.971 | English | train
UPD-01103 | site_diary | DPR | 2026-09-08 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-08 ¦ Substation ¦ Work on Install Transformer TR02 restarted today. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 60 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.98 | English | train
UPD-01310 | ms_project_update | email | 2026-09-05 | OIL-UNIT2-DEMO | MS Project update: PIP-V12-001 actual start = 2026-09-05; work commenced. FYI. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 30 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.906 | English | train
UPD-00466 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ CIV-R02-002 ¦ Around 50% work completed on Road R02 PCC laying; balance is ongoing. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 60 | 2026-09-04 |  |  | continue work | FALSE | 0.98 | English | train
UPD-00520 | excel_note | mobile | 2026-09-09 | OIL-UNIT2-DEMO | Site Update: INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ CANCELLED ¦ NA | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.901 | English | train
UPD-01348 | whatsapp | document | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Hi, no start for lay cable route 7 today. Planner action required. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.966 | English | train
UPD-00627 | whatsapp | email | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: Hi, install pump p03 cancelled for today. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.947 | English | train
UPD-01287 | plain_text | email | 2026-09-19 | OIL-UNIT2-DEMO | Weld Line 23 remains not started. Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.93 | English | train
UPD-01666 | plain_text | mobile | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: Erect Line 23 is behind plan owing to drawing approval pending. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 30 |  |  | drawing approval pending | receive material | FALSE | 0.907 | English | train
UPD-01461 | email | document | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Work on Install Tank T02 internals was stopped because vendor technician not available. Regards, Site Supervisor Planner action required. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | delay | DELAYED | 30 |  |  | vendor technician not available | continue work | FALSE | 0.931 | English | train
UPD-00893 | word_document | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-12 Discipline: Instrumentation Observation: Crew resumed Install Control Valve CV11 after clearance. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 70 | 2026-09-12 |  |  | continue work | FALSE | 0.96 | English | train
UPD-00760 | ms_project_update | document | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: MS Project note: ELE-LTG02-001 progress affected by shortage of 24-inch pipes; expected finish to move. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | mobilise crew | FALSE | 0.909 | English | train
UPD-00289 | excel_note | email | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: PIP-L23-002 ¦ Weld Line 23 ¦ CANCELLED ¦ NA | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.969 | English | train
UPD-01119 | whatsapp | document | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Sir, install unit 2 lighting remains on hold due to material not received. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | resume after clearance | FALSE | 0.943 | English | train
UPD-01357 | site_diary | site_diary | 2026-09-26 | OIL-UNIT2-DEMO | Date 2026-09-26 ¦ Pump House ¦ Today's Install Pump P03 activity has been cancelled. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.924 | English | train
UPD-01628 | plain_text | email | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: Erect Line 23 has been completed at Unit 2. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | receive material | FALSE | 0.934 | English | train
UPD-00790 | ms_project_update | MS_Project | 2026-09-19 | OIL-UNIT2-DEMO | Daily Progress: MS Project update: MEC-T02-001 marked 100% complete. Actual Finish: 2026-09-19. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | completion | COMPLETED | 100 | 2026-09-19 | 2026-09-19 |  | update schedule | FALSE | 0.923 | English | train
UPD-00437 | voice_transcript | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Progress note: Just to update you, no start for install pressure transmitter pt08 today. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.93 | English | train
UPD-01404 | whatsapp | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - Crew resumed Tank T01 foundation completion after clearance. 👍 Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 40 | 2026-09-16 |  |  | update schedule | FALSE | 0.957 | English | train
UPD-00101 | site_diary | mobile | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-17 ¦ Tank Farm ¦ Tank T01 foundation completion will not be executed today. Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.954 | English | train
UPD-00917 | excel_note | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Daily Progress: CIV-R02-002 ¦ Road R02 PCC laying ¦ PARTIAL ¦ NA Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | partial_progress | PARTIAL | 80 | 2026-09-26 |  |  | obtain permit | FALSE | 0.978 | English | train
UPD-00933 | site_diary | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Today: Date 2026-09-24 ¦ Plant Area ¦ Road R02 subgrade preparation completed today. Kindly update the plan. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | planner review | FALSE | 0.927 | English | train
UPD-00444 | voice_transcript | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Okay, today's update is that cannot continue install mcc panel 3 until design revision pending is resolved. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | blockage | BLOCKED | 0 |  |  | design revision pending | mobilise crew | FALSE | 0.965 | English | train
UPD-00095 | site_diary | DPR | 2026-09-14 | OIL-UNIT2-DEMO | Date 2026-09-14 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 has not started yet. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.918 | English | train
UPD-00923 | word_document | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-25 Discipline: Civil Observation: Road R02 subgrade preparation progressing as planned. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 30 | 2026-09-25 |  |  | resume after clearance | FALSE | 0.909 | English | train
UPD-01086 | voice_transcript | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, weld line 23 cancelled for today. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.923 | English | train
UPD-00858 | voice_transcript | email | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: So, basically, install pump p03 remains on hold due to power supply interruption. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | power supply interruption | complete inspection | FALSE | 0.917 | English | train
UPD-00392 | word_document | document | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-09 Discipline: Piping Observation: Crew mobilised and started Install 30-inch header. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 70 | 2026-09-09 |  |  | planner review | FALSE | 0.973 | English | train
UPD-00510 | excel_note | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Progress note: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ IN PROGRESS ¦ NA Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 50 | 2026-09-11 |  |  | continue work | FALSE | 0.96 | English | train
UPD-00484 | word_document | email | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-01 Discipline: Mechanical Observation: Today's Install Pump P03 activity has been cancelled. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | obtain permit | FALSE | 0.97 | English | train
UPD-00077 | plain_text | document | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Install Transformer TR02 ongoing at Substation. FYI. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 80 | 2026-09-08 |  |  | complete inspection | FALSE | 0.936 | English | train
UPD-01585 | word_document | document | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-04 Discipline: Civil Observation: Work on Foundation F15 reinforcement restarted today. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 80 | 2026-09-04 |  |  | receive material | FALSE | 0.981 | English | train
UPD-00146 | pdf_text | document | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 09-09-2026 ¦ INS-PT08-001 ¦ Install Pressure Transmitter PT08 is about 40% complete. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 40 | 2026-09-09 |  |  | update schedule | FALSE | 0.932 | English | train
UPD-01610 | pdf_text | document | 2026-09-01 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ ELE-CBL07-001 ¦ Work on Lay Cable Route 7 restarted today. For information. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 40 | 2026-09-01 |  |  | planner review | FALSE | 0.905 | English | train
UPD-00561 | pdf_text | document | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 19-09-2026 ¦ ELE-TR02-001 ¦ Install Transformer TR02 will not be executed today. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.931 | English | train
UPD-00928 | word_document | email | 2026-09-11 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-11 Discipline: Mechanical Observation: Install Heat Exchanger HX01 is complete as of today. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | resume after clearance | FALSE | 0.906 | English | train
UPD-00152 | ms_project_update | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: INS-JB05-001 progress affected by power supply interruption; expected finish to move. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | continue work | FALSE | 0.966 | English | train
UPD-01796 | site_diary | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | Today: Date 2026-09-10 ¦ Unit 1 ¦ Supervisor confirms Install Pressure Transmitter PT08 completed. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | update schedule | FALSE | 0.981 | English | train
UPD-01652 | email | mobile | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Crew resumed Align Pump P04 after clearance. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 20 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.964 | English | train
UPD-01570 | plain_text | document | 2026-09-04 | OIL-UNIT2-DEMO | No start for Weld Line 24 today. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.973 | English | train
UPD-01743 | excel_note | spreadsheet | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-003 ¦ Foundation F15 concreting ¦ BLOCKED ¦ shortage of 24-inch pipes Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | receive material | FALSE | 0.928 | English | train

## Validation_Updates
record_id | source_modality | source_container | event_date | project_code | raw_input | activity_id | activity_code | canonical_activity | discipline | location | event_type | status | progress_percent | actual_start | actual_finish | delay_reason | expected_next_action | requires_human_review | gold_match_confidence | source_language | dataset_split
UPD-00273 | excel_note | document | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: HSE-001-001 ¦ Complete work-at-height insp. ¦ RESUMED ¦ NA For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | resumption | RESUMED | 50 | 2026-09-26 |  |  | obtain permit | FALSE | 0.935 | English | validation
UPD-00042 | email | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - PIP-L23-003 Dear Team, Hydrotest Line 23 partially complete today. Regards, Site Supervisor For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-28 |  |  | receive material | FALSE | 0.925 | English | validation
UPD-00916 | excel_note | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Unit update: MEC-P03-001 ¦ Install Pump P03 ¦ NOT STARTED ¦ NA Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.94 | English | validation
UPD-00013 | voice_transcript | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: So, basically, no progress on align pump p04 today due to safety clearance pending. Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 30 |  |  | safety clearance pending | mobilise crew | FALSE | 0.91 | English | validation
UPD-00523 | pdf_text | mobile | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 has not started yet. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.935 | English | validation
UPD-00657 | ms_project_update | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Site Update: MS Project note: INS-PT08-001 progress affected by shortage of 24-inch pipes; expected finish to move. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | resume after clearance | FALSE | 0.939 | English | validation
UPD-00844 | word_document | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-11 Discipline: Civil Observation: Started Road R02 PCC laying this morning. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 40 | 2026-09-11 |  |  | complete inspection | FALSE | 0.942 | English | validation
UPD-01375 | excel_note | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - CIV-F15-003 ¦ Foundation F15 concreting ¦ RESUMED ¦ NA FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 30 | 2026-09-23 |  |  | update schedule | FALSE | 0.911 | English | validation
UPD-00407 | whatsapp | document | 2026-09-14 | OIL-UNIT2-DEMO | DPR Update: Terminate Junction Box JB05 done at site. 👍 Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | complete inspection | FALSE | 0.901 | English | validation
UPD-01742 | pdf_text | document | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ CIV-F15-001 ¦ No start for Foundation F15 excavation today. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.954 | English | validation
UPD-01492 | voice_transcript | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that install temperature transmitter t04 is in progress. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-12 |  |  | complete inspection | FALSE | 0.94 | English | validation
UPD-01271 | site_diary | site_diary | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-20 ¦ Unit 2 ¦ Hydrotest Line 23 held up by shortage of 24-inch pipes. Please note. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 10 |  |  | shortage of 24-inch pipes | update schedule | FALSE | 0.96 | English | validation
UPD-01330 | voice_transcript | mobile | 2026-09-11 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that planned work close scaffold inspection actions did not commence. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.963 | English | validation
UPD-00947 | pdf_text | email | 2026-09-24 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 has not started yet. Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.909 | English | validation
UPD-01682 | plain_text | DPR | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Install Temperature Transmitter T04 is delayed because of power supply interruption. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 30 |  |  | power supply interruption | complete inspection | FALSE | 0.934 | English | validation
UPD-01232 | whatsapp | document | 2026-09-28 | OIL-UNIT2-DEMO | Progress note: Sir, planned work erect line 24 did not commence. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.988 | English | validation
UPD-00355 | voice_transcript | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, work is continuing on install transformer tr02. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 60 | 2026-09-08 |  |  | obtain permit | FALSE | 0.932 | English | validation
UPD-00065 | excel_note | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - MEC-P04-001 ¦ Align Pump P04 ¦ IN PROGRESS ¦ NA Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 30 | 2026-09-12 |  |  | resume after clearance | FALSE | 0.972 | English | validation
UPD-01335 | ms_project_update | spreadsheet | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: MS Project update: INS-JB05-001 marked 100% complete. Actual Finish: 2026-09-05. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | planner review | FALSE | 0.969 | English | validation
UPD-00354 | voice_transcript | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that work is continuing on install control valve cv11. Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.99 | English | validation
UPD-00727 | word_document | mobile | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-27 Discipline: Mechanical Observation: Cannot continue Install Tank T02 internals until client approval pending is resolved. FYI. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | blockage | BLOCKED | 0 |  |  | client approval pending | resume after clearance | FALSE | 0.95 | English | validation
UPD-00222 | word_document | document | 2026-09-24 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-24 Discipline: Mechanical Observation: Install Tank T02 internals is about 40% complete. Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 40 | 2026-09-24 |  |  | obtain permit | FALSE | 0.957 | English | validation
UPD-01151 | pdf_text | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 30-09-2026 ¦ HSE-001-001 ¦ Crew is currently working on Complete work-at-height inspection. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-30 |  |  | mobilise crew | FALSE | 0.939 | English | validation
UPD-00223 | email | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header resumed today after scaffold not ready was cleared. Regards, Site Supervisor Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 30 | 2026-09-05 |  |  | obtain permit | FALSE | 0.968 | English | validation
UPD-01485 | site_diary | email | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-13 ¦ Electrical Room ¦ Only part of Install MCC Panel 3 could be completed today. Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | complete inspection | FALSE | 0.945 | English | validation
UPD-00892 | voice_transcript | DPR | 2026-09-05 | OIL-UNIT2-DEMO | DPR Update: Just to update you, install heat exchanger hx01 will not be executed today. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.92 | English | validation
UPD-01306 | word_document | site_diary | 2026-09-16 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-16 Discipline: Instrumentation Observation: Only part of Install Pressure Transmitter PT08 could be completed today. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 20 | 2026-09-16 |  |  | planner review | FALSE | 0.918 | English | validation
UPD-00209 | excel_note | document | 2026-09-20 | OIL-UNIT2-DEMO | Today: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ COMPLETED ¦ NA FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | resume after clearance | FALSE | 0.928 | English | validation
UPD-00256 | pdf_text | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 26-09-2026 ¦ CIV-TK01-001 ¦ Work on Tank T01 foundation completion restarted today. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 50 | 2026-09-26 |  |  | continue work | FALSE | 0.967 | English | validation
UPD-00634 | ms_project_update | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: MS Project update: CIV-F15-002 marked 100% complete. Actual Finish: 2026-09-27. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-27 | 2026-09-27 |  | complete inspection | FALSE | 0.927 | English | validation
UPD-00166 | email | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 is behind plan owing to vendor technician not available. Regards, Site Supervisor Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 60 |  |  | vendor technician not available | continue work | FALSE | 0.989 | English | validation
UPD-01044 | word_document | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-24 Discipline: Mechanical Observation: Align Pump P04 resumed today after client approval pending was cleared. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 60 | 2026-09-24 |  |  | mobilise crew | FALSE | 0.979 | English | validation
UPD-00564 | whatsapp | document | 2026-09-11 | OIL-UNIT2-DEMO | Sir, install control valve cv11 is blocked pending shortage of 24-inch pipes. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | mobilise crew | FALSE | 0.984 | English | validation
UPD-00856 | site_diary | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-24 ¦ Unit 2 ¦ No start for Install Valve V12 today. Please note. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.906 | English | validation
UPD-00705 | email | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - CIV-F15-002 Dear Team, Work on Foundation F15 reinforcement restarted today. Regards, Site Supervisor Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 50 | 2026-09-20 |  |  | complete inspection | FALSE | 0.946 | English | validation
UPD-00679 | pdf_text | document | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 25-09-2026 ¦ CIV-TK01-001 ¦ Tank T01 foundation completion cancelled for today. Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.976 | English | validation
UPD-01087 | pdf_text | email | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ CIV-F15-001 ¦ Foundation F15 excavation started today. Planner action required. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | start | STARTED | 70 | 2026-09-08 |  |  | continue work | FALSE | 0.982 | English | validation
UPD-00060 | ms_project_update | document | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: MS Project update: HSE-002-001 actual start = 2026-09-03; work commenced. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | start | STARTED | 70 | 2026-09-03 |  |  | receive material | FALSE | 0.935 | English | validation
UPD-00377 | email | email | 2026-09-03 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - HSE-002-001 Dear Team, Work on Close scaffold inspection actions restarted today. Regards, Site Supervisor Material expected tomorrow. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 40 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.931 | English | validation
UPD-01462 | site_diary | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-25 ¦ Unit 2 ¦ Today's Foundation F15 reinforcement activity has been cancelled. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.909 | English | validation
UPD-00276 | plain_text | document | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: Partial progress achieved on Tank T01 foundation completion. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 80 | 2026-09-09 |  |  | resume after clearance | FALSE | 0.928 | English | validation
UPD-01707 | pdf_text | email | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 27-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 remains not started. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.984 | English | validation
UPD-00868 | whatsapp | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Progress note: Sir, road r02 subgrade preparation is delayed because of work permit not issued. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 40 |  |  | work permit not issued | receive material | FALSE | 0.908 | English | validation
UPD-00069 | email | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Crew resumed Road R02 PCC laying after clearance. Regards, Site Supervisor Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | resumption | RESUMED | 20 | 2026-09-04 |  |  | resume after clearance | FALSE | 0.922 | English | validation
UPD-01162 | pdf_text | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ PIP-L23-001 ¦ Erect Line 23 is blocked pending access road blocked. Please note. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | access road blocked | update schedule | FALSE | 0.91 | English | validation
UPD-01256 | plain_text | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Lay Cable Route 7 is about 40% complete. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | receive material | FALSE | 0.925 | English | validation
UPD-00646 | pdf_text | email | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 has not started yet. FYI. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.921 | English | validation
UPD-00512 | voice_transcript | spreadsheet | 2026-09-13 | OIL-UNIT2-DEMO | Supervisor update - Okay, today's update is that work on install transformer tr02 restarted today. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 20 | 2026-09-13 |  |  | continue work | FALSE | 0.923 | English | validation
UPD-00648 | excel_note | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ DELAYED ¦ access road blocked Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | delay | DELAYED | 10 |  |  | access road blocked | continue work | FALSE | 0.95 | English | validation
UPD-01339 | email | document | 2026-09-13 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-HX01-001 Dear Team, No start for Install Heat Exchanger HX01 today. Regards, Site Supervisor Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.918 | English | validation
UPD-01781 | email | email | 2026-09-20 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Partial progress achieved on Install Unit 2 lighting. Regards, Site Supervisor | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-20 |  |  | receive material | FALSE | 0.977 | English | validation
UPD-00266 | pdf_text | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 resumed today after crane unavailable was cleared. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 10 | 2026-09-12 |  |  | obtain permit | FALSE | 0.986 | English | validation
UPD-00832 | email | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - INS-JB05-001 Dear Team, Terminate Junction Box JB05 resumed today after drawing approval pending was cleared. Regards, Site Supervisor Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | resumption | RESUMED | 40 | 2026-09-01 |  |  | update schedule | FALSE | 0.973 | English | validation
UPD-00155 | whatsapp | email | 2026-09-27 | OIL-UNIT2-DEMO | Line/area update: cannot continue erect line 24 until insufficient manpower is resolved. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | resume after clearance | FALSE | 0.961 | English | validation
UPD-01138 | site_diary | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Today: Date 2026-09-20 ¦ Unit 2 ¦ Work for Foundation F15 reinforcement is finished. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | continue work | FALSE | 0.903 | English | validation
UPD-00054 | whatsapp | email | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: Sir, weld line 23 is complete as of today. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | update schedule | FALSE | 0.907 | English | validation
UPD-01727 | voice_transcript | mobile | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: Okay, today's update is that erect line 23 is about 25% complete. Kindly update the plan. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-10 |  |  | mobilise crew | FALSE | 0.95 | English | validation
UPD-00830 | ms_project_update | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Today: MS Project note: ELE-LTG02-001 progress affected by inspection clearance pending; expected finish to move. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | continue work | FALSE | 0.917 | English | validation
UPD-00936 | ms_project_update | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: MS Project note: MEC-P04-001 progress affected by inspection clearance pending; expected finish to move. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | inspection clearance pending | continue work | FALSE | 0.917 | English | validation
UPD-00168 | excel_note | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: HSE-001-001 ¦ Complete work-at-height insp. ¦ BLOCKED ¦ valve not available at site For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | planner review | FALSE | 0.966 | English | validation
UPD-01718 | word_document | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-14 Discipline: HSE Observation: Around 50% work completed on Close scaffold inspection actions; balance is ongoing. Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | progress | IN_PROGRESS | 60 | 2026-09-14 |  |  | obtain permit | FALSE | 0.914 | English | validation
UPD-01178 | email | spreadsheet | 2026-09-19 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - INS-T04-001 Dear Team, Started Install Temperature Transmitter T04 this morning. Regards, Site Supervisor For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 80 | 2026-09-19 |  |  | receive material | FALSE | 0.982 | English | validation
UPD-00100 | excel_note | DPR | 2026-09-19 | OIL-UNIT2-DEMO | Progress note: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ RESUMED ¦ NA Kindly update the plan. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 40 | 2026-09-19 |  |  | update schedule | FALSE | 0.903 | English | validation
UPD-01450 | ms_project_update | mobile | 2026-09-04 | OIL-UNIT2-DEMO | MS Project note: CIV-R02-002 progress affected by equipment breakdown; expected finish to move. Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | delay | DELAYED | 80 |  |  | equipment breakdown | obtain permit | FALSE | 0.938 | English | validation
UPD-01726 | plain_text | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: Only part of Install Unit 2 lighting could be completed today. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-14 |  |  | resume after clearance | FALSE | 0.917 | English | validation
UPD-00952 | excel_note | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: MEC-C01-001 ¦ Install Compressor C01 ¦ DELAYED ¦ scaffold not ready | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 30 |  |  | scaffold not ready | complete inspection | FALSE | 0.969 | English | validation
UPD-01176 | pdf_text | document | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ PIP-L24-001 ¦ Erect Line 24 resumed today after valve not available at site was cleared. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | resumption | RESUMED | 60 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.905 | English | validation
UPD-01625 | voice_transcript | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - Okay, today's update is that crew resumed install 30-inch header after clearance. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 40 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.937 | English | validation
UPD-01767 | site_diary | document | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-19 ¦ Unit 1 ¦ Install Pressure Transmitter PT08 partially completed today. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 20 | 2026-09-19 |  |  | planner review | FALSE | 0.963 | English | validation
UPD-01299 | word_document | mobile | 2026-09-10 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-10 Discipline: Civil Observation: Foundation F15 reinforcement started today. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | start | STARTED | 60 | 2026-09-10 |  |  | receive material | FALSE | 0.944 | English | validation
UPD-00725 | excel_note | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: PIP-L24-001 ¦ Erect Line 24 ¦ RESUMED ¦ NA For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | resumption | RESUMED | 20 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.956 | English | validation
UPD-00825 | ms_project_update | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: INS-JB05-001 status = IN PROGRESS. Material expected tomorrow. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-20 |  |  | mobilise crew | FALSE | 0.916 | English | validation
UPD-01468 | voice_transcript | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Daily Progress: Uh, foundation f15 concreting comp. today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | continue work | FALSE | 0.927 | English | validation
UPD-00417 | site_diary | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-29 ¦ Unit 1 ¦ Supervisor confirms Close scaffold inspection actions completed. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | continue work | FALSE | 0.913 | English | validation
UPD-00492 | word_document | document | 2026-09-30 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-30 Discipline: Instrumentation Observation: No start for Install Temperature Transmitter T04 today. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.949 | English | validation
UPD-00032 | word_document | document | 2026-09-25 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-25 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 could not proceed today due to access road blocked. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 50 |  |  | access road blocked | planner review | FALSE | 0.986 | English | validation
UPD-00554 | whatsapp | document | 2026-09-25 | OIL-UNIT2-DEMO | Today: Hi, install valve v12 remains not started. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.919 | English | validation
UPD-00967 | ms_project_update | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: MS Project note: PIP-L24-001 status = NOT STARTED. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.977 | English | validation
UPD-01559 | email | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - ELE-TR02-001 Dear Team, Install Transformer TR02 has been completed at Substation. Regards, Site Supervisor | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | receive material | FALSE | 0.986 | English | validation
UPD-00041 | ms_project_update | spreadsheet | 2026-09-21 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: CIV-F15-001 status = RESUMED. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 40 | 2026-09-21 |  |  | complete inspection | FALSE | 0.983 | English | validation
UPD-00139 | plain_text | document | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Supervisor confirms Weld Line 23 completed. Kindly update the plan. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | continue work | FALSE | 0.943 | English | validation
UPD-01739 | ms_project_update | document | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: MS Project note: ELE-LTG02-001 status = RESUMED. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | resumption | RESUMED | 20 | 2026-09-27 |  |  | continue work | FALSE | 0.921 | English | validation
UPD-01205 | word_document | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-13 Discipline: HSE Observation: Close scaffold inspection actions is in progress. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | progress | IN_PROGRESS | 40 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.915 | English | validation
UPD-01518 | pdf_text | mobile | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 is complete as of today. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-16 | 2026-09-16 |  | obtain permit | FALSE | 0.979 | English | validation
UPD-00889 | email | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting started today. Regards, Site Supervisor Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 40 | 2026-09-05 |  |  | obtain permit | FALSE | 0.945 | English | validation
UPD-00691 | word_document | mobile | 2026-09-30 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-30 Discipline: Instrumentation Observation: Today's Install Pressure Transmitter PT08 activity has been cancelled. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.947 | English | validation
UPD-00464 | ms_project_update | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Site Update: MS Project note: PIP-L23-001 status = CANCELLED. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.97 | English | validation
UPD-00015 | voice_transcript | email | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that supervisor confirms erect line 23 completed. FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | mobilise crew | FALSE | 0.937 | English | validation
UPD-00120 | site_diary | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-09 ¦ Unit 2 ¦ Crew mobilised and started Erect Line 23. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-09 |  |  | mobilise crew | FALSE | 0.983 | English | validation
UPD-01358 | excel_note | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Unit update: CIV-R02-001 ¦ Road R02 subgrade preparation ¦ RESUMED ¦ NA Please note. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | resumption | RESUMED | 40 | 2026-09-08 |  |  | complete inspection | FALSE | 0.984 | English | validation
UPD-01483 | ms_project_update | MS_Project | 2026-09-04 | OIL-UNIT2-DEMO | DPR Update: MS Project note: PIP-L24-002 status = CANCELLED. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.927 | English | validation
UPD-00395 | word_document | mobile | 2026-09-01 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-01 Discipline: Mechanical Observation: Install Heat Exchanger HX01 commenced at Unit 1. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 80 | 2026-09-01 |  |  | continue work | FALSE | 0.973 | English | validation
UPD-01698 | ms_project_update | email | 2026-09-14 | OIL-UNIT2-DEMO | Site Update: MS Project note: ELE-TR02-001 status = NOT STARTED. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.928 | English | validation
UPD-00665 | pdf_text | mobile | 2026-09-08 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ INS-CV11-001 ¦ Planned work Install Control Valve CV11 did not commence. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.936 | English | validation
UPD-00547 | site_diary | email | 2026-09-11 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-11 ¦ Pump House ¦ Work on Install Pump P03 has begun. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 50 | 2026-09-11 |  |  | complete inspection | FALSE | 0.95 | English | validation
UPD-01469 | voice_transcript | DPR | 2026-09-12 | OIL-UNIT2-DEMO | DPR Update: Uh, planned work lay cable route 7 did not commence. FYI. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.919 | English | validation
UPD-01346 | email | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header commenced at Unit 1. Regards, Site Supervisor Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 20 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.933 | English | validation
UPD-00411 | excel_note | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: PIP-L24-003 ¦ Hydrotest Line 24 ¦ PARTIAL ¦ NA Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.974 | English | validation
UPD-01168 | excel_note | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | 10-Sep update: CIV-R02-001 ¦ Road R02 subgrade preparation ¦ COMPLETED ¦ NA | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-01 | 2026-09-01 |  | receive material | FALSE | 0.921 | English | validation
UPD-01507 | word_document | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-26 Discipline: Piping Observation: Partial progress achieved on Erect Line 24. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-26 |  |  | update schedule | FALSE | 0.968 | English | validation
UPD-00252 | voice_transcript | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | So, basically, road r02 pcc laying has been comp. at plant area. Material expected tomorrow. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | complete inspection | FALSE | 0.916 | English | validation
UPD-00002 | plain_text | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Progress note: Road R02 PCC laying held up by QA/QC hold point not cleared. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | delay | DELAYED | 10 |  |  | QA/QC hold point not cleared | resume after clearance | FALSE | 0.973 | English | validation
UPD-01525 | excel_note | spreadsheet | 2026-09-04 | OIL-UNIT2-DEMO | CIV-F15-002 ¦ Foundation F15 reinforcement ¦ IN PROGRESS ¦ NA Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-04 |  |  | receive material | FALSE | 0.92 | English | validation
UPD-00426 | ms_project_update | email | 2026-09-30 | OIL-UNIT2-DEMO | Today: MS Project note: INS-PT08-001 status = RESUMED. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 30 | 2026-09-30 |  |  | complete inspection | FALSE | 0.979 | English | validation
UPD-00074 | word_document | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-21 Discipline: Mechanical Observation: Install Heat Exchanger HX01 started today. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 40 | 2026-09-21 |  |  | obtain permit | FALSE | 0.939 | English | validation
UPD-00755 | plain_text | document | 2026-09-14 | OIL-UNIT2-DEMO | Today: Erect Line 24 progressing as planned. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-14 |  |  | complete inspection | FALSE | 0.944 | English | validation
UPD-01389 | ms_project_update | MS_Project | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: CIV-F15-003 progress affected by client approval pending; expected finish to move. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 10 |  |  | client approval pending | complete inspection | FALSE | 0.952 | English | validation
UPD-00704 | word_document | document | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-06 Discipline: Piping Observation: Weld Line 24 will not be executed today. Please note. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.919 | English | validation
UPD-01603 | word_document | MS_Project | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-25 Discipline: Piping Observation: Hydrotest Line 24 is about 50% complete. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-25 |  |  | planner review | FALSE | 0.905 | English | validation
UPD-01239 | excel_note | document | 2026-09-03 | OIL-UNIT2-DEMO | Today: PIP-L30-001 ¦ Install 30-inch header ¦ BLOCKED ¦ material not received Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | material not received | receive material | FALSE | 0.947 | English | validation
UPD-00651 | word_document | mobile | 2026-09-17 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-17 Discipline: Electrical Observation: Lay Cable Route 7 resumed today after vendor technician not available was cleared. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | resumption | RESUMED | 50 | 2026-09-17 |  |  | continue work | FALSE | 0.902 | English | validation
UPD-01720 | plain_text | document | 2026-09-11 | OIL-UNIT2-DEMO | Complete work-at-height insp. is in progress. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-11 |  |  | resume after clearance | FALSE | 0.99 | English | validation
UPD-00922 | ms_project_update | email | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: MS Project note: PIP-L23-001 progress affected by shortage of 24-inch pipes; expected finish to move. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 20 |  |  | shortage of 24-inch pipes | mobilise crew | FALSE | 0.945 | English | validation
UPD-00978 | site_diary | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Today: Date 2026-09-19 ¦ Unit 2 ¦ Weld Line 23 partially completed today. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 20 | 2026-09-19 |  |  | obtain permit | FALSE | 0.955 | English | validation
UPD-01472 | site_diary | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-26 ¦ Compressor Area ¦ Install Compressor C01 is about 50% complete. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 50 | 2026-09-26 |  |  | resume after clearance | FALSE | 0.936 | English | validation
UPD-01665 | excel_note | mobile | 2026-09-06 | OIL-UNIT2-DEMO | Supervisor update - CIV-F15-001 ¦ Foundation F15 excavation ¦ BLOCKED ¦ welding machine under maintenance For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | welding machine under maintenance | planner review | FALSE | 0.937 | English | validation
UPD-01387 | voice_transcript | document | 2026-09-10 | OIL-UNIT2-DEMO | DPR Update: So, basically, foundation f15 concreting will not be executed today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.923 | English | validation
UPD-01238 | email | document | 2026-09-12 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - HSE-002-001 Dear Team, Cannot continue Close scaffold inspection actions until welding machine under maintenance is resolved. Regards, Site Supervisor FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | welding machine under maintenance | update schedule | FALSE | 0.972 | English | validation
UPD-00699 | email | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - ELE-LTG02-001 Dear Team, Install Unit 2 lighting is complete as of today. Regards, Site Supervisor | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | continue work | FALSE | 0.937 | English | validation
UPD-00702 | whatsapp | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: Planned work Install Pressure Transmitter PT08 did not commence. 👍 Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.948 | English | validation
UPD-00932 | ms_project_update | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: CIV-F15-002 status = NOT STARTED. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.977 | English | validation
UPD-00352 | word_document | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-07 Discipline: Piping Observation: Install 30-inch header is about 10% complete. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 10 | 2026-09-07 |  |  | planner review | FALSE | 0.966 | English | validation
UPD-00046 | pdf_text | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ CIV-F15-002 ¦ Partial progress achieved on Foundation F15 reinforcement. For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.903 | English | validation
UPD-00224 | word_document | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-17 Discipline: Mechanical Observation: Install Tank T02 internals has not started yet. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.968 | English | validation
UPD-00579 | plain_text | mobile | 2026-09-24 | OIL-UNIT2-DEMO | No start for Lay Cable Route 7 today. For information. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.931 | English | validation
UPD-00808 | ms_project_update | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Today: MS Project note: PIP-L24-001 progress affected by welding machine under maintenance; expected finish to move. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | welding machine under maintenance | obtain permit | FALSE | 0.955 | English | validation
UPD-01115 | site_diary | email | 2026-09-13 | OIL-UNIT2-DEMO | Today: Date 2026-09-13 ¦ Unit 1 ¦ Crew resumed Install 30-inch header after clearance. Please note. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | resumption | RESUMED | 50 | 2026-09-13 |  |  | complete inspection | FALSE | 0.921 | English | validation
UPD-00552 | ms_project_update | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Today: MS Project note: INS-PT08-001 status = IN PROGRESS. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | progress | IN_PROGRESS | 50 | 2026-09-13 |  |  | continue work | FALSE | 0.956 | English | validation
UPD-00503 | excel_note | email | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: PIP-L24-002 ¦ Weld Line 24 ¦ DELAYED ¦ rainfall at site For information. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | delay | DELAYED | 70 |  |  | rainfall at site | receive material | FALSE | 0.945 | English | validation
UPD-01640 | whatsapp | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | DPR Update: Hi, no progress on install heat exchanger hx01 today due to crane unavailable. Planner action required. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | delay | DELAYED | 40 |  |  | crane unavailable | complete inspection | FALSE | 0.978 | English | validation
UPD-01108 | word_document | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-28 Discipline: HSE Observation: Close scaffold inspection actions is complete as of today. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | obtain permit | FALSE | 0.927 | English | validation
UPD-00813 | whatsapp | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Install Pressure Transmitter PT08 is about 80% complete. 👍 | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 80 | 2026-09-04 |  |  | update schedule | FALSE | 0.965 | English | validation
UPD-01270 | ms_project_update | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-L23-001 status = IN PROGRESS. Planner action required. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-27 |  |  | complete inspection | FALSE | 0.964 | English | validation
UPD-01201 | ms_project_update | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: CIV-F15-002 status = RESUMED. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 80 | 2026-09-09 |  |  | receive material | FALSE | 0.937 | English | validation
UPD-01078 | whatsapp | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Daily Progress: Sir, today's lay cable route 7 activity has been cancelled. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.977 | English | validation
UPD-00632 | plain_text | document | 2026-09-02 | OIL-UNIT2-DEMO | Site Update: Install Compressor C01 cancelled for today. Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.905 | English | validation
UPD-01017 | word_document | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-09 Discipline: Piping Observation: Execution of Install 30-inch header is blocked by shortage of 24-inch pipes. Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | complete inspection | FALSE | 0.961 | English | validation
UPD-01639 | ms_project_update | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: MS Project note: ELE-MCC03-001 status = RESUMED. Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 40 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.915 | English | validation
UPD-01745 | pdf_text | email | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ CIV-F15-003 ¦ Foundation F15 concreting resumed today after inspection clearance pending was cleared. FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 60 | 2026-09-29 |  |  | update schedule | FALSE | 0.902 | English | validation
UPD-01551 | excel_note | document | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: PIP-L24-001 ¦ Erect Line 24 ¦ STARTED ¦ NA | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-21 |  |  | obtain permit | FALSE | 0.907 | English | validation
UPD-00253 | whatsapp | DPR | 2026-09-29 | OIL-UNIT2-DEMO | DPR Update: Install Unit 2 lighting kicked off today. 👍 Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | start | STARTED | 40 | 2026-09-29 |  |  | planner review | FALSE | 0.942 | English | validation
UPD-00940 | ms_project_update | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | Today: MS Project note: PIP-L24-001 progress affected by crane unavailable; expected finish to move. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | crane unavailable | complete inspection | FALSE | 0.962 | English | validation
UPD-01579 | excel_note | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: PIP-L23-001 ¦ Erect Line 23 ¦ STARTED ¦ NA For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-12 |  |  | receive material | FALSE | 0.944 | English | validation
UPD-01618 | whatsapp | email | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: Sir, install compressor c01 is about 50% complete. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 50 | 2026-09-24 |  |  | update schedule | FALSE | 0.926 | English | validation
UPD-00304 | email | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - INS-CV11-001 Dear Team, Work on Install Control Valve CV11 has begun. Regards, Site Supervisor For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 20 | 2026-09-09 |  |  | complete inspection | FALSE | 0.96 | English | validation
UPD-00876 | pdf_text | DPR | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ HSE-001-001 ¦ Complete work-at-height inspection is about 80% complete. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-06 |  |  | continue work | FALSE | 0.931 | English | validation
UPD-00191 | whatsapp | DPR | 2026-09-19 | OIL-UNIT2-DEMO | 10-Sep update: Hi, erect line 23 started today. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 20 | 2026-09-19 |  |  | obtain permit | FALSE | 0.933 | English | validation
UPD-00007 | plain_text | document | 2026-09-24 | OIL-UNIT2-DEMO | Tank T01 foundation completion partially comp. today. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 60 | 2026-09-24 |  |  | planner review | FALSE | 0.928 | English | validation
UPD-00878 | excel_note | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Today: MEC-P03-001 ¦ Install Pump P03 ¦ IN PROGRESS ¦ NA | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 10 | 2026-09-03 |  |  | resume after clearance | FALSE | 0.951 | English | validation
UPD-00143 | excel_note | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ IN PROGRESS ¦ NA | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 50 | 2026-09-27 |  |  | resume after clearance | FALSE | 0.916 | English | validation
UPD-00802 | whatsapp | email | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Hi, erect line 24 is delayed because of safety clearance pending. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | safety clearance pending | mobilise crew | FALSE | 0.913 | English | validation
UPD-00029 | plain_text | mobile | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: Work is continuing on Align Pump P04. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 70 | 2026-09-01 |  |  | planner review | FALSE | 0.92 | English | validation
UPD-01222 | ms_project_update | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: MS Project note: PIP-V12-001 progress affected by access road blocked; expected finish to move. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | access road blocked | planner review | FALSE | 0.957 | English | validation
UPD-01630 | site_diary | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-30 ¦ Unit 2 ¦ Crew mobilised and started Install Control Valve CV11. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 30 | 2026-09-30 |  |  | complete inspection | FALSE | 0.97 | English | validation
UPD-00700 | voice_transcript | site_diary | 2026-09-04 | OIL-UNIT2-DEMO | Uh, no start for install 30-inch header today. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.908 | English | validation
UPD-00358 | site_diary | mobile | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-23 ¦ Unit 2 ¦ Install Unit 2 lighting is in progress. Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.956 | English | validation
UPD-01423 | excel_note | mobile | 2026-09-17 | OIL-UNIT2-DEMO | DPR Update: PIP-L23-002 ¦ Weld Line 23 ¦ BLOCKED ¦ welding machine under maintenance FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | welding machine under maintenance | obtain permit | FALSE | 0.93 | English | validation
UPD-01433 | plain_text | mobile | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: Partial progress achieved on Install Temperature Transmitter T04. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-08 |  |  | planner review | FALSE | 0.988 | English | validation
UPD-00817 | word_document | MS_Project | 2026-09-15 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-15 Discipline: HSE Observation: Close scaffold inspection actions cancelled for today. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.921 | English | validation
UPD-01416 | whatsapp | site_diary | 2026-09-28 | OIL-UNIT2-DEMO | Unit update: Sir, planned work install unit 2 lighting did not commence. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.931 | English | validation
UPD-01529 | excel_note | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: PIP-L23-003 ¦ Hydrotest Line 23 ¦ DELAYED ¦ power supply interruption FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 80 |  |  | power supply interruption | update schedule | FALSE | 0.937 | English | validation
UPD-00158 | pdf_text | document | 2026-09-16 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ MEC-HX01-001 ¦ Install Heat Exchanger HX01 is complete as of today. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-16 | 2026-09-16 |  | planner review | FALSE | 0.929 | English | validation
UPD-00528 | voice_transcript | document | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that work on install compressor c01 has begun. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | start | STARTED | 30 | 2026-09-29 |  |  | receive material | FALSE | 0.902 | English | validation
UPD-01634 | plain_text | mobile | 2026-09-30 | OIL-UNIT2-DEMO | Daily Progress: Road R02 PCC laying kicked off today. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 10 | 2026-09-30 |  |  | mobilise crew | FALSE | 0.928 | English | validation
UPD-00681 | excel_note | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ RESUMED ¦ NA | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 80 | 2026-09-29 |  |  | planner review | FALSE | 0.947 | English | validation
UPD-01646 | pdf_text | DPR | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 26-09-2026 ¦ CIV-R02-001 ¦ Crew is currently working on Road R02 subgrade preparation. Material expected tomorrow. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 40 | 2026-09-26 |  |  | resume after clearance | FALSE | 0.914 | English | validation
UPD-01008 | ms_project_update | email | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: CIV-F15-003 progress affected by work permit not issued; expected finish to move. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | delay | DELAYED | 60 |  |  | work permit not issued | continue work | FALSE | 0.966 | English | validation
UPD-01415 | whatsapp | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: Line/area update: planned work erect line 24 did not commence. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.977 | English | validation
UPD-00984 | plain_text | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Today: Close scaffold inspection actions has been completed at Unit 1. Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-17 | 2026-09-17 |  | continue work | FALSE | 0.925 | English | validation
UPD-00607 | word_document | mobile | 2026-09-25 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-25 Discipline: Electrical Observation: Install Unit 2 lighting will not be executed today. For information. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.98 | English | validation
UPD-01279 | word_document | document | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-12 Discipline: Electrical Observation: Today's Install Transformer TR02 activity has been cancelled. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.907 | English | validation
UPD-01322 | site_diary | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-01 ¦ Unit 2 ¦ Install Unit 2 lighting is blocked pending inspection clearance pending. Kindly update the plan. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | inspection clearance pending | planner review | FALSE | 0.95 | English | validation
UPD-00287 | excel_note | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: ELE-CBL07-001 ¦ Lay Cable Route 7 ¦ BLOCKED ¦ work permit not issued Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | planner review | FALSE | 0.947 | English | validation
UPD-01321 | whatsapp | spreadsheet | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: Line/area update: crew resumed install pump p03 after clearance. For information. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 20 | 2026-09-01 |  |  | update schedule | FALSE | 0.903 | English | validation
UPD-01645 | ms_project_update | mobile | 2026-09-29 | OIL-UNIT2-DEMO | MS Project update: PIP-L23-002 Actual % Complete = 30% as of 2026-09-29. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-29 |  |  | obtain permit | FALSE | 0.977 | English | validation
UPD-01593 | whatsapp | mobile | 2026-09-05 | OIL-UNIT2-DEMO | Site Update: Line/area update: install pressure transmitter pt08 could not proceed today due to design revision pending. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | delay | DELAYED | 70 |  |  | design revision pending | mobilise crew | FALSE | 0.904 | English | validation
UPD-01139 | plain_text | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Install Pump P03 is blocked pending crane unavailable. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | crane unavailable | resume after clearance | FALSE | 0.919 | English | validation
UPD-01060 | word_document | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-14 Discipline: Instrumentation Observation: Work on Install Control Valve CV11 restarted today. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 20 | 2026-09-14 |  |  | complete inspection | FALSE | 0.95 | English | validation
UPD-01664 | plain_text | spreadsheet | 2026-09-26 | OIL-UNIT2-DEMO | Install Control Valve CV11 held up by equipment breakdown. Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | delay | DELAYED | 70 |  |  | equipment breakdown | complete inspection | FALSE | 0.944 | English | validation
UPD-00242 | voice_transcript | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, today's foundation f15 concreting activity has been cancelled. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.971 | English | validation
UPD-00613 | email | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - ELE-TR02-001 Dear Team, Install Transformer TR02 partially completed today. Regards, Site Supervisor Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | partial_progress | PARTIAL | 50 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.903 | English | validation
UPD-01277 | voice_transcript | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Uh, weld line 23 ongoing at unit 2. For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-07 |  |  | continue work | FALSE | 0.978 | English | validation
UPD-00633 | site_diary | document | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-09 ¦ Unit 2 ¦ Foundation F15 excavation remains on hold due to rainfall at site. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | rainfall at site | mobilise crew | FALSE | 0.916 | English | validation
UPD-00794 | whatsapp | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | Sir, around 50% work completed on align pump p04; balance is ongoing. Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 20 | 2026-09-25 |  |  | continue work | FALSE | 0.981 | English | validation
UPD-01003 | ms_project_update | email | 2026-09-20 | OIL-UNIT2-DEMO | 10-Sep update: MS Project update: MEC-C01-001 marked 100% complete. Actual Finish: 2026-09-20. Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | receive material | FALSE | 0.954 | English | validation
UPD-01535 | plain_text | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: Install Valve V12 resumed today after vendor technician not available was cleared. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | resumption | RESUMED | 20 | 2026-09-14 |  |  | complete inspection | FALSE | 0.917 | English | validation
UPD-00751 | excel_note | document | 2026-09-05 | OIL-UNIT2-DEMO | INS-JB05-001 ¦ Terminate Junction Box JB05 ¦ PARTIAL ¦ NA Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-05 |  |  | complete inspection | FALSE | 0.906 | English | validation
UPD-00959 | plain_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Supervisor update - Close scaffold inspection actions is blocked pending client approval pending. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | client approval pending | receive material | FALSE | 0.904 | English | validation
UPD-01379 | site_diary | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-26 ¦ Substation ¦ Execution of Install Transformer TR02 is blocked by QA/QC hold point not cleared. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | continue work | FALSE | 0.95 | English | validation
UPD-01496 | excel_note | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: CIV-TK01-001 ¦ Tank T01 foundation completion ¦ RESUMED ¦ NA | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 20 | 2026-09-22 |  |  | update schedule | FALSE | 0.966 | English | validation
UPD-00290 | ms_project_update | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: CIV-F15-002 progress affected by safety clearance pending; expected finish to move. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | delay | DELAYED | 80 |  |  | safety clearance pending | complete inspection | FALSE | 0.966 | English | validation
UPD-01308 | site_diary | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Today: Date 2026-09-18 ¦ Compressor Area ¦ Team finished Install Compressor C01. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | update schedule | FALSE | 0.948 | English | validation
UPD-01235 | pdf_text | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 02-09-2026 ¦ PIP-L23-003 ¦ Only part of Hydrotest Line 23 could be completed today. Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-02 |  |  | planner review | FALSE | 0.929 | English | validation
UPD-00840 | ms_project_update | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: MEC-P03-001 progress affected by vendor technician not available; expected finish to move. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 50 |  |  | vendor technician not available | obtain permit | FALSE | 0.975 | English | validation
UPD-00067 | ms_project_update | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Supervisor update - MS Project update: CIV-R02-002 marked 100% complete. Actual Finish: 2026-09-06. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | planner review | FALSE | 0.986 | English | validation
UPD-01714 | excel_note | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: ELE-TR02-001 ¦ Install Transformer TR02 ¦ DELAYED ¦ inspection clearance pending For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | delay | DELAYED | 10 |  |  | inspection clearance pending | receive material | FALSE | 0.951 | English | validation
UPD-00522 | email | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 remains not started. Regards, Site Supervisor Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.978 | English | validation
UPD-01482 | email | document | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 is behind plan owing to design revision pending. Regards, Site Supervisor Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 20 |  |  | design revision pending | complete inspection | FALSE | 0.94 | English | validation
UPD-00438 | ms_project_update | mobile | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: MS Project note: PIP-L23-002 progress affected by access road blocked; expected finish to move. Material expected tomorrow. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | access road blocked | obtain permit | FALSE | 0.931 | English | validation
UPD-00659 | excel_note | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: MEC-T02-001 ¦ Install Tank T02 internals ¦ PARTIAL ¦ NA For information. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 70 | 2026-09-07 |  |  | complete inspection | FALSE | 0.971 | English | validation
UPD-00181 | plain_text | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Terminate Junction Box JB05 is about 75% complete. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-07 |  |  | obtain permit | FALSE | 0.981 | English | validation
UPD-00929 | pdf_text | mobile | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ CIV-TK01-001 ¦ Tank T01 foundation completion has been completed at Tank Farm. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | completion | COMPLETED | 100 | 2026-09-29 | 2026-09-29 |  | complete inspection | FALSE | 0.959 | English | validation
UPD-00602 | pdf_text | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 15-09-2026 ¦ ELE-LTG02-001 ¦ Install Unit 2 lighting will not be executed today. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.905 | English | validation
UPD-00824 | plain_text | document | 2026-09-04 | OIL-UNIT2-DEMO | Today: Planned work Install 30-inch header did not commence. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.95 | English | validation
UPD-00587 | voice_transcript | email | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Uh, started install tank t02 internals this morning. Planner action required. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | start | STARTED | 20 | 2026-09-16 |  |  | obtain permit | FALSE | 0.988 | English | validation
UPD-01516 | pdf_text | email | 2026-09-28 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 started today. Material expected tomorrow. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 70 | 2026-09-28 |  |  | continue work | FALSE | 0.908 | English | validation
UPD-00533 | plain_text | MS_Project | 2026-09-26 | OIL-UNIT2-DEMO | Site Update: Execution of Foundation F15 excavation is blocked by client approval pending. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | complete inspection | FALSE | 0.912 | English | validation
UPD-01602 | ms_project_update | DPR | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: MS Project note: CIV-TK01-001 progress affected by shortage of 24-inch pipes; expected finish to move. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 30 |  |  | shortage of 24-inch pipes | update schedule | FALSE | 0.962 | English | validation
UPD-00345 | pdf_text | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 07-09-2026 ¦ MEC-C01-001 ¦ Around 50% work completed on Install Compressor C01; balance is ongoing. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 30 | 2026-09-07 |  |  | obtain permit | FALSE | 0.945 | English | validation
UPD-00490 | excel_note | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Today: PIP-V12-001 ¦ Install Valve V12 ¦ PARTIAL ¦ NA Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-25 |  |  | obtain permit | FALSE | 0.98 | English | validation
UPD-00211 | ms_project_update | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Daily Progress: MS Project update: HSE-001-001 Actual % Complete = 40% as of 2026-09-13. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.927 | English | validation
UPD-00986 | site_diary | mobile | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-18 ¦ Unit 2 ¦ Complete work-at-height inspection has not started yet. Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.915 | English | validation
UPD-00703 | ms_project_update | spreadsheet | 2026-09-22 | OIL-UNIT2-DEMO | MS Project note: CIV-F15-001 status = IN PROGRESS. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-22 |  |  | receive material | FALSE | 0.957 | English | validation
UPD-01399 | voice_transcript | spreadsheet | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: So, basically, crew is currently working on tank t01 foundation completion. For information. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | progress | IN_PROGRESS | 20 | 2026-09-27 |  |  | continue work | FALSE | 0.952 | English | validation
UPD-00739 | whatsapp | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - Hi, crew mobilised and started install temperature transmitter t04. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 50 | 2026-09-30 |  |  | planner review | FALSE | 0.901 | English | validation
UPD-01376 | word_document | DPR | 2026-09-04 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-04 Discipline: Piping Observation: Weld Line 23 cancelled for today. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.913 | English | validation
UPD-01558 | plain_text | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | Today: Install Control Valve CV11 resumed today after equipment breakdown was cleared. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 10 | 2026-09-06 |  |  | resume after clearance | FALSE | 0.985 | English | validation
UPD-01102 | plain_text | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Install Temperature Transmitter T04 remains on hold due to crane unavailable. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | crane unavailable | resume after clearance | FALSE | 0.909 | English | validation
UPD-00382 | excel_note | document | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - MEC-P04-001 ¦ Align Pump P04 ¦ RESUMED ¦ NA Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 20 | 2026-09-09 |  |  | obtain permit | FALSE | 0.977 | English | validation
UPD-01766 | email | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - CIV-F15-002 Dear Team, Foundation F15 reinforcement has not started yet. Regards, Site Supervisor For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.909 | English | validation
UPD-00894 | pdf_text | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ INS-T04-001 ¦ Work for Install Temperature Transmitter T04 is finished. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | obtain permit | FALSE | 0.908 | English | validation
UPD-01209 | excel_note | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Supervisor update - MEC-P04-001 ¦ Align Pump P04 ¦ PARTIAL ¦ NA | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 25 | 2026-09-27 |  |  | obtain permit | FALSE | 0.964 | English | validation
UPD-00861 | site_diary | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Date 2026-09-14 ¦ Substation ¦ Crew mobilised and started Install Transformer TR02. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 60 | 2026-09-14 |  |  | planner review | FALSE | 0.955 | English | validation
UPD-01007 | excel_note | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: PIP-L23-002 ¦ Weld Line 23 ¦ BLOCKED ¦ client approval pending For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | client approval pending | mobilise crew | FALSE | 0.91 | English | validation
UPD-00977 | plain_text | MS_Project | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: Complete work-at-height inspection remains on hold due to insufficient manpower. Material expected tomorrow. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | mobilise crew | FALSE | 0.904 | English | validation
UPD-00301 | site_diary | email | 2026-09-05 | OIL-UNIT2-DEMO | Today: Date 2026-09-05 ¦ Unit 1 ¦ Work on Close scaffold inspection actions was stopped because drawing approval pending. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 20 |  |  | drawing approval pending | continue work | FALSE | 0.936 | English | validation
UPD-00218 | plain_text | mobile | 2026-09-06 | OIL-UNIT2-DEMO | 10-Sep update: Execution of Install Temperature Transmitter T04 is blocked by valve not available at site. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | planner review | FALSE | 0.956 | English | validation
UPD-00684 | plain_text | document | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Cannot continue Install Control Valve CV11 until equipment breakdown is resolved. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | planner review | FALSE | 0.949 | English | validation
UPD-01051 | voice_transcript | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: So, basically, foundation f15 reinforcement partially completed today. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-23 |  |  | continue work | FALSE | 0.984 | English | validation
UPD-01466 | plain_text | email | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Tank T01 foundation completion is behind plan owing to client approval pending. FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 70 |  |  | client approval pending | complete inspection | FALSE | 0.932 | English | validation
UPD-00207 | pdf_text | document | 2026-09-06 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 06-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 is about 30% complete. Material expected tomorrow. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-06 |  |  | mobilise crew | FALSE | 0.965 | English | validation
UPD-00662 | whatsapp | document | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Sir, work on install control valve cv11 was stopped because welding machine under maintenance. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | delay | DELAYED | 50 |  |  | welding machine under maintenance | receive material | FALSE | 0.962 | English | validation
UPD-00458 | word_document | email | 2026-09-22 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-22 Discipline: HSE Observation: Complete work-at-height inspection ongoing at Unit 2. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-22 |  |  | complete inspection | FALSE | 0.923 | English | validation
UPD-00667 | whatsapp | email | 2026-09-02 | OIL-UNIT2-DEMO | Daily Progress: Crew resumed Install MCC Panel 3 after clearance. 👍 Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | resumption | RESUMED | 40 | 2026-09-02 |  |  | mobilise crew | FALSE | 0.92 | English | validation
UPD-01250 | voice_transcript | MS_Project | 2026-09-14 | OIL-UNIT2-DEMO | DPR Update: So, basically, terminate junction box jb05 is delayed because of insufficient manpower. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | delay | DELAYED | 30 |  |  | insufficient manpower | receive material | FALSE | 0.925 | English | validation
UPD-01140 | pdf_text | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 21-09-2026 ¦ PIP-L30-001 ¦ Only part of Install 30-inch header could be completed today. FYI. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 80 | 2026-09-21 |  |  | continue work | FALSE | 0.943 | English | validation
UPD-01252 | email | mobile | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - MEC-HX01-001 Dear Team, Install Heat Exchanger HX01 started today. Regards, Site Supervisor Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 50 | 2026-09-28 |  |  | planner review | FALSE | 0.908 | English | validation
UPD-00809 | site_diary | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-12 ¦ Unit 2 ¦ No start for Complete work-at-height inspection today. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.908 | English | validation
UPD-01352 | plain_text | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Today: Road R02 subgrade preparation is about 25% complete. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | partial_progress | PARTIAL | 25 | 2026-09-29 |  |  | planner review | FALSE | 0.931 | English | validation
UPD-01312 | whatsapp | document | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: Sir, install control valve cv11 ongoing at unit 2. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-04 |  |  | resume after clearance | FALSE | 0.924 | English | validation
UPD-01662 | word_document | mobile | 2026-09-10 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-10 Discipline: Instrumentation Observation: Terminate Junction Box JB05 is complete as of today. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-10 | 2026-09-10 |  | complete inspection | FALSE | 0.968 | English | validation
UPD-00110 | pdf_text | mobile | 2026-09-20 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 20-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 kicked off today. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 20 | 2026-09-20 |  |  | complete inspection | FALSE | 0.958 | English | validation
UPD-00635 | pdf_text | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ PIP-L23-002 ¦ Weld Line 23 will not be executed today. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.902 | English | validation
UPD-01560 | plain_text | DPR | 2026-09-02 | OIL-UNIT2-DEMO | Site Update: Started Foundation F15 concreting this morning. For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 70 | 2026-09-02 |  |  | resume after clearance | FALSE | 0.98 | English | validation
UPD-00429 | plain_text | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Progress note: Crew resumed Foundation F15 concreting after clearance. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | resumption | RESUMED | 60 | 2026-09-08 |  |  | receive material | FALSE | 0.975 | English | validation
UPD-00412 | site_diary | document | 2026-09-01 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-01 ¦ Unit 2 ¦ Hydrotest Line 23 is in progress. Kindly update the plan. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-01 |  |  | planner review | FALSE | 0.961 | English | validation
UPD-00072 | ms_project_update | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: CIV-F15-001 progress affected by vendor technician not available; expected finish to move. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | vendor technician not available | mobilise crew | FALSE | 0.935 | English | validation
UPD-00562 | whatsapp | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Sir, no start for install transformer tr02 today. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.921 | English | validation
UPD-00488 | voice_transcript | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: Okay, today's update is that work on erect line 23 restarted today. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | resumption | RESUMED | 60 | 2026-09-18 |  |  | receive material | FALSE | 0.966 | English | validation
UPD-01764 | email | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - INS-PT08-001 Dear Team, Install Pressure Transmitter PT08 is in progress. Regards, Site Supervisor Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | progress | IN_PROGRESS | 30 | 2026-09-27 |  |  | obtain permit | FALSE | 0.922 | English | validation
UPD-01691 | plain_text | email | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Team finished Lay Cable Route 7. Please note. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-16 | 2026-09-16 |  | continue work | FALSE | 0.937 | English | validation
UPD-00386 | email | MS_Project | 2026-09-22 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - CIV-F15-003 Dear Team, Around 50% work completed on Foundation F15 concreting; balance is ongoing. Regards, Site Supervisor FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-22 |  |  | planner review | FALSE | 0.934 | English | validation
UPD-01323 | pdf_text | DPR | 2026-09-16 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 16-09-2026 ¦ ELE-MCC03-001 ¦ Install MCC Panel 3 done at site. For information. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-16 | 2026-09-16 |  | planner review | FALSE | 0.925 | English | validation
UPD-01105 | word_document | document | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-09 Discipline: Mechanical Observation: Install Heat Exchanger HX01 has not started yet. Please note. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.981 | English | validation
UPD-01294 | email | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Work for Align Pump P04 is finished. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | update schedule | FALSE | 0.93 | English | validation
UPD-00867 | email | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - CIV-F15-001 Dear Team, Team finished Foundation F15 excavation. Regards, Site Supervisor Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-23 | 2026-09-23 |  | mobilise crew | FALSE | 0.989 | English | validation
UPD-00271 | ms_project_update | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: MS Project update: PIP-L24-001 marked 100% complete. Actual Finish: 2026-09-13. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | mobilise crew | FALSE | 0.987 | English | validation
UPD-00743 | excel_note | MS_Project | 2026-09-05 | OIL-UNIT2-DEMO | Daily Progress: PIP-L24-002 ¦ Weld Line 24 ¦ COMPLETED ¦ NA | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | planner review | FALSE | 0.914 | English | validation
UPD-00724 | pdf_text | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ MEC-P04-001 ¦ Today's Align Pump P04 activity has been cancelled. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.911 | English | validation
UPD-01024 | excel_note | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Supervisor update - HSE-002-001 ¦ Close scaffold insp. actions ¦ COMPLETED ¦ NA Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | planner review | FALSE | 0.933 | English | validation
UPD-00875 | ms_project_update | email | 2026-09-20 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: CIV-R02-001 status = NOT STARTED. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.966 | English | validation
UPD-00758 | whatsapp | mobile | 2026-09-27 | OIL-UNIT2-DEMO | Progress note: Line/area update: install transformer tr02 is blocked pending shortage of 24-inch pipes. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | update schedule | FALSE | 0.937 | English | validation
UPD-00958 | pdf_text | DPR | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ MEC-HX01-001 ¦ Work is continuing on Install Heat Exchanger HX01. FYI. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | progress | IN_PROGRESS | 20 | 2026-09-10 |  |  | resume after clearance | FALSE | 0.919 | English | validation
UPD-00321 | voice_transcript | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Today: Okay, today's update is that hydrotest line 24 has resumed following resolution of the earlier issue. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 70 | 2026-09-12 |  |  | mobilise crew | FALSE | 0.972 | English | validation
UPD-01769 | voice_transcript | document | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - Just to update you, terminate junction box jb05 cancelled for today. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.951 | English | validation
UPD-00086 | ms_project_update | site_diary | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: MS Project update: PIP-L23-002 marked 100% complete. Actual Finish: 2026-09-24. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | receive material | FALSE | 0.918 | English | validation
UPD-01440 | excel_note | email | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: PIP-L24-002 ¦ Weld Line 24 ¦ RESUMED ¦ NA Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 30 | 2026-09-16 |  |  | receive material | FALSE | 0.951 | English | validation
UPD-00971 | whatsapp | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Road R02 subgrade preparation held up by QA/QC hold point not cleared. 👍 | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 70 |  |  | QA/QC hold point not cleared | update schedule | FALSE | 0.948 | English | validation
UPD-01637 | ms_project_update | mobile | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: MEC-P04-001 status = CANCELLED. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.983 | English | validation
UPD-00738 | email | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Install Tank T02 internals kicked off today. Regards, Site Supervisor | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | start | STARTED | 60 | 2026-09-28 |  |  | planner review | FALSE | 0.913 | English | validation

## Test_Updates
record_id | source_modality | source_container | event_date | project_code | raw_input | activity_id | activity_code | canonical_activity | discipline | location | event_type | status | progress_percent | actual_start | actual_finish | delay_reason | expected_next_action | requires_human_review | gold_match_confidence | source_language | dataset_split
UPD-01063 | email | document | 2026-09-25 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header started today. Regards, Site Supervisor Planner action required. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 60 | 2026-09-25 |  |  | resume after clearance | FALSE | 0.975 | English | test
UPD-01420 | email | document | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - PIP-L23-002 Dear Team, Weld Line 23 is behind plan owing to drawing approval pending. Regards, Site Supervisor For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | drawing approval pending | continue work | FALSE | 0.903 | English | test
UPD-01523 | site_diary | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-17 ¦ Compressor Area ¦ Install Compressor C01 could not proceed today due to client approval pending. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 20 |  |  | client approval pending | update schedule | FALSE | 0.951 | English | test
UPD-01056 | site_diary | DPR | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: Date 2026-09-13 ¦ Unit 2 ¦ Work for Foundation F15 concreting is finished. FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | resume after clearance | FALSE | 0.928 | English | test
UPD-00435 | whatsapp | email | 2026-09-21 | OIL-UNIT2-DEMO | DPR Update: Hi, cannot continue tank t01 foundation completion until shortage of 24-inch pipes is resolved. Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | receive material | FALSE | 0.936 | English | test
UPD-01568 | excel_note | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | PIP-L23-003 ¦ Hydrotest Line 23 ¦ RESUMED ¦ NA Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | resumption | RESUMED | 20 | 2026-09-08 |  |  | continue work | FALSE | 0.98 | English | test
UPD-00930 | excel_note | spreadsheet | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - PIP-L24-001 ¦ Erect Line 24 ¦ COMPLETED ¦ NA Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | receive material | FALSE | 0.934 | English | test
UPD-01534 | plain_text | document | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Partial progress achieved on Complete work-at-height inspection. Please note. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-13 |  |  | receive material | FALSE | 0.98 | English | test
UPD-01777 | plain_text | site_diary | 2026-09-30 | OIL-UNIT2-DEMO | Align Pump P04 partially completed today. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 70 | 2026-09-30 |  |  | planner review | FALSE | 0.967 | English | test
UPD-00213 | word_document | document | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-04 Discipline: Civil Observation: Today's Foundation F15 excavation activity has been cancelled. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.965 | English | test
UPD-01793 | excel_note | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Supervisor update - ELE-TR02-001 ¦ Install Transformer TR02 ¦ NOT STARTED ¦ NA Please note. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.977 | English | test
UPD-00231 | email | mobile | 2026-09-28 | OIL-UNIT2-DEMO | 10-Sep update: Subject: Daily Progress Update - HSE-002-001 Dear Team, Crew resumed Close scaffold inspection actions after clearance. Regards, Site Supervisor | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 70 | 2026-09-28 |  |  | mobilise crew | FALSE | 0.95 | English | test
UPD-01760 | plain_text | email | 2026-09-07 | OIL-UNIT2-DEMO | DPR Update: Weld Line 24 is complete as of today. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-07 | 2026-09-07 |  | planner review | FALSE | 0.934 | English | test
UPD-01090 | word_document | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-14 Discipline: Civil Observation: Around 50% work comp. on Road R02 PCC laying; balance is ongoing. Please note. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | progress | IN_PROGRESS | 30 | 2026-09-14 |  |  | complete inspection | FALSE | 0.901 | English | test
UPD-00599 | ms_project_update | document | 2026-09-01 | OIL-UNIT2-DEMO | Today: MS Project note: ELE-CBL07-001 progress affected by work permit not issued; expected finish to move. Kindly update the plan. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | delay | DELAYED | 40 |  |  | work permit not issued | update schedule | FALSE | 0.943 | English | test
UPD-00851 | word_document | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-22 Discipline: Piping Observation: Only part of Erect Line 24 could be completed today. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-22 |  |  | planner review | FALSE | 0.917 | English | test
UPD-01596 | email | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Install Tank T02 internals remains not started. Regards, Site Supervisor Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.967 | English | test
UPD-00048 | site_diary | email | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-29 ¦ Unit 1 ¦ Partial progress achieved on Install Pressure Transmitter PT08. Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 25 | 2026-09-29 |  |  | planner review | FALSE | 0.978 | English | test
UPD-01050 | word_document | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-21 Discipline: Piping Observation: Erect Line 24 will not be executed today. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | mobilise crew | FALSE | 0.903 | English | test
UPD-00772 | pdf_text | site_diary | 2026-09-07 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 07-09-2026 ¦ PIP-L24-003 ¦ Crew resumed Hydrotest Line 24 after clearance. Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 80 | 2026-09-07 |  |  | complete inspection | FALSE | 0.921 | English | test
UPD-01319 | whatsapp | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: Hi, close scaffold insp. actions cancelled for today. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.966 | English | test
UPD-01179 | whatsapp | document | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Line/area update: work on weld line 23 was stopped because client approval pending. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | client approval pending | continue work | FALSE | 0.971 | English | test
UPD-00901 | voice_transcript | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Today: Uh, foundation f15 reinforcement will not be executed today. FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.983 | English | test
UPD-01207 | plain_text | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | Today: Crew is currently working on Terminate Junction Box JB05. Planner action required. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-03 |  |  | receive material | FALSE | 0.934 | English | test
UPD-00017 | word_document | email | 2026-09-01 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-01 Discipline: HSE Observation: Work on Close scaffold inspection actions was stopped because equipment breakdown. Please note. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 70 |  |  | equipment breakdown | planner review | FALSE | 0.932 | English | test
UPD-00677 | email | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - ELE-TR02-001 Dear Team, Install Transformer TR02 resumed today after inspection clearance pending was cleared. Regards, Site Supervisor | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 50 | 2026-09-11 |  |  | obtain permit | FALSE | 0.964 | English | test
UPD-01166 | pdf_text | site_diary | 2026-09-22 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 22-09-2026 ¦ CIV-TK01-001 ¦ Tank T01 foundation completion remains on hold due to inspection clearance pending. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | inspection clearance pending | update schedule | FALSE | 0.96 | English | test
UPD-00296 | ms_project_update | email | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: INS-CV11-001 status = NOT STARTED. Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | planner review | FALSE | 0.905 | English | test
UPD-01009 | plain_text | document | 2026-09-22 | OIL-UNIT2-DEMO | Today: Terminate Junction Box JB05 remains not started. Please note. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.939 | English | test
UPD-01601 | plain_text | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Supervisor update - No start for Close scaffold inspection actions today. Kindly update the plan. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.982 | English | test
UPD-01099 | voice_transcript | site_diary | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: Okay, today's update is that install valve v12 ongoing at unit 2. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-14 |  |  | mobilise crew | FALSE | 0.947 | English | test
UPD-01510 | whatsapp | site_diary | 2026-09-11 | OIL-UNIT2-DEMO | Progress note: Sir, install mcc panel 3 completed today. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | complete inspection | FALSE | 0.908 | English | test
UPD-00810 | voice_transcript | email | 2026-09-29 | OIL-UNIT2-DEMO | Unit update: So, basically, cannot continue weld line 24 until insufficient manpower is resolved. Kindly update the plan. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | resume after clearance | FALSE | 0.909 | English | test
UPD-00378 | plain_text | email | 2026-09-04 | OIL-UNIT2-DEMO | Unit update: Lay Cable Route 7 remains on hold due to design revision pending. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | update schedule | FALSE | 0.979 | English | test
UPD-01253 | word_document | document | 2026-09-21 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-21 Discipline: Civil Observation: Planned work Road R02 subgrade preparation did not commence. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.924 | English | test
UPD-00998 | pdf_text | DPR | 2026-09-23 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ CIV-F15-003 ¦ Foundation F15 concreting cancelled for today. Planner action required. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.902 | English | test
UPD-01438 | excel_note | email | 2026-09-14 | OIL-UNIT2-DEMO | MEC-T02-001 ¦ Install Tank T02 internals ¦ STARTED ¦ NA Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | start | STARTED | 10 | 2026-09-14 |  |  | complete inspection | FALSE | 0.968 | English | test
UPD-00459 | whatsapp | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | Today: Hydrotest Line 23 kicked off today. 👍 Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-09 |  |  | continue work | FALSE | 0.968 | English | test
UPD-00396 | excel_note | document | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: ELE-MCC03-001 ¦ Install MCC Panel 3 ¦ NOT STARTED ¦ NA Kindly update the plan. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.986 | English | test
UPD-00410 | excel_note | mobile | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: MEC-P03-001 ¦ Install Pump P03 ¦ BLOCKED ¦ valve not available at site Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | valve not available at site | update schedule | FALSE | 0.961 | English | test
UPD-00261 | excel_note | site_diary | 2026-09-09 | OIL-UNIT2-DEMO | PIP-V12-001 ¦ Install Valve V12 ¦ NOT STARTED ¦ NA Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.983 | English | test
UPD-00200 | pdf_text | DPR | 2026-09-11 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 11-09-2026 ¦ CIV-R02-001 ¦ Team finished Road R02 subgrade preparation. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-11 | 2026-09-11 |  | mobilise crew | FALSE | 0.949 | English | test
UPD-00608 | plain_text | document | 2026-09-04 | OIL-UNIT2-DEMO | Terminate Junction Box JB05 has been completed at Unit 2. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-04 | 2026-09-04 |  | resume after clearance | FALSE | 0.907 | English | test
UPD-00160 | word_document | document | 2026-09-03 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-03 Discipline: Instrumentation Observation: Crew resumed Install Control Valve CV11 after clearance. For information. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | resumption | RESUMED | 60 | 2026-09-03 |  |  | mobilise crew | FALSE | 0.963 | English | test
UPD-01595 | email | site_diary | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 is complete as of today. Regards, Site Supervisor For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-08 | 2026-09-08 |  | planner review | FALSE | 0.925 | English | test
UPD-00670 | site_diary | mobile | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-23 ¦ Unit 2 ¦ Erect Line 24 will not be executed today. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.918 | English | test
UPD-01174 | ms_project_update | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Daily Progress: MS Project note: ELE-MCC03-001 status = IN PROGRESS. Planner action required. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | progress | IN_PROGRESS | 20 | 2026-09-14 |  |  | planner review | FALSE | 0.944 | English | test
UPD-01457 | excel_note | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Daily Progress: PIP-L24-001 ¦ Erect Line 24 ¦ COMPLETED ¦ NA For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | complete inspection | FALSE | 0.938 | English | test
UPD-00363 | whatsapp | DPR | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Line/area update: no start for install temperature transmitter t04 today. Material expected tomorrow. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.942 | English | test
UPD-00059 | whatsapp | site_diary | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: Line/area update: install temperature transmitter t04 remains not started. Planner action required. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.904 | English | test
UPD-01054 | plain_text | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Progress note: Planned work Road R02 PCC laying did not commence. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.974 | English | test
UPD-01751 | whatsapp | document | 2026-09-19 | OIL-UNIT2-DEMO | DPR Update: Hi, tank t01 foundation completion has resumed following resolution of the earlier issue. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | resumption | RESUMED | 40 | 2026-09-19 |  |  | resume after clearance | FALSE | 0.917 | English | test
UPD-01386 | site_diary | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-20 ¦ Plant Area ¦ Road R02 subgrade preparation kicked off today. FYI. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 60 | 2026-09-20 |  |  | receive material | FALSE | 0.93 | English | test
UPD-00767 | site_diary | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Date 2026-09-18 ¦ Unit 2 ¦ Erect Line 24 completed today. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | update schedule | FALSE | 0.904 | English | test
UPD-00243 | email | mobile | 2026-09-02 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - CIV-F15-003 Dear Team, Foundation F15 concreting done at site. Regards, Site Supervisor For information. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | receive material | FALSE | 0.901 | English | test
UPD-01273 | whatsapp | DPR | 2026-09-16 | OIL-UNIT2-DEMO | 10-Sep update: Sir, today's install tank t02 internals activity has been cancelled. Material expected tomorrow. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | complete inspection | FALSE | 0.964 | English | test
UPD-00135 | plain_text | spreadsheet | 2026-09-02 | OIL-UNIT2-DEMO | Today: Started Road R02 subgrade preparation this morning. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | start | STARTED | 50 | 2026-09-02 |  |  | mobilise crew | FALSE | 0.911 | English | test
UPD-00201 | word_document | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-20 Discipline: Civil Observation: Foundation F15 reinforcement cancelled for today. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.968 | English | test
UPD-01569 | ms_project_update | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Today: MS Project update: PIP-V12-001 actual start = 2026-09-29; work commenced. Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 30 | 2026-09-29 |  |  | update schedule | FALSE | 0.954 | English | test
UPD-00640 | ms_project_update | document | 2026-09-02 | OIL-UNIT2-DEMO | MS Project note: INS-T04-001 status = IN PROGRESS. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 80 | 2026-09-02 |  |  | obtain permit | FALSE | 0.927 | English | test
UPD-01369 | email | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - MEC-C01-001 Dear Team, Install Compressor C01 has been completed at Compressor Area. Regards, Site Supervisor | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | mobilise crew | FALSE | 0.973 | English | test
UPD-00179 | word_document | mobile | 2026-09-15 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-15 Discipline: Civil Observation: Foundation F15 excavation cancelled for today. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.956 | English | test
UPD-00581 | site_diary | mobile | 2026-09-23 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-23 ¦ Tank Farm ¦ Tank T01 foundation completion is about 40% complete. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 40 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.961 | English | test
UPD-00742 | email | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - CIV-R02-002 Dear Team, Road R02 PCC laying cancelled for today. Regards, Site Supervisor Planner action required. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.941 | English | test
UPD-01430 | voice_transcript | DPR | 2026-09-02 | OIL-UNIT2-DEMO | 10-Sep update: Uh, only part of install compressor c01 could be completed today. Please note. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 90 | 2026-09-02 |  |  | resume after clearance | FALSE | 0.914 | English | test
UPD-01373 | pdf_text | MS_Project | 2026-09-01 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 01-09-2026 ¦ MEC-P03-001 ¦ Install Pump P03 partially completed today. Please note. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | partial_progress | PARTIAL | 40 | 2026-09-01 |  |  | update schedule | FALSE | 0.961 | English | test
UPD-00806 | excel_note | document | 2026-09-24 | OIL-UNIT2-DEMO | DPR Update: HSE-002-001 ¦ Close scaffold inspection actions ¦ BLOCKED ¦ vendor technician not available Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | blockage | BLOCKED | 0 |  |  | vendor technician not available | planner review | FALSE | 0.914 | English | test
UPD-01651 | site_diary | MS_Project | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-04 ¦ Unit 1 ¦ Install 30-inch header is complete as of today. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-04 | 2026-09-04 |  | update schedule | FALSE | 0.938 | English | test
UPD-00797 | site_diary | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-07 ¦ Unit 2 ¦ Partial progress achieved on Install Unit 2 lighting. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-07 |  |  | continue work | FALSE | 0.914 | English | test
UPD-00660 | site_diary | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-15 ¦ Unit 2 ¦ Started Erect Line 23 this morning. Material expected tomorrow. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-15 |  |  | obtain permit | FALSE | 0.938 | English | test
UPD-00919 | email | spreadsheet | 2026-09-20 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - MEC-T02-001 Dear Team, Install Tank T02 internals will not be executed today. Regards, Site Supervisor For information. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.902 | English | test
UPD-00833 | site_diary | document | 2026-09-02 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-02 ¦ Electrical Room ¦ Install MCC Panel 3 cancelled for today. Material expected tomorrow. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | cancellation | CANCELLED | 0 |  |  |  | resume after clearance | FALSE | 0.989 | English | test
UPD-00237 | word_document | mobile | 2026-09-02 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-02 Discipline: Instrumentation Observation: Supervisor confirms Install Pressure Transmitter PT08 completed. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | completion | COMPLETED | 100 | 2026-09-02 | 2026-09-02 |  | receive material | FALSE | 0.985 | English | test
UPD-01647 | whatsapp | site_diary | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Hi, work on install 30-inch header has begun. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | start | STARTED | 50 | 2026-09-12 |  |  | complete inspection | FALSE | 0.927 | English | test
UPD-01425 | pdf_text | email | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ CIV-R02-001 ¦ Road R02 subgrade preparation has been completed at Plant Area. Kindly update the plan. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | receive material | FALSE | 0.921 | English | test
UPD-01012 | plain_text | DPR | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Supervisor confirms Install Unit 2 lighting completed. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | mobilise crew | FALSE | 0.932 | English | test
UPD-00592 | excel_note | site_diary | 2026-09-01 | OIL-UNIT2-DEMO | Today: MEC-P04-001 ¦ Align Pump P04 ¦ RESUMED ¦ NA FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | resumption | RESUMED | 10 | 2026-09-01 |  |  | planner review | FALSE | 0.935 | English | test
UPD-00709 | whatsapp | DPR | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: Hi, install transformer tr02 is in progress. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | progress | IN_PROGRESS | 30 | 2026-09-23 |  |  | receive material | FALSE | 0.961 | English | test
UPD-01451 | plain_text | spreadsheet | 2026-09-30 | OIL-UNIT2-DEMO | Daily Progress: Install Unit 2 lighting is blocked pending drawing approval pending. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | drawing approval pending | update schedule | FALSE | 0.9 | English | test
UPD-01539 | plain_text | MS_Project | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Install Transformer TR02 has resumed following resolution of the earlier issue. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 50 | 2026-09-12 |  |  | continue work | FALSE | 0.952 | English | test
UPD-00033 | voice_transcript | DPR | 2026-09-09 | OIL-UNIT2-DEMO | 10-Sep update: Okay, today's update is that started install control valve cv11 this morning. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | start | STARTED | 50 | 2026-09-09 |  |  | complete inspection | FALSE | 0.912 | English | test
UPD-00282 | site_diary | document | 2026-09-30 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-30 ¦ Unit 2 ¦ No start for Weld Line 23 today. Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.925 | English | test
UPD-00673 | excel_note | document | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: PIP-L23-003 ¦ Hydrotest Line 23 ¦ COMPLETED ¦ NA Material expected tomorrow. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-22 | 2026-09-22 |  | obtain permit | FALSE | 0.932 | English | test
UPD-01583 | voice_transcript | document | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, crew is currently working on install compressor c01. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 60 | 2026-09-09 |  |  | planner review | FALSE | 0.901 | English | test
UPD-00872 | voice_transcript | document | 2026-09-26 | OIL-UNIT2-DEMO | Daily Progress: Uh, started foundation f15 concreting this morning. FYI. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | start | STARTED | 70 | 2026-09-26 |  |  | planner review | FALSE | 0.934 | English | test
UPD-01133 | site_diary | spreadsheet | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-17 ¦ Unit 1 ¦ Close scaffold inspection actions resumed today after welding machine under maintenance was cleared. For information. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 50 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.978 | English | test
UPD-01575 | word_document | email | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-18 Discipline: Piping Observation: Install 30-inch header ongoing at Unit 1. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | progress | IN_PROGRESS | 70 | 2026-09-18 |  |  | complete inspection | FALSE | 0.948 | English | test
UPD-00306 | excel_note | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Today: PIP-V12-001 ¦ Install Valve V12 ¦ STARTED ¦ NA Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 50 | 2026-09-21 |  |  | continue work | FALSE | 0.943 | English | test
UPD-00140 | excel_note | mobile | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: MEC-P04-001 ¦ Align Pump P04 ¦ IN PROGRESS ¦ NA | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 40 | 2026-09-23 |  |  | continue work | FALSE | 0.982 | English | test
UPD-01785 | excel_note | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - PIP-V12-001 ¦ Install Valve V12 ¦ COMPLETED ¦ NA Planner action required. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | update schedule | FALSE | 0.965 | English | test
UPD-01069 | voice_transcript | document | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: Okay, today's update is that only part of foundation f15 concreting could be completed today. Kindly update the plan. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | partial_progress | PARTIAL | 75 | 2026-09-26 |  |  | obtain permit | FALSE | 0.955 | English | test
UPD-00948 | voice_transcript | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: So, basically, install pump p03 resumed today after access road blocked was cleared. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 20 | 2026-09-23 |  |  | planner review | FALSE | 0.934 | English | test
UPD-00690 | word_document | document | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-08 Discipline: Civil Observation: Tank T01 foundation completion has not started yet. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.96 | English | test
UPD-01041 | excel_note | mobile | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ BLOCKED ¦ design revision pending For information. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | receive material | FALSE | 0.963 | English | test
UPD-00880 | email | MS_Project | 2026-09-28 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Work is continuing on Hydrotest Line 24. Regards, Site Supervisor FYI. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-28 |  |  | complete inspection | FALSE | 0.926 | English | test
UPD-00241 | ms_project_update | DPR | 2026-09-27 | OIL-UNIT2-DEMO | Unit update: MS Project update: CIV-F15-001 Actual % Complete = 30% as of 2026-09-27. Kindly update the plan. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-27 |  |  | receive material | FALSE | 0.918 | English | test
UPD-01326 | pdf_text | mobile | 2026-09-28 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ MEC-P04-001 ¦ Align Pump P04 is blocked pending client approval pending. Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | client approval pending | resume after clearance | FALSE | 0.909 | English | test
UPD-00788 | pdf_text | MS_Project | 2026-09-10 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 10-09-2026 ¦ INS-PT08-001 ¦ Install Pressure Transmitter PT08 resumed today after crane unavailable was cleared. Planner action required. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 80 | 2026-09-10 |  |  | complete inspection | FALSE | 0.976 | English | test
UPD-01185 | ms_project_update | email | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: MS Project note: CIV-R02-002 progress affected by QA/QC hold point not cleared; expected finish to move. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | resume after clearance | FALSE | 0.935 | English | test
UPD-00515 | ms_project_update | site_diary | 2026-09-03 | OIL-UNIT2-DEMO | Today: MS Project note: MEC-C01-001 status = IN PROGRESS. FYI. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | progress | IN_PROGRESS | 30 | 2026-09-03 |  |  | continue work | FALSE | 0.943 | English | test
UPD-00586 | email | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - INS-T04-001 Dear Team, Install Temperature Transmitter T04 ongoing at Unit 2. Regards, Site Supervisor For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-30 |  |  | resume after clearance | FALSE | 0.926 | English | test
UPD-00915 | voice_transcript | document | 2026-09-10 | OIL-UNIT2-DEMO | Daily Progress: Uh, install pressure transmitter pt08 cancelled for today. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.967 | English | test
UPD-00921 | word_document | spreadsheet | 2026-09-14 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-14 Discipline: Mechanical Observation: Install Heat Exchanger HX01 done at site. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | obtain permit | FALSE | 0.951 | English | test
UPD-00116 | ms_project_update | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-F15-002 status = IN PROGRESS. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-13 |  |  | mobilise crew | FALSE | 0.987 | English | test
UPD-00230 | whatsapp | DPR | 2026-09-12 | OIL-UNIT2-DEMO | Daily Progress: Line/area update: terminate junction box jb05 is complete as of today. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-12 | 2026-09-12 |  | planner review | FALSE | 0.938 | English | test
UPD-01398 | word_document | mobile | 2026-09-07 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-07 Discipline: Piping Observation: Install 30-inch header partially completed today. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | partial_progress | PARTIAL | 75 | 2026-09-07 |  |  | complete inspection | FALSE | 0.981 | English | test
UPD-01096 | pdf_text | spreadsheet | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ INS-PT08-001 ¦ Execution of Install Pressure Transmitter PT08 is blocked by material not received. Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | material not received | complete inspection | FALSE | 0.933 | English | test
UPD-01432 | plain_text | mobile | 2026-09-26 | OIL-UNIT2-DEMO | DPR Update: Crew is currently working on Install Pressure Transmitter PT08. FYI. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | progress | IN_PROGRESS | 70 | 2026-09-26 |  |  | mobilise crew | FALSE | 0.968 | English | test
UPD-01377 | word_document | mobile | 2026-09-19 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-19 Discipline: Piping Observation: Hydrotest Line 23 progressing as planned. Planner action required. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-19 |  |  | receive material | FALSE | 0.925 | English | test
UPD-01643 | excel_note | document | 2026-09-26 | OIL-UNIT2-DEMO | Today: PIP-L24-001 ¦ Erect Line 24 ¦ BLOCKED ¦ drawing approval pending For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | drawing approval pending | obtain permit | FALSE | 0.958 | English | test
UPD-00855 | whatsapp | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | Unit update: Hi, foundation f15 reinforcement remains on hold due to insufficient manpower. FYI. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | update schedule | FALSE | 0.936 | English | test
UPD-00796 | excel_note | spreadsheet | 2026-09-23 | OIL-UNIT2-DEMO | Site Update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ PARTIAL ¦ NA Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | partial_progress | PARTIAL | 25 | 2026-09-23 |  |  | receive material | FALSE | 0.909 | English | test
UPD-00935 | pdf_text | mobile | 2026-09-13 | OIL-UNIT2-DEMO | DAILY PROGRESS REPORT Project: OIL Unit Expansion 13-09-2026 ¦ MEC-P04-001 ¦ Partial progress achieved on Align Pump P04. Kindly update the plan. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | partial_progress | PARTIAL | 90 | 2026-09-13 |  |  | planner review | FALSE | 0.968 | English | test
UPD-01000 | whatsapp | email | 2026-09-30 | OIL-UNIT2-DEMO | Progress note: Hi, work on install temperature transmitter t04 restarted today. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 60 | 2026-09-30 |  |  | continue work | FALSE | 0.922 | English | test
UPD-00650 | word_document | email | 2026-09-05 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-05 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 partially completed today. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 50 | 2026-09-05 |  |  | mobilise crew | FALSE | 0.903 | English | test
UPD-00047 | voice_transcript | document | 2026-09-16 | OIL-UNIT2-DEMO | Today: Okay, today's update is that only part of terminate junction box jb05 could be completed today. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 70 | 2026-09-16 |  |  | obtain permit | FALSE | 0.902 | English | test
UPD-01180 | voice_transcript | site_diary | 2026-09-26 | OIL-UNIT2-DEMO | Progress note: So, basically, close scaffold inspection actions done at site. Planner action required. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | completion | COMPLETED | 100 | 2026-09-26 | 2026-09-26 |  | resume after clearance | FALSE | 0.961 | English | test
UPD-00272 | word_document | DPR | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-08 Discipline: Piping Observation: Erect Line 23 is delayed bcoz of drawing approval pending. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | delay | DELAYED | 30 |  |  | drawing approval pending | update schedule | FALSE | 0.944 | English | test
UPD-00779 | ms_project_update | email | 2026-09-05 | OIL-UNIT2-DEMO | Supervisor update - MS Project update: ELE-LTG02-001 marked 100% complete. Actual Finish: 2026-09-05. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-05 | 2026-09-05 |  | resume after clearance | FALSE | 0.928 | English | test
UPD-01418 | whatsapp | DPR | 2026-09-17 | OIL-UNIT2-DEMO | Progress note: Line/area update: execution of install control valve cv11 is blocked by power supply interruption. Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | power supply interruption | update schedule | FALSE | 0.97 | English | test
UPD-00408 | plain_text | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Complete work-at-height inspection started today. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | start | STARTED | 80 | 2026-09-09 |  |  | obtain permit | FALSE | 0.942 | English | test
UPD-00610 | pdf_text | email | 2026-09-03 | OIL-UNIT2-DEMO | 10-Sep update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 03-09-2026 ¦ INS-PT08-001 ¦ Crew mobilised and started Install Pressure Transmitter PT08. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | start | STARTED | 80 | 2026-09-03 |  |  | planner review | FALSE | 0.913 | English | test
UPD-00364 | excel_note | document | 2026-09-05 | OIL-UNIT2-DEMO | Today: CIV-TK01-001 ¦ Tank T01 foundation completion ¦ DELAYED ¦ crane unavailable Kindly update the plan. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 60 |  |  | crane unavailable | update schedule | FALSE | 0.969 | English | test
UPD-00818 | whatsapp | document | 2026-09-16 | OIL-UNIT2-DEMO | Daily Progress: Hi, weld line 24 is about 90% complete. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-16 |  |  | receive material | FALSE | 0.919 | English | test
UPD-01243 | excel_note | document | 2026-09-15 | OIL-UNIT2-DEMO | Supervisor update - INS-CV11-001 ¦ Install Control Valve CV11 ¦ PARTIAL ¦ NA Planner action required. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-15 |  |  | update schedule | FALSE | 0.919 | English | test
UPD-00803 | plain_text | MS_Project | 2026-09-29 | OIL-UNIT2-DEMO | Supervisor update - Erect Line 23 progressing as planned. FYI. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-29 |  |  | update schedule | FALSE | 0.948 | English | test
UPD-00931 | pdf_text | DPR | 2026-09-05 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 05-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 is delayed because of late material inspection. For information. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | late material inspection | update schedule | FALSE | 0.972 | English | test
UPD-00807 | ms_project_update | site_diary | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: CIV-F15-003 status = IN PROGRESS. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-25 |  |  | obtain permit | FALSE | 0.934 | English | test
UPD-00885 | ms_project_update | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | Today: MS Project update: CIV-F15-001 marked 100% complete. Actual Finish: 2026-09-06. Material expected tomorrow. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | complete inspection | FALSE | 0.912 | English | test
UPD-00430 | site_diary | MS_Project | 2026-09-09 | OIL-UNIT2-DEMO | Unit update: Date 2026-09-09 ¦ Unit 1 ¦ Close scaffold inspection actions is about 70% complete. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | partial_progress | PARTIAL | 70 | 2026-09-09 |  |  | receive material | FALSE | 0.968 | English | test
UPD-00401 | voice_transcript | document | 2026-09-10 | OIL-UNIT2-DEMO | Okay, today's update is that install 30-inch header is behind plan owing to client approval pending. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 40 |  |  | client approval pending | mobilise crew | FALSE | 0.948 | English | test
UPD-00859 | site_diary | mobile | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-25 ¦ Unit 2 ¦ Complete work-at-height inspection progressing as planned. For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-25 |  |  | obtain permit | FALSE | 0.971 | English | test
UPD-00765 | voice_transcript | mobile | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Okay, today's update is that install pump p03 held up by crane unavailable. FYI. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | delay | DELAYED | 10 |  |  | crane unavailable | receive material | FALSE | 0.956 | English | test
UPD-01064 | site_diary | site_diary | 2026-09-21 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-21 ¦ Unit 2 ¦ Crew resumed Complete work-at-height inspection after clearance. Planner action required. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | resumption | RESUMED | 80 | 2026-09-21 |  |  | mobilise crew | FALSE | 0.951 | English | test
UPD-00828 | ms_project_update | DPR | 2026-09-14 | OIL-UNIT2-DEMO | Progress note: MS Project update: MEC-P04-001 marked 100% complete. Actual Finish: 2026-09-14. For information. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-14 | 2026-09-14 |  | planner review | FALSE | 0.985 | English | test
UPD-00860 | voice_transcript | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Uh, weld line 24 done at site. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | update schedule | FALSE | 0.908 | English | test
UPD-00111 | plain_text | mobile | 2026-09-26 | OIL-UNIT2-DEMO | Supervisor update - Crew is currently working on Foundation F15 reinforcement. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 60 | 2026-09-26 |  |  | planner review | FALSE | 0.927 | English | test
UPD-00315 | site_diary | site_diary | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-13 ¦ Unit 2 ¦ Erect Line 24 started today. FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | start | STARTED | 70 | 2026-09-13 |  |  | update schedule | FALSE | 0.906 | English | test
UPD-01150 | email | spreadsheet | 2026-09-08 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - INS-PT08-001 Dear Team, Install Pressure Transmitter PT08 has resumed following resolution of the earlier issue. Regards, Site Supervisor For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | resumption | RESUMED | 20 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.929 | English | test
UPD-00866 | plain_text | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | Site Update: Install Unit 2 lighting held up by welding machine under maintenance. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 60 |  |  | welding machine under maintenance | mobilise crew | FALSE | 0.973 | English | test
UPD-01132 | voice_transcript | mobile | 2026-09-14 | OIL-UNIT2-DEMO | Supervisor update - So, basically, partial progress achieved on install tank t02 internals. Kindly update the plan. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | partial_progress | PARTIAL | 10 | 2026-09-14 |  |  | complete inspection | FALSE | 0.945 | English | test
UPD-01218 | pdf_text | document | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ INS-PT08-001 ¦ Install Pressure Transmitter PT08 partially completed today. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 20 | 2026-09-28 |  |  | receive material | FALSE | 0.951 | English | test
UPD-01276 | voice_transcript | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Today: Okay, today's update is that foundation f15 excavation kicked off today. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | start | STARTED | 30 | 2026-09-25 |  |  | obtain permit | FALSE | 0.944 | English | test
UPD-01046 | voice_transcript | DPR | 2026-09-03 | OIL-UNIT2-DEMO | DPR Update: So, basically, foundation f15 excavation progressing as planned. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-03 |  |  | receive material | FALSE | 0.949 | English | test
UPD-01470 | ms_project_update | document | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: ELE-LTG02-001 progress affected by QA/QC hold point not cleared; expected finish to move. Please note. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | update schedule | FALSE | 0.9 | English | test
UPD-01378 | whatsapp | mobile | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: Sir, crew resumed install transformer tr02 after clearance. Material expected tomorrow. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | resumption | RESUMED | 30 | 2026-09-24 |  |  | obtain permit | FALSE | 0.94 | English | test
UPD-00970 | excel_note | document | 2026-09-24 | OIL-UNIT2-DEMO | 10-Sep update: CIV-R02-002 ¦ Road R02 PCC laying ¦ STARTED ¦ NA FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | start | STARTED | 70 | 2026-09-24 |  |  | complete inspection | FALSE | 0.924 | English | test
UPD-01194 | site_diary | email | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-07 ¦ Unit 2 ¦ Weld Line 24 is in progress. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-07 |  |  | mobilise crew | FALSE | 0.919 | English | test
UPD-00300 | excel_note | document | 2026-09-22 | OIL-UNIT2-DEMO | Site Update: INS-PT08-001 ¦ Install Pressure Transmitter PT08 ¦ PARTIAL ¦ NA Material expected tomorrow. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 50 | 2026-09-22 |  |  | obtain permit | FALSE | 0.966 | English | test
UPD-01148 | word_document | email | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Daily Site Report Date: 2026-09-23 Discipline: Civil Observation: Tank T01 foundation completion remains on hold due to QA/QC hold point not cleared. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | complete inspection | FALSE | 0.974 | English | test
UPD-00257 | word_document | mobile | 2026-09-03 | OIL-UNIT2-DEMO | Unit update: Daily Site Report Date: 2026-09-03 Discipline: Piping Observation: Erect Line 24 could not proceed today due to vendor technician not available. Material expected tomorrow. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | delay | DELAYED | 40 |  |  | vendor technician not available | complete inspection | FALSE | 0.923 | English | test
UPD-01261 | site_diary | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-18 ¦ Unit 2 ¦ Lay Cable Route 7 completed today. Material expected tomorrow. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | update schedule | FALSE | 0.986 | English | test
UPD-00983 | ms_project_update | email | 2026-09-25 | OIL-UNIT2-DEMO | Progress note: MS Project note: CIV-R02-001 progress affected by drawing approval pending; expected finish to move. Planner action required. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | delay | DELAYED | 60 |  |  | drawing approval pending | mobilise crew | FALSE | 0.923 | English | test
UPD-01293 | pdf_text | DPR | 2026-09-08 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 08-09-2026 ¦ MEC-P04-001 ¦ Align Pump P04 could not proceed today due to client approval pending. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | delay | DELAYED | 40 |  |  | client approval pending | continue work | FALSE | 0.967 | English | test
UPD-01538 | site_diary | DPR | 2026-09-20 | OIL-UNIT2-DEMO | Date 2026-09-20 ¦ Unit 2 ¦ Install Unit 2 lighting is in progress. Planner action required. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-20 |  |  | mobilise crew | FALSE | 0.909 | English | test
UPD-00845 | word_document | mobile | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-23 Discipline: Civil Observation: Road R02 subgrade preparation ongoing at Plant Area. For information. | 4 | CIV-R02-001 | Road R02 subgrade preparation | Civil | Plant Area | progress | IN_PROGRESS | 70 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.953 | English | test
UPD-01061 | ms_project_update | mobile | 2026-09-13 | OIL-UNIT2-DEMO | Progress note: MS Project update: CIV-F15-001 actual start = 2026-09-13; work commenced. FYI. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | start | STARTED | 30 | 2026-09-13 |  |  | obtain permit | FALSE | 0.957 | English | test
UPD-01721 | pdf_text | document | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 23-09-2026 ¦ PIP-L24-003 ¦ Hydrotest Line 24 kicked off today. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-23 |  |  | update schedule | FALSE | 0.982 | English | test
UPD-01676 | email | MS_Project | 2026-09-08 | OIL-UNIT2-DEMO | Daily Progress: Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Work on Install MCC Panel 3 has begun. Regards, Site Supervisor | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | start | STARTED | 40 | 2026-09-08 |  |  | obtain permit | FALSE | 0.988 | English | test
UPD-01782 | plain_text | document | 2026-09-21 | OIL-UNIT2-DEMO | Progress note: Work on Close scaffold inspection actions restarted today. Material expected tomorrow. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | resumption | RESUMED | 20 | 2026-09-21 |  |  | planner review | FALSE | 0.984 | English | test
UPD-00588 | email | MS_Project | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - PIP-V12-001 Dear Team, Only part of Install Valve V12 could be done today. Regards, Site Supervisor Material expected tomorrow. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | partial_progress | PARTIAL | 40 | 2026-09-03 |  |  | receive material | FALSE | 0.963 | English | test
UPD-00314 | pdf_text | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 18-09-2026 ¦ MEC-T02-001 ¦ Crew resumed Install Tank T02 internals after clearance. For information. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | resumption | RESUMED | 70 | 2026-09-18 |  |  | obtain permit | FALSE | 0.956 | English | test
UPD-00337 | site_diary | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Site Update: Date 2026-09-21 ¦ Pump House ¦ Today's Align Pump P04 activity has been cancelled. Please note. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.946 | English | test
UPD-01669 | word_document | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Today: Daily Site Report Date: 2026-09-25 Discipline: Piping Observation: No start for Hydrotest Line 23 today. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.94 | English | test
UPD-00157 | excel_note | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Unit update: MEC-HX01-001 ¦ Install Heat Exchanger HX01 ¦ RESUMED ¦ NA For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | resumption | RESUMED | 20 | 2026-09-23 |  |  | resume after clearance | FALSE | 0.965 | English | test
UPD-00741 | excel_note | DPR | 2026-09-18 | OIL-UNIT2-DEMO | Site Update: INS-CV11-001 ¦ Install Control Valve CV11 ¦ COMPLETED ¦ NA Please note. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | completion | COMPLETED | 100 | 2026-09-18 | 2026-09-18 |  | receive material | FALSE | 0.946 | English | test
UPD-00161 | excel_note | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | Today: CIV-TK01-001 ¦ Tank T01 foundation completion ¦ BLOCKED ¦ shortage of 24-inch pipes FYI. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | blockage | BLOCKED | 0 |  |  | shortage of 24-inch pipes | receive material | FALSE | 0.947 | English | test
UPD-01075 | site_diary | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | 10-Sep update: Date 2026-09-29 ¦ Unit 2 ¦ Install Unit 2 lighting held up by welding machine under maintenance. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | delay | DELAYED | 80 |  |  | welding machine under maintenance | update schedule | FALSE | 0.904 | English | test
UPD-00236 | plain_text | document | 2026-09-18 | OIL-UNIT2-DEMO | Align Pump P04 kicked off today. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 50 | 2026-09-18 |  |  | obtain permit | FALSE | 0.979 | English | test
UPD-00424 | ms_project_update | MS_Project | 2026-09-07 | OIL-UNIT2-DEMO | MS Project note: INS-T04-001 status = RESUMED. Please note. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | resumption | RESUMED | 70 | 2026-09-07 |  |  | mobilise crew | FALSE | 0.902 | English | test
UPD-00766 | site_diary | email | 2026-09-08 | OIL-UNIT2-DEMO | Date 2026-09-08 ¦ Unit 2 ¦ Work on Install Valve V12 has begun. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-08 |  |  | resume after clearance | FALSE | 0.913 | English | test
UPD-00518 | whatsapp | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Today: Line/area update: today's erect line 24 activity has been cancelled. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.911 | English | test
UPD-01616 | ms_project_update | MS_Project | 2026-09-04 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: INS-JB05-001 status = CANCELLED. For information. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.903 | English | test
UPD-00333 | email | MS_Project | 2026-09-11 | OIL-UNIT2-DEMO | DPR Update: Subject: Daily Progress Update - PIP-L24-003 Dear Team, Hydrotest Line 24 remains on hold due to design revision pending. Regards, Site Supervisor | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | design revision pending | resume after clearance | FALSE | 0.929 | English | test
UPD-01532 | word_document | mobile | 2026-09-28 | OIL-UNIT2-DEMO | Site Update: Daily Site Report Date: 2026-09-28 Discipline: Civil Observation: Execution of Road R02 PCC laying is blocked by insufficient manpower. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | blockage | BLOCKED | 0 |  |  | insufficient manpower | receive material | FALSE | 0.978 | English | test
UPD-01556 | ms_project_update | document | 2026-09-20 | OIL-UNIT2-DEMO | Today: MS Project update: PIP-L24-003 marked 100% complete. Actual Finish: 2026-09-20. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-20 | 2026-09-20 |  | resume after clearance | FALSE | 0.923 | English | test
UPD-01137 | word_document | MS_Project | 2026-09-20 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-20 Discipline: Mechanical Observation: No progress on Install Compressor C01 today due to client approval pending. Planner action required. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 70 |  |  | client approval pending | obtain permit | FALSE | 0.977 | English | test
UPD-00597 | pdf_text | DPR | 2026-09-29 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 29-09-2026 ¦ CIV-F15-003 ¦ Today's Foundation F15 concreting activity has been cancelled. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.936 | English | test
UPD-01772 | ms_project_update | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: MS Project note: CIV-F15-001 progress affected by late material inspection; expected finish to move. Please note. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | late material inspection | continue work | FALSE | 0.928 | English | test
UPD-00415 | voice_transcript | email | 2026-09-14 | OIL-UNIT2-DEMO | Unit update: So, basically, install unit 2 lighting progressing as planned. Material expected tomorrow. | 23 | ELE-LTG02-001 | Install Unit 2 lighting | Electrical | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-14 |  |  | obtain permit | FALSE | 0.942 | English | test
UPD-01022 | email | spreadsheet | 2026-09-16 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - MEC-C01-001 Dear Team, Install Compressor C01 cancelled for today. Regards, Site Supervisor Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | cancellation | CANCELLED | 0 |  |  |  | continue work | FALSE | 0.957 | English | test
UPD-00470 | voice_transcript | MS_Project | 2026-09-18 | OIL-UNIT2-DEMO | Progress note: Uh, partial progress achieved on hydrotest line 24. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | partial_progress | PARTIAL | 30 | 2026-09-18 |  |  | continue work | FALSE | 0.922 | English | test
UPD-00784 | pdf_text | document | 2026-09-24 | OIL-UNIT2-DEMO | Today: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ PIP-V12-001 ¦ Install Valve V12 commenced at Unit 2. For information. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-24 |  |  | obtain permit | FALSE | 0.972 | English | test
UPD-00486 | voice_transcript | DPR | 2026-09-01 | OIL-UNIT2-DEMO | Supervisor update - Just to update you, team finished install compressor c01. For information. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | completion | COMPLETED | 100 | 2026-09-01 | 2026-09-01 |  | receive material | FALSE | 0.939 | English | test
UPD-00519 | email | MS_Project | 2026-09-23 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - INS-JB05-001 Dear Team, Terminate Junction Box JB05 partially completed today. Regards, Site Supervisor FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | partial_progress | PARTIAL | 80 | 2026-09-23 |  |  | mobilise crew | FALSE | 0.989 | English | test
UPD-00188 | word_document | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-23 Discipline: Instrumentation Observation: No progress on Install Control Valve CV11 today due to crane unavailable. Kindly update the plan. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | delay | DELAYED | 40 |  |  | crane unavailable | mobilise crew | FALSE | 0.983 | English | test
UPD-00151 | plain_text | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Today: No progress on Weld Line 23 today due to welding machine under maintenance. FYI. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | delay | DELAYED | 60 |  |  | welding machine under maintenance | complete inspection | FALSE | 0.977 | English | test
UPD-01290 | plain_text | MS_Project | 2026-09-13 | OIL-UNIT2-DEMO | Today: Erect Line 23 progressing as planned. For information. | 7 | PIP-L23-001 | Erect Line 23 | Piping | Unit 2 | progress | IN_PROGRESS | 40 | 2026-09-13 |  |  | resume after clearance | FALSE | 0.975 | English | test
UPD-00130 | voice_transcript | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | Supervisor update - Just to update you, foundation f15 reinforcement has been complete at unit 2. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | completion | COMPLETED | 100 | 2026-09-15 | 2026-09-15 |  | resume after clearance | FALSE | 0.98 | English | test
UPD-01473 | excel_note | spreadsheet | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: MEC-P04-001 ¦ Align Pump P04 ¦ STARTED ¦ NA Material expected tomorrow. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | start | STARTED | 70 | 2026-09-03 |  |  | complete inspection | FALSE | 0.947 | English | test
UPD-01571 | whatsapp | DPR | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Sir, install compressor c01 is delayed because of equipment breakdown. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | delay | DELAYED | 10 |  |  | equipment breakdown | continue work | FALSE | 0.965 | English | test
UPD-00384 | email | document | 2026-09-26 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - HSE-001-001 Dear Team, Complete work-at-height inspection remains on hold due to vendor technician not available. Regards, Site Supervisor For information. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | vendor technician not available | complete inspection | FALSE | 0.917 | English | test
UPD-01536 | plain_text | document | 2026-09-17 | OIL-UNIT2-DEMO | Today: Close scaffold inspection actions is behind plan owing to access road blocked. FYI. | 29 | HSE-002-001 | Close scaffold inspection actions | HSE | Unit 1 | delay | DELAYED | 20 |  |  | access road blocked | update schedule | FALSE | 0.957 | English | test
UPD-01082 | ms_project_update | MS_Project | 2026-09-24 | OIL-UNIT2-DEMO | MS Project note: PIP-L24-001 status = NOT STARTED. Kindly update the plan. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | complete inspection | FALSE | 0.969 | English | test
UPD-01146 | plain_text | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Install Transformer TR02 remains on hold due to drawing approval pending. For information. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | blockage | BLOCKED | 0 |  |  | drawing approval pending | complete inspection | FALSE | 0.939 | English | test
UPD-00671 | pdf_text | mobile | 2026-09-04 | OIL-UNIT2-DEMO | Progress note: DAILY PROGRESS REPORT Project: OIL Unit Expansion 04-09-2026 ¦ MEC-C01-001 ¦ Planned work Install Compressor C01 did not commence. Material expected tomorrow. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | no_start | NOT_STARTED | 0 |  |  |  | obtain permit | FALSE | 0.917 | English | test
UPD-01765 | plain_text | spreadsheet | 2026-09-15 | OIL-UNIT2-DEMO | 10-Sep update: Foundation F15 reinforcement ongoing at Unit 2. Kindly update the plan. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-15 |  |  | planner review | FALSE | 0.978 | English | test
UPD-00590 | plain_text | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Daily Progress: Planned work Weld Line 23 did not commence. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.945 | English | test
UPD-01224 | email | mobile | 2026-09-18 | OIL-UNIT2-DEMO | Today: Subject: Daily Progress Update - PIP-L23-002 Dear Team, Weld Line 23 could not proceed today due to access road blocked. Regards, Site Supervisor For information. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | delay | DELAYED | 50 |  |  | access road blocked | receive material | FALSE | 0.978 | English | test
UPD-01565 | plain_text | email | 2026-09-07 | OIL-UNIT2-DEMO | 10-Sep update: Around 50% work completed on Install Valve V12; balance is ongoing. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-07 |  |  | obtain permit | FALSE | 0.937 | English | test
UPD-01246 | voice_transcript | document | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: So, basically, partial progress achieved on weld line 23. Planner action required. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | partial_progress | PARTIAL | 70 | 2026-09-03 |  |  | complete inspection | FALSE | 0.919 | English | test
UPD-00975 | email | spreadsheet | 2026-09-02 | OIL-UNIT2-DEMO | Progress note: Subject: Daily Progress Update - PIP-L30-001 Dear Team, Install 30-inch header held up by welding machine under maintenance. Regards, Site Supervisor Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | delay | DELAYED | 50 |  |  | welding machine under maintenance | mobilise crew | FALSE | 0.954 | English | test
UPD-01220 | word_document | DPR | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-25 Discipline: Instrumentation Observation: Install Temperature Transmitter T04 progressing as planned. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | progress | IN_PROGRESS | 10 | 2026-09-25 |  |  | update schedule | FALSE | 0.964 | English | test
UPD-00288 | word_document | spreadsheet | 2026-09-25 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-25 Discipline: HSE Observation: Complete work-at-height inspection partially completed today. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 90 | 2026-09-25 |  |  | mobilise crew | FALSE | 0.937 | English | test
UPD-00118 | excel_note | spreadsheet | 2026-09-09 | OIL-UNIT2-DEMO | Daily Progress: MEC-T02-001 ¦ Install Tank T02 internals ¦ COMPLETED ¦ NA Please note. | 18 | MEC-T02-001 | Install Tank T02 internals | Mechanical | Tank Farm | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | mobilise crew | FALSE | 0.924 | English | test
UPD-00949 | whatsapp | mobile | 2026-09-10 | OIL-UNIT2-DEMO | 10-Sep update: Sir, terminate junction box jb05 will not be executed today. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.966 | English | test
UPD-01199 | voice_transcript | site_diary | 2026-09-05 | OIL-UNIT2-DEMO | DPR Update: Uh, crew resumed hydrotest line 24 after clearance. For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 40 | 2026-09-05 |  |  | resume after clearance | FALSE | 0.979 | English | test
UPD-00057 | site_diary | email | 2026-09-06 | OIL-UNIT2-DEMO | Supervisor update - Date 2026-09-06 ¦ Unit 2 ¦ Work on Foundation F15 excavation restarted today. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | resumption | RESUMED | 70 | 2026-09-06 |  |  | continue work | FALSE | 0.976 | English | test
UPD-01511 | voice_transcript | email | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: Just to update you, install temperature transmitter t04 could not proceed today due to insufficient manpower. For information. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | delay | DELAYED | 10 |  |  | insufficient manpower | update schedule | FALSE | 0.907 | English | test
UPD-01762 | whatsapp | email | 2026-09-18 | OIL-UNIT2-DEMO | Unit update: Sir, started install heat exchanger hx01 this morning. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | start | STARTED | 70 | 2026-09-18 |  |  | mobilise crew | FALSE | 0.98 | English | test
UPD-00847 | voice_transcript | site_diary | 2026-09-17 | OIL-UNIT2-DEMO | Today: So, basically, install heat exchanger hx01 is about 70% complete. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | partial_progress | PARTIAL | 70 | 2026-09-17 |  |  | resume after clearance | FALSE | 0.954 | English | test
UPD-01049 | email | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - MEC-P04-001 Dear Team, Team finished Align Pump P04. Regards, Site Supervisor Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | completion | COMPLETED | 100 | 2026-09-21 | 2026-09-21 |  | receive material | FALSE | 0.923 | English | test
UPD-00837 | pdf_text | email | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - DAILY PROGRESS REPORT Project: OIL Unit Expansion 28-09-2026 ¦ MEC-C01-001 ¦ Execution of Install Compressor C01 is blocked by QA/QC hold point not cleared. Kindly update the plan. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | resume after clearance | FALSE | 0.954 | English | test
UPD-01775 | plain_text | DPR | 2026-09-03 | OIL-UNIT2-DEMO | Supervisor update - Install Pressure Transmitter PT08 is about 10% complete. For information. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | partial_progress | PARTIAL | 10 | 2026-09-03 |  |  | complete inspection | FALSE | 0.946 | English | test
UPD-00269 | ms_project_update | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | DPR Update: MS Project note: INS-T04-001 progress affected by matl not received; expected finish to move. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | complete inspection | FALSE | 0.974 | English | test
UPD-01183 | voice_transcript | document | 2026-09-17 | OIL-UNIT2-DEMO | Okay, today's update is that today's install temperature transmitter t04 activity has been cancelled. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | receive material | FALSE | 0.978 | English | test
UPD-01084 | plain_text | email | 2026-09-09 | OIL-UNIT2-DEMO | Supervisor update - Team finished Install Heat Exchanger HX01. For information. | 19 | MEC-HX01-001 | Install Heat Exchanger HX01 | Mechanical | Unit 1 | completion | COMPLETED | 100 | 2026-09-09 | 2026-09-09 |  | complete inspection | FALSE | 0.917 | English | test
UPD-00292 | ms_project_update | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Today: MS Project note: CIV-TK01-001 progress affected by scaffold not ready; expected finish to move. Please note. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | delay | DELAYED | 50 |  |  | scaffold not ready | continue work | FALSE | 0.922 | English | test
UPD-00475 | whatsapp | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Today: Hi, work on weld line 24 restarted today. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 40 | 2026-09-29 |  |  | receive material | FALSE | 0.973 | English | test
UPD-01173 | whatsapp | MS_Project | 2026-09-17 | OIL-UNIT2-DEMO | Site Update: Line/area update: terminate junction box jb05 resumed today after shortage of 24-inch pipes was cleared. Kindly update the plan. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | resumption | RESUMED | 20 | 2026-09-17 |  |  | receive material | FALSE | 0.959 | English | test
UPD-00541 | plain_text | document | 2026-09-07 | OIL-UNIT2-DEMO | Site Update: Install Pump P03 resumed today after work permit not issued was cleared. Kindly update the plan. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | resumption | RESUMED | 80 | 2026-09-07 |  |  | complete inspection | FALSE | 0.988 | English | test
UPD-00079 | ms_project_update | document | 2026-09-25 | OIL-UNIT2-DEMO | 10-Sep update: MS Project note: INS-PT08-001 progress affected by drawing approval pending; expected finish to move. Kindly update the plan. | 25 | INS-PT08-001 | Install Pressure Transmitter PT08 | Instrumentation | Unit 1 | blockage | BLOCKED | 0 |  |  | drawing approval pending | obtain permit | FALSE | 0.941 | English | test
UPD-00786 | plain_text | spreadsheet | 2026-09-29 | OIL-UNIT2-DEMO | Install Compressor C01 partially completed today. | 17 | MEC-C01-001 | Install Compressor C01 | Mechanical | Compressor Area | partial_progress | PARTIAL | 10 | 2026-09-29 |  |  | complete inspection | FALSE | 0.949 | English | test
UPD-00405 | email | email | 2026-09-28 | OIL-UNIT2-DEMO | Supervisor update - Subject: Daily Progress Update - ELE-MCC03-001 Dear Team, Install MCC Panel 3 done at site. Regards, Site Supervisor Please note. | 20 | ELE-MCC03-001 | Install MCC Panel 3 | Electrical | Electrical Room | completion | COMPLETED | 100 | 2026-09-28 | 2026-09-28 |  | obtain permit | FALSE | 0.926 | English | test
UPD-00747 | word_document | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | Daily Progress: Daily Site Report Date: 2026-09-21 Discipline: Piping Observation: Install 30-inch header completed today. Kindly update the plan. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-21 | 2026-09-21 |  | planner review | FALSE | 0.946 | English | test
UPD-00785 | plain_text | site_diary | 2026-09-15 | OIL-UNIT2-DEMO | Unit update: No start for Terminate Junction Box JB05 today. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | update schedule | FALSE | 0.98 | English | test
UPD-01262 | site_diary | mobile | 2026-09-21 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-21 ¦ Tank Farm ¦ Partial progress achieved on Tank T01 foundation completion. Planner action required. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 25 | 2026-09-21 |  |  | continue work | FALSE | 0.938 | English | test
UPD-01768 | voice_transcript | DPR | 2026-09-23 | OIL-UNIT2-DEMO | DPR Update: So, basically, partial progress achieved on complete work-at-height inspection. FYI. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | partial_progress | PARTIAL | 10 | 2026-09-23 |  |  | update schedule | FALSE | 0.909 | English | test
UPD-00208 | ms_project_update | DPR | 2026-09-21 | OIL-UNIT2-DEMO | Unit update: MS Project note: PIP-L24-001 progress affected by insufficient manpower; expected finish to move. Planner action required. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | insufficient manpower | resume after clearance | FALSE | 0.94 | English | test
UPD-01503 | whatsapp | spreadsheet | 2026-09-24 | OIL-UNIT2-DEMO | Today: Hi, foundation f15 reinforcement resumed today after valve not available at site was cleared. Material expected tomorrow. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | resumption | RESUMED | 80 | 2026-09-24 |  |  | planner review | FALSE | 0.926 | English | test
UPD-01394 | word_document | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-29 Discipline: Civil Observation: Execution of Foundation F15 excavation is blocked by safety clearance pending. For information. | 1 | CIV-F15-001 | Foundation F15 excavation | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | planner review | FALSE | 0.905 | English | test
UPD-01088 | email | DPR | 2026-09-06 | OIL-UNIT2-DEMO | Site Update: Subject: Daily Progress Update - PIP-L23-002 Dear Team, No start for Weld Line 23 today. Regards, Site Supervisor Please note. | 8 | PIP-L23-002 | Weld Line 23 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | receive material | FALSE | 0.965 | English | test
UPD-00297 | voice_transcript | email | 2026-09-03 | OIL-UNIT2-DEMO | Site Update: Okay, today's update is that install pump p03 is in progress. For information. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | progress | IN_PROGRESS | 50 | 2026-09-03 |  |  | update schedule | FALSE | 0.92 | English | test
UPD-00262 | plain_text | document | 2026-09-13 | OIL-UNIT2-DEMO | Unit update: Terminate Junction Box JB05 is blocked pending access road blocked. FYI. | 27 | INS-JB05-001 | Terminate Junction Box JB05 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | access road blocked | obtain permit | FALSE | 0.905 | English | test
UPD-00056 | whatsapp | document | 2026-09-27 | OIL-UNIT2-DEMO | 10-Sep update: No start for Erect Line 24 today. 👍 FYI. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | continue work | FALSE | 0.907 | English | test
UPD-01234 | pdf_text | document | 2026-09-12 | OIL-UNIT2-DEMO | DPR Update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 12-09-2026 ¦ PIP-V12-001 ¦ Install Valve V12 has not started yet. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | no_start | NOT_STARTED | 0 |  |  |  | resume after clearance | FALSE | 0.907 | English | test
UPD-01464 | whatsapp | DPR | 2026-09-22 | OIL-UNIT2-DEMO | Supervisor update - Sir, hydrotest line 24 has resumed following resolution of the earlier issue. Kindly update the plan. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | resumption | RESUMED | 40 | 2026-09-22 |  |  | resume after clearance | FALSE | 0.964 | English | test
UPD-00654 | plain_text | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Today: Install Transformer TR02 started today. Planner action required. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | start | STARTED | 60 | 2026-09-06 |  |  | complete inspection | FALSE | 0.939 | English | test
UPD-01240 | whatsapp | DPR | 2026-09-22 | OIL-UNIT2-DEMO | 10-Sep update: Hi, execution of install pump p03 is blocked by late material inspection. Planner action required. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | late material inspection | continue work | FALSE | 0.91 | English | test
UPD-00688 | whatsapp | DPR | 2026-09-23 | OIL-UNIT2-DEMO | Supervisor update - Hi, install pump p03 commenced at pump house. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 20 | 2026-09-23 |  |  | complete inspection | FALSE | 0.989 | English | test
UPD-01368 | word_document | document | 2026-09-19 | OIL-UNIT2-DEMO | Daily Site Report Date: 2026-09-19 Discipline: Electrical Observation: Execution of Lay Cable Route 7 is blocked by QA/QC hold point not cleared. | 21 | ELE-CBL07-001 | Lay Cable Route 7 | Electrical | Unit 2 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | complete inspection | FALSE | 0.909 | English | test
UPD-01202 | word_document | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-07 Discipline: Civil Observation: Around 50% work completed on Foundation F15 concreting; balance is ongoing. Please note. | 3 | CIV-F15-003 | Foundation F15 concreting | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-07 |  |  | update schedule | FALSE | 0.924 | English | test
UPD-01203 | ms_project_update | email | 2026-09-25 | OIL-UNIT2-DEMO | MS Project update: MEC-P03-001 actual start = 2026-09-25; work commenced. Material expected tomorrow. | 15 | MEC-P03-001 | Install Pump P03 | Mechanical | Pump House | start | STARTED | 10 | 2026-09-25 |  |  | obtain permit | FALSE | 0.955 | English | test
UPD-01118 | voice_transcript | site_diary | 2026-09-18 | OIL-UNIT2-DEMO | DPR Update: Just to update you, install control valve cv11 remains on hold due to equipment breakdown. FYI. | 26 | INS-CV11-001 | Install Control Valve CV11 | Instrumentation | Unit 2 | blockage | BLOCKED | 0 |  |  | equipment breakdown | receive material | FALSE | 0.913 | English | test
UPD-00182 | word_document | mobile | 2026-09-13 | OIL-UNIT2-DEMO | 10-Sep update: Daily Site Report Date: 2026-09-13 Discipline: Piping Observation: Erect Line 24 completed today. Please note. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-13 | 2026-09-13 |  | complete inspection | FALSE | 0.982 | English | test
UPD-01442 | voice_transcript | site_diary | 2026-09-23 | OIL-UNIT2-DEMO | Daily Progress: Just to update you, install temperature transmitter t04 kicked off today. Kindly update the plan. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | start | STARTED | 80 | 2026-09-23 |  |  | update schedule | FALSE | 0.93 | English | test
UPD-01434 | pdf_text | document | 2026-09-24 | OIL-UNIT2-DEMO | Unit update: DAILY PROGRESS REPORT Project: OIL Unit Expansion 24-09-2026 ¦ PIP-L23-003 ¦ Hydrotest Line 23 has been done at Unit 2. FYI. | 9 | PIP-L23-003 | Hydrotest Line 23 | Piping | Unit 2 | completion | COMPLETED | 100 | 2026-09-24 | 2026-09-24 |  | planner review | FALSE | 0.964 | English | test
UPD-01609 | plain_text | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Site Update: Around 50% work completed on Erect Line 24; balance is ongoing. For information. | 10 | PIP-L24-001 | Erect Line 24 | Piping | Unit 2 | progress | IN_PROGRESS | 20 | 2026-09-16 |  |  | continue work | FALSE | 0.95 | English | test
UPD-01211 | site_diary | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-06 ¦ Unit 2 ¦ Install Temperature Transmitter T04 will not be executed today. FYI. | 24 | INS-T04-001 | Install Temperature Transmitter T04 | Instrumentation | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.936 | English | test
UPD-01689 | word_document | MS_Project | 2026-09-27 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-27 Discipline: Mechanical Observation: Execution of Align Pump P04 is blocked by work permit not issued. Planner action required. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | work permit not issued | complete inspection | FALSE | 0.914 | English | test
UPD-01572 | email | DPR | 2026-09-13 | OIL-UNIT2-DEMO | Subject: Daily Progress Update - PIP-L24-002 Dear Team, Weld Line 24 remains on hold due to safety clearance pending. Regards, Site Supervisor For information. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | safety clearance pending | update schedule | FALSE | 0.932 | English | test
UPD-00280 | ms_project_update | site_diary | 2026-09-03 | OIL-UNIT2-DEMO | Today: MS Project note: CIV-R02-002 status = NOT STARTED. Kindly update the plan. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | no_start | NOT_STARTED | 0 |  |  |  | mobilise crew | FALSE | 0.916 | English | test
UPD-00124 | excel_note | mobile | 2026-09-13 | OIL-UNIT2-DEMO | DPR Update: PIP-L24-002 ¦ Weld Line 24 ¦ STARTED ¦ NA Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | start | STARTED | 10 | 2026-09-13 |  |  | obtain permit | FALSE | 0.909 | English | test
UPD-00883 | word_document | site_diary | 2026-09-10 | OIL-UNIT2-DEMO | Progress note: Daily Site Report Date: 2026-09-10 Discipline: Civil Observation: Execution of Foundation F15 reinforcement is blocked by work permit not issued. Please note. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | blockage | BLOCKED | 0 |  |  | work permit not issued | receive material | FALSE | 0.959 | English | test
UPD-00638 | plain_text | spreadsheet | 2026-09-12 | OIL-UNIT2-DEMO | Supervisor update - Cannot continue Complete work-at-height inspection until material not received is resolved. | 28 | HSE-001-001 | Complete work-at-height inspection | HSE | Unit 2 | blockage | BLOCKED | 0 |  |  | material not received | continue work | FALSE | 0.947 | English | test
UPD-00291 | excel_note | email | 2026-09-01 | OIL-UNIT2-DEMO | DPR Update: PIP-L24-003 ¦ Hydrotest Line 24 ¦ STARTED ¦ NA For information. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | start | STARTED | 80 | 2026-09-01 |  |  | planner review | FALSE | 0.946 | English | test
UPD-01728 | ms_project_update | spreadsheet | 2026-09-07 | OIL-UNIT2-DEMO | DPR Update: MS Project note: CIV-R02-002 status = CANCELLED. For information. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | cancellation | CANCELLED | 0 |  |  |  | planner review | FALSE | 0.989 | English | test
UPD-00479 | site_diary | site_diary | 2026-09-09 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-09 ¦ Tank Farm ¦ Partial progress achieved on Tank T01 foundation completion. | 6 | CIV-TK01-001 | Tank T01 foundation completion | Civil | Tank Farm | partial_progress | PARTIAL | 75 | 2026-09-09 |  |  | complete inspection | FALSE | 0.971 | English | test
UPD-00020 | voice_transcript | site_diary | 2026-09-29 | OIL-UNIT2-DEMO | Site Update: So, basically, install 30-inch header is blocked pending qa/qc hold point not cleared. For information. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | blockage | BLOCKED | 0 |  |  | QA/QC hold point not cleared | complete inspection | FALSE | 0.949 | English | test
UPD-00251 | excel_note | mobile | 2026-09-11 | OIL-UNIT2-DEMO | DPR Update: CIV-F15-002 ¦ Foundation F15 reinforcement ¦ IN PROGRESS ¦ NA Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | progress | IN_PROGRESS | 30 | 2026-09-11 |  |  | obtain permit | FALSE | 0.906 | English | test
UPD-01388 | word_document | DPR | 2026-09-02 | OIL-UNIT2-DEMO | DPR Update: Daily Site Report Date: 2026-09-02 Discipline: Civil Observation: Road R02 PCC laying held up by power supply interruption. FYI. | 5 | CIV-R02-002 | Road R02 PCC laying | Civil | Plant Area | delay | DELAYED | 80 |  |  | power supply interruption | continue work | FALSE | 0.986 | English | test
UPD-00409 | whatsapp | spreadsheet | 2026-09-18 | OIL-UNIT2-DEMO | Sir, install valve v12 progressing as planned. FYI. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 70 | 2026-09-18 |  |  | update schedule | FALSE | 0.917 | English | test
UPD-01672 | whatsapp | MS_Project | 2026-09-06 | OIL-UNIT2-DEMO | Line/area update: install 30-inch header has been completed at unit 1. Material expected tomorrow. | 13 | PIP-L30-001 | Install 30-inch header | Piping | Unit 1 | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | receive material | FALSE | 0.978 | English | test
UPD-00216 | email | spreadsheet | 2026-09-06 | OIL-UNIT2-DEMO | Unit update: Subject: Daily Progress Update - MEC-P04-001 Dear Team, Align Pump P04 ongoing at Pump House. Regards, Site Supervisor | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | progress | IN_PROGRESS | 80 | 2026-09-06 |  |  | planner review | FALSE | 0.932 | English | test
UPD-01204 | plain_text | mobile | 2026-09-16 | OIL-UNIT2-DEMO | Unit update: Today's Foundation F15 reinforcement activity has been cancelled. Planner action required. | 2 | CIV-F15-002 | Foundation F15 reinforcement | Civil | Unit 2 | cancellation | CANCELLED | 0 |  |  |  | update schedule | FALSE | 0.91 | English | test
UPD-00544 | site_diary | site_diary | 2026-09-06 | OIL-UNIT2-DEMO | Daily Progress: Date 2026-09-06 ¦ Substation ¦ Supervisor confirms Install Transformer TR02 completed. Kindly update the plan. | 22 | ELE-TR02-001 | Install Transformer TR02 | Electrical | Substation | completion | COMPLETED | 100 | 2026-09-06 | 2026-09-06 |  | continue work | FALSE | 0.975 | English | test
UPD-00164 | ms_project_update | MS_Project | 2026-09-21 | OIL-UNIT2-DEMO | MS Project note: PIP-L24-003 progress affected by valve not available at site; expected finish to move. Planner action required. | 12 | PIP-L24-003 | Hydrotest Line 24 | Piping | Unit 2 | blockage | BLOCKED | 0 |  |  | valve not available at site | obtain permit | FALSE | 0.984 | English | test
UPD-01545 | voice_transcript | MS_Project | 2026-09-30 | OIL-UNIT2-DEMO | Daily Progress: Uh, install valve v12 is in progress. Kindly update the plan. | 14 | PIP-V12-001 | Install Valve V12 | Piping | Unit 2 | progress | IN_PROGRESS | 50 | 2026-09-30 |  |  | planner review | FALSE | 0.929 | English | test
UPD-00460 | site_diary | email | 2026-09-20 | OIL-UNIT2-DEMO | Progress note: Date 2026-09-20 ¦ Pump House ¦ Align Pump P04 remains on hold due to vendor technician not available. FYI. | 16 | MEC-P04-001 | Align Pump P04 | Mechanical | Pump House | blockage | BLOCKED | 0 |  |  | vendor technician not available | planner review | FALSE | 0.985 | English | test
UPD-01605 | ms_project_update | document | 2026-09-07 | OIL-UNIT2-DEMO | Supervisor update - MS Project note: PIP-L24-002 status = RESUMED. Planner action required. | 11 | PIP-L24-002 | Weld Line 24 | Piping | Unit 2 | resumption | RESUMED | 60 | 2026-09-07 |  |  | mobilise crew | FALSE | 0.926 | English | test

## Ambiguous_Review
record_id | source_modality | raw_input | candidate_activity_codes | expected_decision | ambiguity_reason | gold_status | gold_event_type
AMB-0001 | whatsapp | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | completion
AMB-0002 | site_diary | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | completion
AMB-0003 | email | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | completion
AMB-0004 | voice_transcript | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0005 | voice_transcript | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | progress
AMB-0006 | word_document | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | progress
AMB-0007 | pdf_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | progress
AMB-0008 | word_document | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | completion
AMB-0009 | whatsapp | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | start
AMB-0010 | excel_note | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | completion
AMB-0011 | word_document | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | start
AMB-0012 | email | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | COMPLETED | completion
AMB-0013 | whatsapp | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | progress
AMB-0014 | site_diary | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | progress
AMB-0015 | email | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | start
AMB-0016 | voice_transcript | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | completion
AMB-0017 | ms_project_update | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | progress
AMB-0018 | whatsapp | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | start
AMB-0019 | pdf_text | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | progress
AMB-0020 | excel_note | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0021 | plain_text | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0022 | voice_transcript | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | COMPLETED | progress
AMB-0023 | voice_transcript | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | completion
AMB-0024 | word_document | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | start
AMB-0025 | email | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | completion
AMB-0026 | site_diary | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | progress
AMB-0027 | voice_transcript | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | STARTED | start
AMB-0028 | ms_project_update | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | completion
AMB-0029 | site_diary | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | STARTED | completion
AMB-0030 | excel_note | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | start
AMB-0031 | site_diary | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0032 | site_diary | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | progress
AMB-0033 | plain_text | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | STARTED | completion
AMB-0034 | voice_transcript | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | start
AMB-0035 | email | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | completion
AMB-0036 | word_document | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | start
AMB-0037 | email | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | start
AMB-0038 | ms_project_update | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | IN_PROGRESS | progress
AMB-0039 | plain_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | completion
AMB-0040 | email | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0041 | email | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | COMPLETED | completion
AMB-0042 | word_document | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | COMPLETED | progress
AMB-0043 | pdf_text | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | progress
AMB-0044 | pdf_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | completion
AMB-0045 | plain_text | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | progress
AMB-0046 | pdf_text | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | STARTED | start
AMB-0047 | plain_text | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | STARTED | start
AMB-0048 | pdf_text | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | progress
AMB-0049 | word_document | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | progress
AMB-0050 | site_diary | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0051 | plain_text | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | start
AMB-0052 | site_diary | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | completion
AMB-0053 | site_diary | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | progress
AMB-0054 | ms_project_update | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0055 | site_diary | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | progress
AMB-0056 | excel_note | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0057 | voice_transcript | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | STARTED | start
AMB-0058 | excel_note | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | start
AMB-0059 | whatsapp | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0060 | pdf_text | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | start
AMB-0061 | whatsapp | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | progress
AMB-0062 | excel_note | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | IN_PROGRESS | progress
AMB-0063 | email | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | IN_PROGRESS | completion
AMB-0064 | voice_transcript | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0065 | plain_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | completion
AMB-0066 | ms_project_update | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | progress
AMB-0067 | whatsapp | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0068 | site_diary | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | IN_PROGRESS | start
AMB-0069 | excel_note | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | STARTED | start
AMB-0070 | pdf_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | progress
AMB-0071 | pdf_text | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | start
AMB-0072 | site_diary | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | IN_PROGRESS | completion
AMB-0073 | whatsapp | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | completion
AMB-0074 | pdf_text | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0075 | plain_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | completion
AMB-0076 | plain_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | progress
AMB-0077 | excel_note | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | completion
AMB-0078 | word_document | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | IN_PROGRESS | start
AMB-0079 | pdf_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | completion
AMB-0080 | excel_note | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0081 | ms_project_update | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | progress
AMB-0082 | plain_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0083 | plain_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | progress
AMB-0084 | word_document | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | start
AMB-0085 | whatsapp | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | progress
AMB-0086 | site_diary | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | start
AMB-0087 | ms_project_update | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | COMPLETED | completion
AMB-0088 | voice_transcript | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | progress
AMB-0089 | excel_note | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | start
AMB-0090 | ms_project_update | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | progress
AMB-0091 | word_document | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | start
AMB-0092 | word_document | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | COMPLETED | progress
AMB-0093 | email | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | STARTED | start
AMB-0094 | word_document | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0095 | site_diary | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | STARTED | start
AMB-0096 | site_diary | Inspection completed. | HSE-001-001 ¦ HSE-002-001 | HUMAN_REVIEW | Inspection type/location unclear | COMPLETED | completion
AMB-0097 | ms_project_update | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | completion
AMB-0098 | whatsapp | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | progress
AMB-0099 | pdf_text | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | completion
AMB-0100 | ms_project_update | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | STARTED | progress
AMB-0101 | ms_project_update | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | COMPLETED | start
AMB-0102 | word_document | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | COMPLETED | start
AMB-0103 | ms_project_update | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0104 | voice_transcript | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | completion
AMB-0105 | word_document | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | completion
AMB-0106 | voice_transcript | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | COMPLETED | progress
AMB-0107 | word_document | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | STARTED | completion
AMB-0108 | pdf_text | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start
AMB-0109 | site_diary | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | start
AMB-0110 | excel_note | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | completion
AMB-0111 | voice_transcript | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | COMPLETED | start
AMB-0112 | voice_transcript | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | STARTED | start
AMB-0113 | pdf_text | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | IN_PROGRESS | completion
AMB-0114 | email | Pump work started. | MEC-P03-001 ¦ MEC-P04-001 | HUMAN_REVIEW | Pump identity missing | IN_PROGRESS | progress
AMB-0115 | ms_project_update | Line 23 activity is progressing. | PIP-L23-001 ¦ PIP-L23-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | progress
AMB-0116 | excel_note | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | COMPLETED | completion
AMB-0117 | ms_project_update | Valve work finished in Unit 2. | PIP-V12-001 ¦ INS-CV11-001 | HUMAN_REVIEW | Could refer to piping valve or control valve | IN_PROGRESS | progress
AMB-0118 | whatsapp | Foundation work is complete. | CIV-F15-003 ¦ CIV-TK01-001 | HUMAN_REVIEW | Foundation identity missing | STARTED | start
AMB-0119 | ms_project_update | Unit 2 electrical work ongoing. | ELE-CBL07-001 ¦ ELE-LTG02-001 | HUMAN_REVIEW | Activity too broad | STARTED | start
AMB-0120 | pdf_text | Line 24 work completed today. | PIP-L24-001 ¦ PIP-L24-002 | HUMAN_REVIEW | Ambiguous between erection and welding | IN_PROGRESS | start

## Unmatched_New
record_id | source_modality | raw_input | candidate_activity_codes | expected_decision | ambiguity_reason
NEW-0001 | excel_note | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0002 | word_document | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0003 | word_document | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0004 | site_diary | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0005 | plain_text | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0006 | email | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0007 | site_diary | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0008 | pdf_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0009 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0010 | whatsapp | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0011 | whatsapp | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0012 | plain_text | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0013 | word_document | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0014 | site_diary | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0015 | excel_note | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0016 | whatsapp | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0017 | whatsapp | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0018 | whatsapp | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0019 | voice_transcript | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0020 | site_diary | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0021 | excel_note | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0022 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0023 | email | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0024 | word_document | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0025 | word_document | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0026 | email | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0027 | word_document | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0028 | ms_project_update | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0029 | voice_transcript | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0030 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0031 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0032 | ms_project_update | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0033 | email | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0034 | pdf_text | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0035 | whatsapp | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0036 | email | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0037 | pdf_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0038 | plain_text | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0039 | plain_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0040 | voice_transcript | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0041 | word_document | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0042 | email | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0043 | email | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0044 | site_diary | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0045 | excel_note | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0046 | pdf_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0047 | pdf_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0048 | email | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0049 | pdf_text | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0050 | voice_transcript | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0051 | ms_project_update | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0052 | whatsapp | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0053 | excel_note | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0054 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0055 | excel_note | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0056 | voice_transcript | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0057 | pdf_text | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0058 | email | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0059 | email | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0060 | excel_note | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0061 | pdf_text | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0062 | site_diary | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0063 | voice_transcript | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0064 | word_document | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0065 | pdf_text | Temporary lighting arrangement completed in laydown area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0066 | site_diary | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0067 | excel_note | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0068 | email | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0069 | word_document | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0070 | whatsapp | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0071 | site_diary | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0072 | whatsapp | Vendor mobilised for nitrogen package installation. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0073 | pdf_text | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0074 | word_document | Temporary access platform erected near Unit 3. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0075 | ms_project_update | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0076 | pdf_text | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0077 | whatsapp | New cable tray route installed in Area C. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0078 | voice_transcript | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0079 | email | Additional support steel installed near the flare area. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity
NEW-0080 | excel_note | New drainage trench started behind warehouse. |  | UNMATCHED_NEW_ACTIVITY | No sufficiently similar planned L5/L6 activity

## Intent_Taxonomy
intent_code | definition | common_language
START | Work/activity has begun | started, commenced, began, mobilised
PROGRESS | Work is ongoing or partially complete | in progress, ongoing, 50%, progressing
COMPLETION | Work is finished | completed, done, finished, 100%
DELAY | Planned work is delayed | delayed, could not proceed, behind plan
BLOCKAGE | Work cannot continue until dependency is resolved | blocked, on hold, pending
RESUMPTION | Previously stopped work has restarted | resumed, restarted, recommenced
CANCELLATION | Planned activity cancelled | cancelled, called off
NO_START | Planned activity did not begin | not started, did not commence
QUERY | Information is requested rather than reported | please confirm, status?, what is the update
CORRECTION | Previously reported information is corrected | correction, revise, earlier update was wrong

## Event_Taxonomy
event_type | meaning | status_mapping
start | Actual start detected | STARTED
progress | Progress/percentage detected | IN_PROGRESS/PARTIAL
completion | Actual completion detected | COMPLETED
delay | Delay/variance detected | DELAYED
blockage | Blocking dependency detected | BLOCKED
resumption | Work restart detected | RESUMED
cancellation | Cancellation detected | CANCELLED
no_start | No-start condition detected | NOT_STARTED